## Read Me
Pre-Construction Commercial Register
What this is | The 175 retained items in your pre-construction commercial pack, mapped into the purpose-built folder structure. The 55 documents marked as not required were removed from the stage checklists and Master Register.
Why a new tree | Your earlier folder structure was designed for the construction/delivery phase (Monthly Management, Subcontractor valuations, Close Out). It doesn't fit a pre-construction pack — half its folders would be empty and many pre-con documents had no home. This tree fixes that. Your construction-phase tree is untouched; use it once the job starts on site.
Sheets | Stage 1 / 2 / 3 — updated phase checklists (Bid, Award, Pre-Con). / Master Register — all 175 retained items with folder columns (T–Y). / Pre-Con Folder Structure and Folder Coverage — live counts by folder. / Dashboard — live totals and workstream analysis.
Naming | PROJ-MCR-CM-[TYPE]-[####]_[Title]. Every folder has a unique TYPE code (no collisions). Set the real project code per job — find-and-replace PROJ in column W.
Stages vs folders | Folder = where a document lives for its whole life (fixed). Stage = which phase it must be cleared by (a filter). They're independent, so nothing gets renamed as it moves between Stages.
Owners | Mapped to your four-person team (Samar / Javeria / Madiha), with CM approving all.
Still to confirm | Confirm whether the retained Project Bank Account / Escrow Requirements item belongs in folder 6.30; the struck tax, CIS and credit-risk documents have been removed.

## Stage 1 - Bid & Tender
Stage 1 - Bid & Tender
11 items · 8 Critical · 4 go to client
Everything needed to win the main contract. Only the shaded 'goes to client' rows physically go out; the rest are internal tender records kept as the priced baseline.
Ref | Document / Control | Goes to client? | Workstream | Priority | Stage / Stage | Folder (L1 › L2) | TYPE | Proposed File Name | Owner
PC-A-001 | Client ITT / Tender Documents (as issued) | Internal record | Tender & Bid Baseline | Critical | Tender receipt | 1.0 › 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0001_ClientITT | QS
PC-A-002 | Tender Addenda / Bulletin Register | Internal record | Tender & Bid Baseline | Critical | Tender period | 1.0 › 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0004_TenderAddenda | QS
PC-A-003 | Tender Clarifications and RFI Log | Internal record | Tender & Bid Baseline | Critical | Tender period | 1.0 › 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0005_TenderClarificationsRFILog | QS
PC-A-006 | Priced Tender Submission (full build-up) | Yes — goes to client | Tender & Bid Baseline | Critical | Tender submission | 1.0 › 1.20 Priced Bid & Assumptions | BID | PROJ-MCR-CM-BID-0001_PricedTenderSubmission | QS
PC-A-007 | Tender Qualifications, Exclusions and Assumptions Schedule | Yes — goes to client | Tender & Bid Baseline | Critical | Tender submission | 1.0 › 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0001_TenderQualifications | QS
PC-A-008 | Tender Baseline Programme | Yes — goes to client | Tender & Bid Baseline | Critical | Tender submission | 1.0 › 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0002_TenderBaselineProgramme | QS
PC-A-009 | Tender Adjudication / Settlement Summary | Internal record | Tender & Bid Baseline | Critical | Tender submission | 1.0 › 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0003_TenderAdjudication | QS
PC-A-010 | Tender Risk and Opportunity Schedule | Internal record | Tender & Bid Baseline | Critical | Tender submission | 1.0 › 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0004_TenderRiskOpportunitySchedule | QS
PC-A-004 | Site Visit / Existing Conditions Record | Internal record | Tender & Bid Baseline | High | Tender period | 1.0 › 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0006_SiteVisit | QS
PC-A-005 | Tender Return Requirements Checklist | Internal record | Tender & Bid Baseline | High | Tender period | 1.0 › 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0007_TenderReturnRequirementsChecklist | QS
PC-A-011 | Bid Bonds / Tender Security Record | Yes — goes to client | Tender & Bid Baseline | High | Tender submission | 1.0 › 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0005_BidBonds | QS

## Stage 2 - Contract Award
Stage 2 - Contract Award
19 items · 14 Critical
Everything to close and sign — including cross-cutting items (LADs, insurance exclusions, ground risk, S106, funding) that must be resolved before execution.
Ref | Document / Control | Workstream | Priority | Stage / Stage | Folder (L1 › L2) | TYPE | Proposed File Name | Owner
PC-B-001 | Contract-vs-Tender Reconciliation | Contract Formation | Critical | Pre-contract | 2.0 › 2.20 Tender-to-Contract Reconciliation | T2C | PROJ-MCR-CM-T2C-0001_ContractVsTenderReconciliation | CM
PC-B-002 | Executed Building Contract | Contract Formation | Critical | Contract execution | 2.0 › 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0001_ExecutedBuildingContract | CM
PC-B-003 | Contract Particulars Register | Contract Formation | Critical | Contract execution | 2.0 › 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0002_ContractParticularsRegister | CM
PC-B-004 | Contractor’s Proposals Register | Contract Formation | Critical | Pre-contract | 2.0 › 2.40 ER / CP & Compliance | ERCP | PROJ-MCR-CM-ERCP-0002_ContractorSProposalsRegister | PCC
PC-B-005 | ER/CP Compliance and Divergence Matrix | Contract Formation | Critical | Pre-contract | 2.0 › 2.40 ER / CP & Compliance | ERCP | PROJ-MCR-CM-ERCP-0003_ER | PCC
PC-B-006 | Contract Sum Analysis / Contract Sum Breakdown | Contract Formation | Critical | Contract execution | 2.0 › 2.60 Contract Pricing Basis | CPB | PROJ-MCR-CM-CPB-0001_ContractSumAnalysis | QS
PC-B-007 | Pricing Document / Bill of Quantities / Schedule of Rates | Contract Formation | Critical | Contract execution | 2.0 › 2.60 Contract Pricing Basis | CPB | PROJ-MCR-CM-CPB-0002_PricingDocument | QS
PC-B-008 | Contract Data / Scope / Works Information (NEC where applicable) | Contract Formation | Critical | Contract execution | 2.0 › 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0004_ContractData | CM
PC-B-009 | Letter of Intent Register and Authority | Contract Formation | Critical | Pre-contract | 2.0 › 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0001_LetterIntentRegisterAuthority | CM
PC-B-011 | Contract Approval / DeleStaged Authority Sign-Off | Contract Formation | Critical | Before execution | 2.0 › 2.20 Tender-to-Contract Reconciliation | T2C | PROJ-MCR-CM-T2C-0004_ContractApproval | CM
PC-B-012 | Key Contract Dates and Notices Schedule | Contract Formation | Critical | Contract execution | 2.0 › 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0005_KeyContractDatesNoticesSchedule | CM
PC-D-020 | Reconciliation to Client Budget / Funding Limit | Cost Planning & Budget | Critical | Pre-contract | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0008_ReconciliationClientBudget | QS
PC-H-001 | Client Payment Schedule | Cashflow, Payment & Tax | Critical | Contract execution | 6.0 › 6.10 Payment Framework | PYF | PROJ-MCR-CM-PYF-0001_ClientPaymentSchedule | QS
PC-H-003 | Working Capital and Peak Funding Assessment | Cashflow, Payment & Tax | Critical | Pre-contract | 6.0 › 6.20 Cashflow & Funding | CFF | PROJ-MCR-CM-CFF-0002_WorkingCapitalPeakFundingAssessment | PCC
PC-B-010 | Pre-Contract Services Agreement and Fee Tracker | Contract Formation | High | PCSA | 2.0 › 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0002_PreContractServicesAgreementFee | CM
PC-B-013 | Dispute Resolution and Governing Law Summary | Contract Formation | High | Contract execution | 2.0 › 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0003_DisputeResolutionGoverningLawSummary | CM
PC-B-014 | Assignment, Novation and Change of Control Requirements | Contract Formation | High | Before execution | 2.0 › 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0005_Assignment | CM
PC-D-012 | Inflation / Escalation Assessment | Cost Planning & Budget | High | Pre-contract | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0001_Inflation | QS
PC-M-002 | Section 106 / Community Infrastructure Levy Schedule | Property, Statutory & Third Parties | High | Pre-contract | 10.0 › 10.10 Planning & Statutory Obligations | STA | PROJ-MCR-CM-STA-0002_Section106 | PCC

## Stage 3 - Pre-Construction
Stage 3 - Pre-Construction
145 items · 69 Critical
Everything to get ready to build once won. Almost all internal.
Ref | Document / Control | Workstream | Priority | Stage / Stage | Folder (L1 › L2) | TYPE | Proposed File Name | Owner
PC-C-001 | Project Scope Responsibility Matrix | Scope & Design Cost Control | Critical | Pre-construction | 3.0 › 3.10 Scope Definition & Interfaces | SCP | PROJ-MCR-CM-SCP-0001_ProjectScopeResponsibilityMatrix | PCC
PC-C-002 | Subcontract Package Matrix | Scope & Design Cost Control | Critical | Pre-construction | 3.0 › 3.10 Scope Definition & Interfaces | SCP | PROJ-MCR-CM-SCP-0002_SubcontractPackageMatrix | PCC
PC-C-003 | Package Interface Matrix | Scope & Design Cost Control | Critical | Pre-construction | 3.0 › 3.10 Scope Definition & Interfaces | SCP | PROJ-MCR-CM-SCP-0003_PackageInterfaceMatrix | PCC
PC-C-004 | Design-to-Cost Tracker | Scope & Design Cost Control | Critical | Design development | 3.0 › 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0001_DesignCostTracker | QS
PC-C-005 | Cost Check at Design Stage | Scope & Design Cost Control | Critical | Each design Stage | 3.0 › 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0002_CostCheckAtDesignStage | QS
PC-C-009 | Consultant Appointment and Scope Review | Scope & Design Cost Control | Critical | Pre-construction | 3.0 › 3.40 Consultant Appointments | CNS | PROJ-MCR-CM-CNS-0001_ConsultantAppointmentScopeReview | CA
PC-C-012 | Testing, Commissioning and Performance Requirements Matrix | Scope & Design Cost Control | Critical | Pre-construction | 3.0 › 3.50 Performance & Handover Requirements | PHR | PROJ-MCR-CM-PHR-0001_Testing | PCC
PC-D-001 | Detailed Cost Plan | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0001_DetailedCostPlan | QS
PC-D-003 | Work Breakdown Structure / Cost Breakdown Structure | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.70 Cost Coding | COD | PROJ-MCR-CM-COD-0001_WorkBreakdownStructure | PCC
PC-D-004 | Cost Code Structure | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.70 Cost Coding | COD | PROJ-MCR-CM-COD-0002_CostCodeStructure | PCC
PC-D-006 | Opening Cost/Value Reconciliation (CVR) | Cost Planning & Budget | Critical | Pre-start | 3.0 › 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0003_OpeningCost | QS
PC-D-007 | Preliminaries Budget | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0001_PreliminariesBudget | PCC
PC-D-010 | Logistics and Site Establishment Budget | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0004_LogisticsSiteEstablishmentBudget | PCC
PC-D-014 | Provisional Sums and Prime Cost Sums Schedule | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0003_ProvisionalSumsPrimeCostSums | QS
PC-D-015 | Contingency Allocation and Drawdown Register | Cost Planning & Budget | Critical | Pre-construction onward | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0004_ContingencyAllocationDrawdownRegister | QS
PC-D-016 | Risk-Pricing Reconciliation | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0005_RiskPricingReconciliation | QS
PC-D-019 | Cost Plan Assumptions and Exclusions Register | Cost Planning & Budget | Critical | Pre-construction | 3.0 › 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0004_CostPlanAssumptionsExclusionsRegister | QS
PC-E-001 | Procurement Strategy Report | Procurement Strategy | Critical | Pre-construction | 4.0 › 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0001_ProcurementStrategyReport | PCC
PC-E-002 | Procurement Schedule / Tender Event Schedule | Procurement Strategy | Critical | Pre-construction | 4.0 › 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0002_ProcurementSchedule | PCC
PC-E-003 | Subcontract Procurement Tracker | Procurement Strategy | Critical | Pre-construction | 4.0 › 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0003_SubcontractProcurementTracker | PCC
PC-E-004 | Long Lead Item Tracker | Procurement Strategy | Critical | Pre-construction | 4.0 › 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0004_LongLeadItemTracker | PCC
PC-E-010 | Due Diligence / PQQ Records | Procurement Strategy | Critical | Pre-construction | 4.0 › 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0004_DueDiligence | CA
PC-F-001 | Package Enquiry / ITT Document Checklist | Tendering & Package Award | Critical | Before enquiry | 4.0 › 4.40 Package Enquiry | PKE | PROJ-MCR-CM-PKE-0002_PackageEnquiry | QS
PC-F-005 | Tender Analysis Sheet / Tender Comparison Matrix | Tendering & Package Award | Critical | Tender analysis | 4.0 › 4.50 Package Tender Analysis | PTA | PROJ-MCR-CM-PTA-0002_TenderAnalysisSheet | QS
PC-F-007 | Pre-Let / Pre-Award Meeting Minutes | Tendering & Package Award | Critical | Before award | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0002_PreLet | QS
PC-F-008 | Commercial Recommendation Report | Tendering & Package Award | Critical | Before award | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0003_CommercialRecommendationReport | QS
PC-F-009 | Award Approval / DeleStaged Authority Record | Tendering & Package Award | Critical | Before award | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0004_AwardApproval | QS
PC-F-012 | Bid Validity and Price Hold Confirmation | Tendering & Package Award | Critical | Before award | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0007_BidValidityPriceHoldConfirmation | QS
PC-G-001 | Subcontract Order Schedule | Subcontract Formation | Critical | Pre-start | 5.0 › 5.10 Order Control | SCO | PROJ-MCR-CM-SCO-0001_SubcontractOrderSchedule | PCC
PC-G-002 | Approved Subcontract / Purchase Order Templates | Subcontract Formation | Critical | Pre-construction | 0.0 › 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0001_ApprovedSubcontract | CA
PC-G-003 | Subcontract Programme and Key Dates Schedule | Subcontract Formation | Critical | Before award | 5.0 › 5.20 Downstream Terms & Flow-Down | SDT | PROJ-MCR-CM-SDT-0005_SubcontractProgrammeKeyDatesSchedule | QS
PC-G-005 | Collateral Warranty / Third-Party Rights Flow-Down Schedule | Subcontract Formation | Critical | Before award | 5.0 › 5.30 Security & Insurance | SSI | PROJ-MCR-CM-SSI-0001_CollateralWarranty | CA
PC-G-008 | Letter of Intent Tracker | Subcontract Formation | Critical | Pre-start | 5.0 › 5.10 Order Control | SCO | PROJ-MCR-CM-SCO-0002_LetterIntentTracker | PCC
PC-G-009 | Executed Subcontract Register | Subcontract Formation | Critical | Pre-start | 5.0 › 5.10 Order Control | SCO | PROJ-MCR-CM-SCO-0003_ExecutedSubcontractRegister | PCC
PC-H-002 | Cashflow Forecast (Income and Expenditure) | Cashflow, Payment & Tax | Critical | Pre-construction | 6.0 › 6.20 Cashflow & Funding | CFF | PROJ-MCR-CM-CFF-0001_CashflowForecast | PCC
PC-I-001 | Commercial Risk Register | Risk, Opportunity & Governance | Critical | Pre-construction | 7.0 › 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0001_CommercialRiskRegister | PCC
PC-I-002 | Risk Mitigation Plan | Risk, Opportunity & Governance | Critical | Pre-construction | 7.0 › 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0002_RiskMitigationPlan | PCC
PC-J-001 | Change Control Procedure | Change, Claims & Entitlement | Critical | Pre-start | 0.0 › 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0003_ChangeControlProcedure | CA
PC-J-002 | Variation / Compensation Event Register | Change, Claims & Entitlement | Critical | Pre-start onward | 7.0 › 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0001_Variation | QS
PC-J-003 | Client / Architect / Contract Administrator Instruction Register | Change, Claims & Entitlement | Critical | Pre-start onward | 7.0 › 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0003_Client | QS
PC-J-004 | Early Warning Register | Change, Claims & Entitlement | Critical | Pre-start onward | 7.0 › 7.30 Entitlement & Claims Set-Up | ENT | PROJ-MCR-CM-ENT-0003_EarlyWarningRegister | CM
PC-J-005 | Extension of Time Procedure and Impact Register | Change, Claims & Entitlement | Critical | Pre-start | 7.0 › 7.30 Entitlement & Claims Set-Up | ENT | PROJ-MCR-CM-ENT-0005_ExtensionTimeProcedureImpactRegister | CM
PC-J-006 | Dayworks Procedure, Agreed Rates and Register | Change, Claims & Entitlement | Critical | Pre-start | 7.0 › 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0004_DayworksProcedure | QS
PC-J-008 | Final Account Strategy Register | Change, Claims & Entitlement | Critical | Pre-start | 7.0 › 7.30 Entitlement & Claims Set-Up | ENT | PROJ-MCR-CM-ENT-0006_FinalAccountStrategyRegister | CM
PC-K-001 | Accepted / Contract Baseline Programme | Programme & Delay Commercials | Critical | Pre-start | 8.0 › 8.10 Baseline Programme & Constraints | PGM | PROJ-MCR-CM-PGM-0001_Accepted | PCC
PC-K-002 | Programme Assumptions and Constraints Register | Programme & Delay Commercials | Critical | Pre-start | 8.0 › 8.10 Baseline Programme & Constraints | PGM | PROJ-MCR-CM-PGM-0002_ProgrammeAssumptionsConstraintsRegister | PCC
PC-K-003 | Sectional Completion and Key Dates Schedule | Programme & Delay Commercials | Critical | Pre-start | 8.0 › 8.10 Baseline Programme & Constraints | PGM | PROJ-MCR-CM-PGM-0003_SectionalCompletionKeyDatesSchedule | PCC
PC-L-001 | Main Contract Insurance Schedule and Evidence | Insurance, Security & Warranties | Critical | Pre-start | 9.0 › 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0001_MainContractInsuranceScheduleEvidence | CA
PC-L-002 | Insurance Responsibility Matrix | Insurance, Security & Warranties | Critical | Pre-start | 9.0 › 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0002_InsuranceResponsibilityMatrix | CA
PC-L-005 | Collateral Warranty Matrix | Insurance, Security & Warranties | Critical | Pre-start | 9.0 › 9.30 Warranties & Third-Party Rights | WTR | PROJ-MCR-CM-WTR-0001_CollateralWarrantyMatrix | CA
PC-L-008 | Professional Indemnity Insurance Schedule | Insurance, Security & Warranties | Critical | Pre-start | 9.0 › 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0004_ProfessionalIndemnityInsuranceSchedule | CA
PC-M-001 | Planning Permission and Condition Cost Register | Property, Statutory & Third Parties | Critical | Pre-construction | 10.0 › 10.10 Planning & Statutory Obligations | STA | PROJ-MCR-CM-STA-0001_PlanningPermissionConditionCostRegister | PCC
PC-M-003 | Building Regulations / Building Control Fees and Requirements | Property, Statutory & Third Parties | Critical | Pre-construction | 10.0 › 10.10 Planning & Statutory Obligations | STA | PROJ-MCR-CM-STA-0003_BuildingRegulations | PCC
PC-M-009 | Utility Search, Diversion and Connection Register | Property, Statutory & Third Parties | Critical | Pre-construction | 10.0 › 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0003_UtilitySearch | PCC
PC-M-012 | Client Direct Suppliers / Nominated Parties Interface Schedule | Property, Statutory & Third Parties | Critical | Pre-construction | 10.0 › 10.40 Ground & Interface Risk | GIR | PROJ-MCR-CM-GIR-0002_ClientDirectSuppliers | CM
PC-N-002 | CVR Reporting Calendar and Template | Reporting & Project Controls | Critical | Pre-start | 0.0 › 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0006_CVRReportingCalendarTemplate | CA
PC-N-003 | Cost Value Reconciliation Template | Reporting & Project Controls | Critical | Pre-start | 0.0 › 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0007_CostValueReconciliationTemplate | CA
PC-N-004 | Cost Forecast / Forecast Final Cost Report | Reporting & Project Controls | Critical | Pre-start | 11.0 › 11.20 Cost & Procurement Reporting | RPC | PROJ-MCR-CM-RPC-0001_CostForecast | PCC
PC-N-011 | Audit Trail / Document Control Protocol | Reporting & Project Controls | Critical | Pre-start | 0.0 › 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0007_AuditTrail | CA
PC-O-001 | Estimating-to-Delivery Handover Record | Mobilisation & Delivery Handover | Critical | Pre-start | 12.0 › 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0001_EstimatingDeliveryHandoverRecord | CM
PC-O-002 | Pre-Construction Commercial Readiness Review | Mobilisation & Delivery Handover | Critical | Before site start | 12.0 › 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0001_PreConstructionCommercialReadinessReview | CM
PC-O-003 | Commercial Mobilisation Checklist | Mobilisation & Delivery Handover | Critical | Before site start | 12.0 › 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0002_CommercialMobilisationChecklist | CM
PC-O-004 | Package Readiness / Release-to-Procure Checklist | Mobilisation & Delivery Handover | Critical | Pre-construction | 12.0 › 12.30 Package Readiness | PKR | PROJ-MCR-CM-PKR-0001_PackageReadiness | QS
PC-O-005 | Package Release-to-Start Checklist | Mobilisation & Delivery Handover | Critical | Pre-start | 12.0 › 12.30 Package Readiness | PKR | PROJ-MCR-CM-PKR-0002_PackageReleaseStartChecklist | QS
PC-O-006 | Outstanding Commercial Decisions Register | Mobilisation & Delivery Handover | Critical | Before site start | 12.0 › 12.40 Outstanding Commercial Exposure | EXP | PROJ-MCR-CM-EXP-0001_OutstandingCommercialDecisionsRegister | PCC
PC-O-007 | Open Qualifications / Assumptions Close-Out Schedule | Mobilisation & Delivery Handover | Critical | Before site start | 12.0 › 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0002_OpenQualifications | CM
PC-O-008 | Unplaced Orders and Exposure Report | Mobilisation & Delivery Handover | Critical | Before site start | 12.0 › 12.40 Outstanding Commercial Exposure | EXP | PROJ-MCR-CM-EXP-0002_UnplacedOrdersExposureReport | PCC
PC-O-010 | Opening Forecast and Cashflow Approval | Mobilisation & Delivery Handover | Critical | Before site start | 12.0 › 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0003_OpeningForecastCashflowApproval | CM
PC-O-014 | Commercial Pack Approval and Issue Record | Mobilisation & Delivery Handover | Critical | Pre-start Stage | 12.0 › 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0005_CommercialPackApprovalIssueRecord | CM
PC-C-006 | Specification Compliance and Betterment Register | Scope & Design Cost Control | High | Design development | 3.0 › 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0003_SpecificationComplianceBettermentRegister | QS
PC-C-007 | Room Data / Schedule of Accommodation Cost Check | Scope & Design Cost Control | High | Design development | 3.0 › 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0004_RoomData | QS
PC-C-010 | Design Consultant Fee Schedule and Tracker | Scope & Design Cost Control | High | Pre-construction onward | 3.0 › 3.40 Consultant Appointments | CNS | PROJ-MCR-CM-CNS-0002_DesignConsultantFeeScheduleTracker | CA
PC-C-011 | BIM / Information Management Requirements Cost Review | Scope & Design Cost Control | High | Pre-construction | 3.0 › 3.20 Design Management | DSN | PROJ-MCR-CM-DSN-0005_BIM | PCC
PC-C-013 | O&M, Handover and Asset Information Requirements Matrix | Scope & Design Cost Control | High | Pre-construction | 3.0 › 3.50 Performance & Handover Requirements | PHR | PROJ-MCR-CM-PHR-0002_OM | PCC
PC-D-002 | Elemental Cost Breakdown | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0002_ElementalCostBreakdown | QS
PC-D-005 | Cost Allocation Schedule | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.70 Cost Coding | COD | PROJ-MCR-CM-COD-0003_CostAllocationSchedule | PCC
PC-D-008 | Design Fees Budget | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0002_DesignFeesBudget | PCC
PC-D-009 | Temporary Works Budget | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0003_TemporaryWorksBudget | PCC
PC-D-011 | Utilities and Statutory Charges Budget | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0005_UtilitiesStatutoryChargesBudget | PCC
PC-D-013 | Currency and Commodity Exposure Schedule | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0002_CurrencyCommodityExposureSchedule | QS
PC-D-017 | Value Engineering Register | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0006_ValueEngineeringRegister | QS
PC-D-018 | Benchmarking and Market Testing Report | Cost Planning & Budget | High | Pre-construction | 3.0 › 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0007_BenchmarkingMarketTestingReport | QS
PC-E-005 | Procurement Responsibility Matrix | Procurement Strategy | High | Pre-construction | 4.0 › 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0005_ProcurementResponsibilityMatrix | PCC
PC-E-006 | Package Award Schedule | Procurement Strategy | High | Pre-construction | 4.0 › 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0006_PackageAwardSchedule | PCC
PC-E-007 | Supply Chain Market Engagement Plan | Procurement Strategy | High | Pre-construction | 4.0 › 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0001_SupplyChainMarketEngagementPlan | CA
PC-E-009 | Approved Supply Chain Register | Procurement Strategy | High | Pre-construction | 4.0 › 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0003_ApprovedSupplyChainRegister | CA
PC-E-011 | Supply Chain Risk Assessment | Procurement Strategy | High | Pre-construction | 4.0 › 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0006_SupplyChainRiskAssessment | CA
PC-E-012 | Single-Source / Negotiated Procurement Justification | Procurement Strategy | High | Before enquiry / award | 4.0 › 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0007_SingleSource | CA
PC-E-013 | Modern Slavery, Sanctions and Ethical Procurement Checks | Procurement Strategy | High | Before award | 4.0 › 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0008_ModernSlavery | CA
PC-E-014 | Social Value / Local Labour Procurement Plan | Procurement Strategy | High | Pre-construction | 4.0 › 4.30 Responsible Procurement | RSP | PROJ-MCR-CM-RSP-0001_SocialValue | PCC
PC-E-015 | Sustainable Procurement and Responsible Sourcing Schedule | Procurement Strategy | High | Pre-construction | 4.0 › 4.30 Responsible Procurement | RSP | PROJ-MCR-CM-RSP-0002_SustainableProcurementResponsibleSourcingSchedule | PCC
PC-F-002 | Tender Return Schedule and Pricing Template | Tendering & Package Award | High | Before enquiry | 4.0 › 4.40 Package Enquiry | PKE | PROJ-MCR-CM-PKE-0004_TenderReturnSchedulePricingTemplate | QS
PC-F-003 | Tender Query and Clarification Log - per package | Tendering & Package Award | High | Tender period | 4.0 › 4.40 Package Enquiry | PKE | PROJ-MCR-CM-PKE-0005_TenderQueryClarificationLog | QS
PC-F-004 | Tender Return Register | Tendering & Package Award | High | Tender return | 4.0 › 4.50 Package Tender Analysis | PTA | PROJ-MCR-CM-PTA-0001_TenderReturnRegister | QS
PC-F-006 | Tender Interview / Mid-Bid Meeting Record | Tendering & Package Award | High | Tender analysis | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0001_TenderInterview | QS
PC-F-010 | Buying Gains / Losses Tracker | Tendering & Package Award | High | At award | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0005_BuyingGains | QS
PC-F-011 | Post-Tender Negotiation Record | Tendering & Package Award | High | Before award | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0006_PostTenderNegotiationRecord | QS
PC-G-004 | Subcontract Damages / Delay Recovery Schedule | Subcontract Formation | High | Before award | 5.0 › 5.20 Downstream Terms & Flow-Down | SDT | PROJ-MCR-CM-SDT-0006_SubcontractDamages | QS
PC-G-006 | Subcontract Insurance Requirements Schedule | Subcontract Formation | High | Before award | 5.0 › 5.30 Security & Insurance | SSI | PROJ-MCR-CM-SSI-0002_SubcontractInsuranceRequirementsSchedule | CA
PC-G-007 | Subcontract Bond / Parent Company Guarantee Requirements | Subcontract Formation | High | Before award | 5.0 › 5.30 Security & Insurance | SSI | PROJ-MCR-CM-SSI-0003_SubcontractBond | CA
PC-G-010 | Off-Site Materials and Vesting Procedure | Subcontract Formation | High | Before off-site payment | 5.0 › 5.40 Materials & Mobilisation | SMM | PROJ-MCR-CM-SMM-0001_OffSiteMaterialsVestingProcedure | QS
PC-H-004 | Retention Register | Cashflow, Payment & Tax | High | Pre-start onward | 6.0 › 6.20 Cashflow & Funding | CFF | PROJ-MCR-CM-CFF-0003_RetentionRegister | PCC
PC-H-005 | Project Bank Account / Escrow Requirements | Cashflow, Payment & Tax | High | Pre-start | 6.0 › 6.30 Tax & Payment Security | TPS | PROJ-MCR-CM-TPS-0003_ProjectBankAccount | PCC
PC-H-006 | Cost Accrual and Invoice Cut-Off Procedure | Cashflow, Payment & Tax | High | Pre-start | 0.0 › 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0001_CostAccrualInvoiceCutOff | CA
PC-H-007 | Materials on Site Evidence Requirements | Cashflow, Payment & Tax | High | Pre-start | 0.0 › 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0002_MaterialsOnSiteEvidenceRequirements | CA
PC-I-003 | Risk Ownership Matrix | Risk, Opportunity & Governance | High | Pre-construction | 7.0 › 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0003_RiskOwnershipMatrix | PCC
PC-I-004 | Opportunity Register | Risk, Opportunity & Governance | High | Pre-construction | 7.0 › 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0004_OpportunityRegister | PCC
PC-I-005 | Commercial Risk Workshop Minutes | Risk, Opportunity & Governance | High | Pre-construction | 0.0 › 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0001_CommercialRiskWorkshopMinutes | CA
PC-I-006 | Commercial Responsibility Matrix (RACI) | Risk, Opportunity & Governance | High | Pre-construction | 0.0 › 0.30 DeleStaged Authority & Governance | GOV | PROJ-MCR-CM-GOV-0003_CommercialResponsibilityMatrix | CM
PC-I-007 | Conflict of Interest Declarations | Risk, Opportunity & Governance | High | Pre-construction | 0.0 › 0.30 DeleStaged Authority & Governance | GOV | PROJ-MCR-CM-GOV-0004_ConflictInterestDeclarations | CM
PC-I-008 | Fraud, Bribery and Gifts/Hospitality Compliance Record | Risk, Opportunity & Governance | High | Pre-construction | 0.0 › 0.30 DeleStaged Authority & Governance | GOV | PROJ-MCR-CM-GOV-0005_Fraud | CM
PC-J-007 | Contra-Charge Procedure and Register | Change, Claims & Entitlement | High | Pre-start onward | 7.0 › 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0005_ContraChargeProcedureRegister | QS
PC-J-009 | Claims Legal Privilege and Review Protocol | Change, Claims & Entitlement | High | Pre-start | 0.0 › 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0006_ClaimsLegalPrivilegeReviewProtocol | CA
PC-K-004 | Delay Notice and EOT Submission Templates | Programme & Delay Commercials | High | Pre-start | 0.0 › 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0004_DelayNoticeEOTSubmissionTemplates | CA
PC-K-005 | Float Ownership and Concurrent Delay Position Note | Programme & Delay Commercials | High | Pre-start | 8.0 › 8.20 Delay & LADs Commercials | DLY | PROJ-MCR-CM-DLY-0002_FloatOwnershipConcurrentDelayPosition | PCC
PC-K-006 | Programme Risk Allowance / Schedule Risk Analysis | Programme & Delay Commercials | High | Pre-construction | 8.0 › 8.20 Delay & LADs Commercials | DLY | PROJ-MCR-CM-DLY-0003_ProgrammeRiskAllowance | PCC
PC-L-003 | Performance Bond Tracker | Insurance, Security & Warranties | High | Pre-start | 9.0 › 9.20 Bonds & Guarantees | BND | PROJ-MCR-CM-BND-0001_PerformanceBondTracker | CA
PC-L-004 | Parent Company Guarantee Tracker | Insurance, Security & Warranties | High | Pre-start | 9.0 › 9.20 Bonds & Guarantees | BND | PROJ-MCR-CM-BND-0002_ParentCompanyGuaranteeTracker | CA
PC-L-006 | Third-Party Rights Schedule | Insurance, Security & Warranties | High | Pre-start | 9.0 › 9.30 Warranties & Third-Party Rights | WTR | PROJ-MCR-CM-WTR-0002_ThirdPartyRightsSchedule | CA
PC-L-007 | Warranty Register | Insurance, Security & Warranties | High | Pre-construction | 9.0 › 9.30 Warranties & Third-Party Rights | WTR | PROJ-MCR-CM-WTR-0003_WarrantyRegister | CA
PC-L-009 | Latent Defects / Structural Warranty Requirements | Insurance, Security & Warranties | High | Pre-start | 9.0 › 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0005_LatentDefects | CA
PC-M-004 | Party Wall Awards / Neighbour Agreements Register | Property, Statutory & Third Parties | High | Pre-construction | 10.0 › 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0001_PartyWallAwards | PCC
PC-M-005 | Rights of Light / Oversailing / Crane Licence Register | Property, Statutory & Third Parties | High | Pre-construction | 10.0 › 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0002_RightsLight | PCC
PC-M-006 | Landlord / Tenant / Lease Interface Schedule | Property, Statutory & Third Parties | High | Pre-construction | 10.0 › 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0003_Landlord | PCC
PC-M-007 | Highways / Section 278 / Section 38 Obligations Schedule | Property, Statutory & Third Parties | High | Pre-construction | 10.0 › 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0001_Highways | PCC
PC-M-008 | Drainage / Section 104 and Water Authority Schedule | Property, Statutory & Third Parties | High | Pre-construction | 10.0 › 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0002_Drainage | PCC
PC-M-010 | Environmental Permits / Licences Cost Schedule | Property, Statutory & Third Parties | High | Pre-construction | 10.0 › 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0004_EnvironmentalPermits | PCC
PC-M-011 | Access, Easement and Wayleave Register | Property, Statutory & Third Parties | High | Pre-construction | 10.0 › 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0004_Access | PCC
PC-N-001 | Monthly Commercial Report Template | Reporting & Project Controls | High | Pre-start | 0.0 › 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0005_MonthlyCommercialReportTemplate | CA
PC-N-005 | Client Commercial Reporting Format | Reporting & Project Controls | High | Pre-start | 11.0 › 11.10 Reporting Framework | RPT | PROJ-MCR-CM-RPT-0002_ClientCommercialReportingFormat | PCC
PC-N-006 | Procurement Status Report | Reporting & Project Controls | High | Pre-construction | 11.0 › 11.20 Cost & Procurement Reporting | RPC | PROJ-MCR-CM-RPC-0002_ProcurementStatusReport | PCC
PC-N-009 | Decision and Approval Register | Reporting & Project Controls | High | Pre-construction | 0.0 › 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0003_DecisionApprovalRegister | CA
PC-N-010 | Commercial Action Tracker | Reporting & Project Controls | High | Pre-construction | 0.0 › 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0004_CommercialActionTracker | CA
PC-N-012 | Commercial File Structure and Naming Convention | Reporting & Project Controls | High | Pre-start | 0.0 › 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0008_CommercialFileStructureNamingConvention | CA
PC-N-013 | Data Access, Confidentiality and Retention Rules | Reporting & Project Controls | High | Pre-start | 0.0 › 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0009_DataAccess | CA
PC-O-009 | Advance Orders / Deposits / Free-Issue Materials Schedule | Mobilisation & Delivery Handover | High | Pre-start | 12.0 › 12.40 Outstanding Commercial Exposure | EXP | PROJ-MCR-CM-EXP-0003_AdvanceOrders | PCC
PC-O-011 | Pre-Start Commercial Briefing Record | Mobilisation & Delivery Handover | High | Before site start | 12.0 › 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0004_PreStartCommercialBriefingRecord | CM
PC-O-012 | Final Account Strategy Note | Mobilisation & Delivery Handover | High | Before site start | 12.0 › 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0003_FinalAccountStrategyNote | CM
PC-O-013 | Handover Deliverables and Warranty Procurement Matrix | Mobilisation & Delivery Handover | High | Before site start | 12.0 › 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0004_HandoverDeliverablesWarrantyProcurementMatrix | CM
PC-C-008 | Samples, Mock-ups and Benchmark Cost Register | Scope & Design Cost Control | Medium | Pre-construction | 3.0 › 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0005_Samples | QS
PC-E-008 | Tender List Approval Register | Procurement Strategy | Medium | Pre-construction | 4.0 › 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0002_TenderListApprovalRegister | CA
PC-I-009 | Commercial Lessons Learned / Benchmark Brief | Risk, Opportunity & Governance | Medium | Pre-construction | 7.0 › 7.40 Lessons Learned | LSN | PROJ-MCR-CM-LSN-0001_CommercialLessonsLearned | PCC
PC-N-007 | Commercial KPI Schedule | Reporting & Project Controls | Medium | Pre-start | 11.0 › 11.10 Reporting Framework | RPT | PROJ-MCR-CM-RPT-0003_CommercialKPISchedule | PCC
PC-N-008 | Commercial Meeting Calendar and Terms of Reference | Reporting & Project Controls | Medium | Pre-start | 0.0 › 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0002_CommercialMeetingCalendarTermsReference | CA
PC-F-013 | Unsuccessful Tenderer Close-Out Record | Tendering & Package Award | Low | After award | 4.0 › 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0008_UnsuccessfulTendererCloseOutRecord | QS

## Pre-Con Folder Structure
Pre-Construction Commercial — Folder Structure
Purpose-built for the pre-construction phase. Naming: PROJ-MCR-CM-[TYPE]-[####]_[Title]. Your construction-phase tree is unchanged.
L1 Code | Level 1 Folder | L2 Code | Level 2 Folder | TYPE | Owner | Items
0.0 | Admin & Document Control
|  | 0.10 | Commercial Procedures & Protocols | PROC | CA | 7
|  | 0.20 | Standard Templates | TMP | CA | 5
|  | 0.30 | DeleStaged Authority & Governance | GOV | CM | 3
|  | 0.40 | Meetings, Contacts & Decisions | MTG | CA | 4
1.0 | Tender & Bid Baseline
|  | 1.10 | Tender Source Information (Frozen) | TSI | QS | 5
|  | 1.20 | Priced Bid & Assumptions | BID | QS | 1
|  | 1.30 | Bid Governance & Submission | BGV | QS | 5
2.0 | Contract Formation
|  | 2.10 | Executed Contract & Particulars | CON | CM | 4
|  | 2.20 | Tender-to-Contract Reconciliation | T2C | CM | 2
|  | 2.30 | Contract Risk & Liabilities | CRL | CM | 4
|  | 2.40 | ER / CP & Compliance | ERCP | PCC | 2
|  | 2.50 | Contract Correspondence | CCR | CA | 0
|  | 2.60 | Contract Pricing Basis | CPB | QS | 2
3.0 | Scope, Design & Cost Planning
|  | 3.10 | Scope Definition & Interfaces | SCP | PCC | 3
|  | 3.20 | Design Management | DSN | PCC | 1
|  | 3.30 | Design Cost Control | DCC | QS | 5
|  | 3.40 | Consultant Appointments | CNS | CA | 2
|  | 3.50 | Performance & Handover Requirements | PHR | PCC | 2
|  | 3.60 | Cost Baseline | CBL | QS | 4
|  | 3.70 | Cost Coding | COD | PCC | 3
|  | 3.80 | Budget Build-Up | BUD | PCC | 5
|  | 3.90 | Provisional Sums, Contingency & Value | PSV | QS | 8
4.0 | Procurement & Package Award
|  | 4.10 | Procurement Strategy & Schedule | PRS | PCC | 6
|  | 4.20 | Supply Chain Management | SCM | CA | 7
|  | 4.30 | Responsible Procurement | RSP | PCC | 2
|  | 4.40 | Package Enquiry | PKE | QS | 3
|  | 4.50 | Package Tender Analysis | PTA | QS | 2
|  | 4.60 | Package Award & Recommendation | PAW | QS | 8
5.0 | Subcontract Formation
|  | 5.10 | Order Control | SCO | PCC | 3
|  | 5.20 | Downstream Terms & Flow-Down | SDT | QS | 2
|  | 5.30 | Security & Insurance | SSI | CA | 3
|  | 5.40 | Materials & Mobilisation | SMM | QS | 1
6.0 | Cashflow, Payment & Tax
|  | 6.10 | Payment Framework | PYF | QS | 1
|  | 6.20 | Cashflow & Funding | CFF | PCC | 3
|  | 6.30 | Tax & Payment Security | TPS | PCC | 1
7.0 | Risk, Governance & Entitlement
|  | 7.10 | Risk & Opportunity Registers | RSK | PCC | 4
|  | 7.20 | Change & Variation Control | CVC | QS | 4
|  | 7.30 | Entitlement & Claims Set-Up | ENT | CM | 3
|  | 7.40 | Lessons Learned | LSN | PCC | 1
8.0 | Programme & Delay Commercials
|  | 8.10 | Baseline Programme & Constraints | PGM | PCC | 3
|  | 8.20 | Delay & LADs Commercials | DLY | PCC | 2
9.0 | Insurance, Security & Warranties
|  | 9.10 | Project Insurances | INS | CA | 4
|  | 9.20 | Bonds & Guarantees | BND | CA | 2
|  | 9.30 | Warranties & Third-Party Rights | WTR | CA | 3
10.0 | Property, Statutory & Third Parties
|  | 10.10 | Planning & Statutory Obligations | STA | PCC | 3
|  | 10.20 | Utilities & Infrastructure | UTL | PCC | 4
|  | 10.30 | Third-Party & Neighbour Rights | TPR | PCC | 4
|  | 10.40 | Ground & Interface Risk | GIR | CM | 1
11.0 | Commercial Reporting & Controls
|  | 11.10 | Reporting Framework | RPT | PCC | 2
|  | 11.20 | Cost & Procurement Reporting | RPC | PCC | 2
12.0 | Mobilisation & Pre-Start Handover
|  | 12.10 | Commercial Readiness | RDY | CM | 5
|  | 12.20 | Estimating-to-Delivery Handover | HND | CM | 4
|  | 12.30 | Package Readiness | PKR | QS | 2
|  | 12.40 | Outstanding Commercial Exposure | EXP | PCC | 3

## Master Register
Pre-Construction Commercial Pack - Extensive Master Register
Ref | Workstream | Subcategory | Document / Control | Purpose / Commercial Risk | Include in Pack? | Status | Priority | Governance Tier | Primary Owner | Contributors | Audience | Stage / Stage | Frequency | Due Date | Current Version | Storage Link / File Ref | Source / Basis | Notes / Action | Level 1 Folder | Level 2 Folder | TYPE | Proposed File Name | Meridian Owner | Stage
PC-A-001 | Tender & Bid Baseline | Tender source information | Client ITT / Tender Documents (as issued) | Defines the information and scope actually priced; preserve the complete issue as the tender baseline. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Estimator | Commercial Manager | Internal / Client | Tender receipt | Once |  |  |  | Source Word register |  | 1.0 Tender & Bid Baseline | 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0001_ClientITT | QS | Stage 1 - Bid
PC-A-002 | Tender & Bid Baseline | Tender source information | Tender Addenda / Bulletin Register | Captures every bulletin, revised document and pricing instruction issued during tender. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Estimator | Design Manager; QS | Internal | Tender period | Live during tender |  |  |  | Source Word register |  | 1.0 Tender & Bid Baseline | 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0004_TenderAddenda | QS | Stage 1 - Bid
PC-A-003 | Tender & Bid Baseline | Tender source information | Tender Clarifications and RFI Log | Records queries, responses, assumptions and unanswered matters affecting scope or price. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Estimator | Design Manager; QS | Internal / Client | Tender period | Live during tender |  |  |  | Source Word register |  | 1.0 Tender & Bid Baseline | 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0005_TenderClarificationsRFILog | QS | Stage 1 - Bid
PC-A-004 | Tender & Bid Baseline | Tender source information | Site Visit / Existing Conditions Record | Records visible conditions, access, logistics and constraints relied upon in pricing. | TBC | Not Started | High | Tier 3 - Internal Control | Estimator | Project Manager; Design Manager | Internal | Tender period | Once / each visit |  |  |  | Expanded recommendation |  | 1.0 Tender & Bid Baseline | 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0006_SiteVisit | QS | Stage 1 - Bid
PC-A-005 | Tender & Bid Baseline | Tender source information | Tender Return Requirements Checklist | Controls all mandatory return documents, forms, declarations and submission deadlines. | TBC | Not Started | High | Tier 3 - Internal Control | Estimator | Commercial Manager | Internal | Tender period | Live during tender |  |  |  | Expanded recommendation |  | 1.0 Tender & Bid Baseline | 1.10 Tender Source Information (Frozen) | TSI | PROJ-MCR-CM-TSI-0007_TenderReturnRequirementsChecklist | QS | Stage 1 - Bid
PC-A-006 | Tender & Bid Baseline | Tender source information | Priced Tender Submission (full build-up) | Preserves the submitted price, quantities, rates, resource assumptions and allowances. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Estimator | QS; Commercial Manager | Internal | Tender submission | Once |  |  |  | Source Word register |  | 1.0 Tender & Bid Baseline | 1.20 Priced Bid & Assumptions | BID | PROJ-MCR-CM-BID-0001_PricedTenderSubmission | QS | Stage 1 - Bid
PC-A-007 | Tender & Bid Baseline | Tender source information | Tender Qualifications, Exclusions and Assumptions Schedule | Primary record of items included, excluded or qualified; must be carried into the contract. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Estimator; Legal | Internal / Client | Tender submission | Update through negotiation |  |  |  | Both source lists |  | 1.0 Tender & Bid Baseline | 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0001_TenderQualifications | QS | Stage 1 - Bid
PC-A-008 | Tender & Bid Baseline | Tender source information | Tender Baseline Programme | Records the duration, sequencing, access and procurement assumptions underpinning the price. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Planner | Commercial Manager; Project Manager | Internal / Client | Tender submission | Once / agreed revision |  |  |  | Source Word register |  | 1.0 Tender & Bid Baseline | 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0002_TenderBaselineProgramme | QS | Stage 1 - Bid
PC-A-009 | Tender & Bid Baseline | Tender source information | Tender Adjudication / Settlement Summary | Formal internal approval of price, margin, risk, qualifications and authority to submit. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Director | Commercial Manager; Estimator | Board / Internal | Tender submission | Once |  |  |  | Source Word register |  | 1.0 Tender & Bid Baseline | 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0003_TenderAdjudication | QS | Stage 1 - Bid
PC-A-010 | Tender & Bid Baseline | Tender source information | Tender Risk and Opportunity Schedule | Quantifies bid risks, opportunities, owners, mitigations and allowances included in the tender. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Estimator; Project Manager | Board / Internal | Tender submission | Update through negotiation |  |  |  | Expanded recommendation |  | 1.0 Tender & Bid Baseline | 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0004_TenderRiskOpportunitySchedule | QS | Stage 1 - Bid
PC-A-011 | Tender & Bid Baseline | Tender source information | Bid Bonds / Tender Security Record | Confirms any tender bond, validity period, wording and release requirements. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Finance; Legal | Internal | Tender submission | Once |  |  |  | Expanded recommendation |  | 1.0 Tender & Bid Baseline | 1.30 Bid Governance & Submission | BGV | PROJ-MCR-CM-BGV-0005_BidBonds | QS | Stage 1 - Bid
PC-B-001 | Contract Formation | Main contract and appointments | Contract-vs-Tender Reconciliation | Identifies every movement between tender and signed deal, including qualifications that were lost or amended. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Estimator; Legal | Board / Internal | Pre-contract | Once before execution |  |  |  | Source Word register |  | 2.0 Contract Formation | 2.20 Tender-to-Contract Reconciliation | T2C | PROJ-MCR-CM-T2C-0001_ContractVsTenderReconciliation | CM | Stage 2 - Award
PC-B-002 | Contract Formation | Main contract and appointments | Executed Building Contract | Complete signed contract including articles, conditions, schedules, amendments and appendices. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Director | Commercial Manager; Legal | Client / Board | Contract execution | Once |  |  |  | Both source lists |  | 2.0 Contract Formation | 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0001_ExecutedBuildingContract | CM | Stage 2 - Award
PC-B-003 | Contract Formation | Main contract and appointments | Contract Particulars Register | Summarises dates, retention, LADs, defects period, payment terms, insurance, bonds and caps. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | Legal | Internal | Contract execution | Once / revise if amended |  |  |  | Source workbook |  | 2.0 Contract Formation | 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0002_ContractParticularsRegister | CM | Stage 2 - Award
PC-B-004 | Contract Formation | Main contract and appointments | Contractor’s Proposals Register | Indexes all CP documents and records the contractor’s offered solution. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Design Manager | Commercial Manager | Internal / Client | Pre-contract | Once / each agreed revision |  |  |  | Source Word register |  | 2.0 Contract Formation | 2.40 ER / CP & Compliance | ERCP | PROJ-MCR-CM-ERCP-0002_ContractorSProposalsRegister | PCC | Stage 2 - Award
PC-B-005 | Contract Formation | Main contract and appointments | ER/CP Compliance and Divergence Matrix | Identifies omissions, conflicts and departures between ER, CP, tender and contract documents. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Design Manager | Commercial Manager; Legal | Internal / Client | Pre-contract | Live until closed |  |  |  | Expanded recommendation |  | 2.0 Contract Formation | 2.40 ER / CP & Compliance | ERCP | PROJ-MCR-CM-ERCP-0003_ER | PCC | Stage 2 - Award
PC-B-006 | Contract Formation | Main contract and appointments | Contract Sum Analysis / Contract Sum Breakdown | Agreed value breakdown used for payment, change valuation and budget control. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | QS | Estimator; Commercial Manager | Client / Internal | Contract execution | Once / agreed revisions |  |  |  | Both source lists |  | 2.0 Contract Formation | 2.60 Contract Pricing Basis | CPB | PROJ-MCR-CM-CPB-0001_ContractSumAnalysis | QS | Stage 2 - Award
PC-B-007 | Contract Formation | Main contract and appointments | Pricing Document / Bill of Quantities / Schedule of Rates | Preserves the contractual pricing basis, quantities, rates and valuation rules. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Estimator | Internal / Client | Contract execution | Once |  |  |  | Expanded recommendation |  | 2.0 Contract Formation | 2.60 Contract Pricing Basis | CPB | PROJ-MCR-CM-CPB-0002_PricingDocument | QS | Stage 2 - Award
PC-B-008 | Contract Formation | Main contract and appointments | Contract Data / Scope / Works Information (NEC where applicable) | Captures the operative NEC documents and defined obligations where NEC is used. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Legal; Project Manager | Internal / Client | Contract execution | Once / agreed revisions |  |  |  | Expanded recommendation |  | 2.0 Contract Formation | 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0004_ContractData | CM | Stage 2 - Award
PC-B-009 | Contract Formation | Main contract and appointments | Letter of Intent Register and Authority | Controls scope, value cap, expiry, insurance and termination rights before full contract. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Legal; Finance | Board / Internal | Pre-contract | Live until superseded |  |  |  | Source workbook |  | 2.0 Contract Formation | 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0001_LetterIntentRegisterAuthority | CM | Stage 2 - Award
PC-B-010 | Contract Formation | Main contract and appointments | Pre-Contract Services Agreement and Fee Tracker | Defines PCSA deliverables, fees, IP, design responsibility and transition into the main contract. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Design Manager; Finance | Client / Internal | PCSA | Monthly |  |  |  | Expanded recommendation |  | 2.0 Contract Formation | 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0002_PreContractServicesAgreementFee | CM | Stage 2 - Award
PC-B-011 | Contract Formation | Main contract and appointments | Contract Approval / DeleStaged Authority Sign-Off | Evidence that the final contract position is approved at the correct authority level. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Director | Commercial Manager; Finance | Board / Internal | Before execution | Once |  |  |  | Expanded recommendation |  | 2.0 Contract Formation | 2.20 Tender-to-Contract Reconciliation | T2C | PROJ-MCR-CM-T2C-0004_ContractApproval | CM | Stage 2 - Award
PC-B-012 | Contract Formation | Main contract and appointments | Key Contract Dates and Notices Schedule | Single schedule of due dates, notice periods, sectional completion, LADs, payment and expiry dates. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | Planner; QS | Internal | Contract execution | Live |  |  |  | Both source lists |  | 2.0 Contract Formation | 2.10 Executed Contract & Particulars | CON | PROJ-MCR-CM-CON-0005_KeyContractDatesNoticesSchedule | CM | Stage 2 - Award
PC-B-013 | Contract Formation | Main contract and appointments | Dispute Resolution and Governing Law Summary | Records adjudication, arbitration/litigation, jurisdiction and escalation provisions. | TBC | Not Started | High | Tier 3 - Internal Control | Legal | Commercial Manager | Internal | Contract execution | Once |  |  |  | Expanded recommendation |  | 2.0 Contract Formation | 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0003_DisputeResolutionGoverningLawSummary | CM | Stage 2 - Award
PC-B-014 | Contract Formation | Main contract and appointments | Assignment, Novation and Change of Control Requirements | Records consent, novation, assignment and corporate-change obligations. | TBC | Not Started | High | Tier 3 - Internal Control | Legal | Commercial Manager | Internal | Before execution | Once |  |  |  | Expanded recommendation |  | 2.0 Contract Formation | 2.30 Contract Risk & Liabilities | CRL | PROJ-MCR-CM-CRL-0005_Assignment | CM | Stage 2 - Award
PC-C-001 | Scope & Design Cost Control | Scope definition and design interface | Project Scope Responsibility Matrix | Allocates every scope element to employer, contractor, consultant, subcontractor or third party. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Design Manager; Project Manager | Internal / Client | Pre-construction | Live until design freeze |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.10 Scope Definition & Interfaces | SCP | PROJ-MCR-CM-SCP-0001_ProjectScopeResponsibilityMatrix | PCC | Stage 3 - Pre-Con
PC-C-002 | Scope & Design Cost Control | Scope definition and design interface | Subcontract Package Matrix | Allocates work across packages and exposes gaps, overlaps and double-counting. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Commercial Manager; Design Manager | Internal | Pre-construction | Live |  |  |  | Source Word register |  | 3.0 Scope, Design & Cost Planning | 3.10 Scope Definition & Interfaces | SCP | PROJ-MCR-CM-SCP-0002_SubcontractPackageMatrix | PCC | Stage 3 - Pre-Con
PC-C-003 | Scope & Design Cost Control | Scope definition and design interface | Package Interface Matrix | Defines boundaries between trades including builder’s work, supports, penetrations, firestopping and making good. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Design Manager | QS; Project Manager | Internal | Pre-construction | Live |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.10 Scope Definition & Interfaces | SCP | PROJ-MCR-CM-SCP-0003_PackageInterfaceMatrix | PCC | Stage 3 - Pre-Con
PC-C-004 | Scope & Design Cost Control | Scope definition and design interface | Design-to-Cost Tracker | Compares developing design against approved package budgets and flags overspend before tender. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | QS | Design Manager; Estimator | Board / Internal | Design development | Fortnightly / monthly |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0001_DesignCostTracker | QS | Stage 3 - Pre-Con
PC-C-005 | Scope & Design Cost Control | Scope definition and design interface | Cost Check at Design Stage | Formal cost report and approval at each RIBA/design stage before the next stage proceeds. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | QS; Design Manager | Client / Board | Each design Stage | At each Stage |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0002_CostCheckAtDesignStage | QS | Stage 3 - Pre-Con
PC-C-006 | Scope & Design Cost Control | Scope definition and design interface | Specification Compliance and Betterment Register | Separates contractual compliance from enhancements that require client approval and funding. | TBC | Not Started | High | Tier 2 - Commercial Review | Design Manager | QS | Internal / Client | Design development | Live |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0003_SpecificationComplianceBettermentRegister | QS | Stage 3 - Pre-Con
PC-C-007 | Scope & Design Cost Control | Scope definition and design interface | Room Data / Schedule of Accommodation Cost Check | Reconciles room requirements and quantities to the cost plan and scope. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Design Manager | Internal | Design development | At each design freeze |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0004_RoomData | QS | Stage 3 - Pre-Con
PC-C-008 | Scope & Design Cost Control | Scope definition and design interface | Samples, Mock-ups and Benchmark Cost Register | Records required samples/mock-ups, ownership, cost allowance and approval consequences. | TBC | Not Started | Medium | Tier 3 - Internal Control | QS | Design Manager; Project Manager | Internal | Pre-construction | Live |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.30 Design Cost Control | DCC | PROJ-MCR-CM-DCC-0005_Samples | QS | Stage 3 - Pre-Con
PC-C-009 | Scope & Design Cost Control | Scope definition and design interface | Consultant Appointment and Scope Review | Confirms consultant deliverables, exclusions, fee, programme, PI and collateral warranty obligations. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Design Manager; Legal | Internal | Pre-construction | Per appointment |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.40 Consultant Appointments | CNS | PROJ-MCR-CM-CNS-0001_ConsultantAppointmentScopeReview | CA | Stage 3 - Pre-Con
PC-C-010 | Scope & Design Cost Control | Scope definition and design interface | Design Consultant Fee Schedule and Tracker | Controls agreed fees, additional services, payment milestones and remaining forecast. | TBC | Not Started | High | Tier 3 - Internal Control | QS | Design Manager; Finance | Internal | Pre-construction onward | Monthly |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.40 Consultant Appointments | CNS | PROJ-MCR-CM-CNS-0002_DesignConsultantFeeScheduleTracker | CA | Stage 3 - Pre-Con
PC-C-011 | Scope & Design Cost Control | Scope definition and design interface | BIM / Information Management Requirements Cost Review | Identifies BIM, CDE, COBie, model and information-delivery obligations with cost/resource impacts. | TBC | Not Started | High | Tier 3 - Internal Control | Design Manager | Commercial Manager; BIM Manager | Internal | Pre-construction | Once / change |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.20 Design Management | DSN | PROJ-MCR-CM-DSN-0005_BIM | PCC | Stage 3 - Pre-Con
PC-C-012 | Scope & Design Cost Control | Scope definition and design interface | Testing, Commissioning and Performance Requirements Matrix | Captures performance, testing, witnessing, seasonal commissioning and evidence requirements within trade scopes. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Design Manager | MEP Manager; QS | Internal / Client | Pre-construction | Live |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.50 Performance & Handover Requirements | PHR | PROJ-MCR-CM-PHR-0001_Testing | PCC | Stage 3 - Pre-Con
PC-C-013 | Scope & Design Cost Control | Scope definition and design interface | O&M, Handover and Asset Information Requirements Matrix | Defines handover deliverables early and allocates them into procurement packages. | TBC | Not Started | High | Tier 2 - Commercial Review | Design Manager | Document Controller; QS | Internal / Client | Pre-construction | Live |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.50 Performance & Handover Requirements | PHR | PROJ-MCR-CM-PHR-0002_OM | PCC | Stage 3 - Pre-Con
PC-D-001 | Cost Planning & Budget | Cost baseline and coding | Detailed Cost Plan | Internal trade and element cost baseline including quantities, rates, allowances and exclusions. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Estimator; Commercial Manager | Internal | Pre-construction | At each design Stage |  |  |  | Source workbook |  | 3.0 Scope, Design & Cost Planning | 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0001_DetailedCostPlan | QS | Stage 3 - Pre-Con
PC-D-002 | Cost Planning & Budget | Cost baseline and coding | Elemental Cost Breakdown | Cost analysis by NRM element to track design development and benchmark value. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Estimator | Internal | Pre-construction | At each design Stage |  |  |  | Source workbook |  | 3.0 Scope, Design & Cost Planning | 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0002_ElementalCostBreakdown | QS | Stage 3 - Pre-Con
PC-D-003 | Cost Planning & Budget | Cost baseline and coding | Work Breakdown Structure / Cost Breakdown Structure | Common coding hierarchy linking scope, procurement, programme, commitments and reporting. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | Planner; Finance | Internal | Pre-construction | Once / controlled revisions |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.70 Cost Coding | COD | PROJ-MCR-CM-COD-0001_WorkBreakdownStructure | PCC | Stage 3 - Pre-Con
PC-D-004 | Cost Planning & Budget | Cost baseline and coding | Cost Code Structure | Coding framework used for orders, invoices, CVR, cashflow and final account. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | Finance; QS | Internal | Pre-construction | Once |  |  |  | Source workbook |  | 3.0 Scope, Design & Cost Planning | 3.70 Cost Coding | COD | PROJ-MCR-CM-COD-0002_CostCodeStructure | PCC | Stage 3 - Pre-Con
PC-D-005 | Cost Planning & Budget | Cost baseline and coding | Cost Allocation Schedule | Maps every budget allowance to a cost code, package and responsible QS. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Commercial Manager | Internal | Pre-construction | Live |  |  |  | Source workbook |  | 3.0 Scope, Design & Cost Planning | 3.70 Cost Coding | COD | PROJ-MCR-CM-COD-0003_CostAllocationSchedule | PCC | Stage 3 - Pre-Con
PC-D-006 | Cost Planning & Budget | Cost baseline and coding | Opening Cost/Value Reconciliation (CVR) | Establishes contract value, budget, margin, risk and forecast baseline handed to delivery. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | QS; Finance | Board / Internal | Pre-start | Once |  |  |  | Source Word register |  | 3.0 Scope, Design & Cost Planning | 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0003_OpeningCost | QS | Stage 3 - Pre-Con
PC-D-007 | Cost Planning & Budget | Cost baseline and coding | Preliminaries Budget | Separates fixed and time-related preliminaries, staffing, plant, logistics and temporary services. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Project Manager; Planner | Internal | Pre-construction | Monthly forecast |  |  |  | Source Word register |  | 3.0 Scope, Design & Cost Planning | 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0001_PreliminariesBudget | PCC | Stage 3 - Pre-Con
PC-D-008 | Cost Planning & Budget | Cost baseline and coding | Design Fees Budget | Budgets consultant, specialist design, surveys, approvals and design-management costs. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Design Manager | Internal | Pre-construction | Monthly forecast |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0002_DesignFeesBudget | PCC | Stage 3 - Pre-Con
PC-D-009 | Cost Planning & Budget | Cost baseline and coding | Temporary Works Budget | Budgets design, checking, materials, installation, inspection and removal of temporary works. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Temporary Works Coordinator | Internal | Pre-construction | Monthly forecast |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0003_TemporaryWorksBudget | PCC | Stage 3 - Pre-Con
PC-D-010 | Cost Planning & Budget | Cost baseline and coding | Logistics and Site Establishment Budget | Tests welfare, hoarding, cranes, hoists, scaffolding, security, utilities and access against programme duration. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Project Manager; Planner | Internal | Pre-construction | At logistics revisions |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0004_LogisticsSiteEstablishmentBudget | PCC | Stage 3 - Pre-Con
PC-D-011 | Cost Planning & Budget | Cost baseline and coding | Utilities and Statutory Charges Budget | Captures applications, upgrades, diversions, temporary supplies, meters and authority charges. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | MEP Manager | Internal | Pre-construction | Monthly forecast |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.80 Budget Build-Up | BUD | PROJ-MCR-CM-BUD-0005_UtilitiesStatutoryChargesBudget | PCC | Stage 3 - Pre-Con
PC-D-012 | Cost Planning & Budget | Cost baseline and coding | Inflation / Escalation Assessment | Quantifies tender-date to procurement-date exposure by labour, material and package. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Estimator | Commercial Manager | Board / Internal | Pre-contract | Monthly / key award Stages |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0001_Inflation | QS | Stage 2 - Award
PC-D-013 | Cost Planning & Budget | Cost baseline and coding | Currency and Commodity Exposure Schedule | Records foreign currency, steel, fuel or other indexed exposure and mitigation. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Finance; Procurement | Board / Internal | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0002_CurrencyCommodityExposureSchedule | QS | Stage 3 - Pre-Con
PC-D-014 | Cost Planning & Budget | Cost baseline and coding | Provisional Sums and Prime Cost Sums Schedule | Records definitions, allowances, scope, procurement route, expenditure and adjustment rules. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | QS | Design Manager | Client / Internal | Pre-construction | Monthly |  |  |  | Both source lists |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0003_ProvisionalSumsPrimeCostSums | QS | Stage 3 - Pre-Con
PC-D-015 | Cost Planning & Budget | Cost baseline and coding | Contingency Allocation and Drawdown Register | Separates client, design, construction and commercial contingency with approval rules. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | QS; Finance | Board / Internal | Pre-construction onward | Monthly |  |  |  | Source workbook |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0004_ContingencyAllocationDrawdownRegister | QS | Stage 3 - Pre-Con
PC-D-016 | Cost Planning & Budget | Cost baseline and coding | Risk-Pricing Reconciliation | Reconciles quantified risk exposure to explicit allowances and contingency in the cost plan. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | QS | Internal | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0005_RiskPricingReconciliation | QS | Stage 3 - Pre-Con
PC-D-017 | Cost Planning & Budget | Cost baseline and coding | Value Engineering Register | Records proposal, baseline, saving, design/programme effects, approvals and implementation. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | QS | Design Manager; Project Manager | Client / Board | Pre-construction | Live |  |  |  | Source workbook |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0006_ValueEngineeringRegister | QS | Stage 3 - Pre-Con
PC-D-018 | Cost Planning & Budget | Cost baseline and coding | Benchmarking and Market Testing Report | Tests key rates and allowances against historic projects, live tenders and market intelligence. | TBC | Not Started | High | Tier 2 - Commercial Review | Estimator | QS; Procurement | Internal / Client | Pre-construction | At cost plan revisions |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0007_BenchmarkingMarketTestingReport | QS | Stage 3 - Pre-Con
PC-D-019 | Cost Planning & Budget | Cost baseline and coding | Cost Plan Assumptions and Exclusions Register | Central record of measurement rules, scope assumptions, exclusions and unresolved cost items. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Design Manager | Internal / Client | Pre-construction | Live |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.60 Cost Baseline | CBL | PROJ-MCR-CM-CBL-0004_CostPlanAssumptionsExclusionsRegister | QS | Stage 3 - Pre-Con
PC-D-020 | Cost Planning & Budget | Cost baseline and coding | Reconciliation to Client Budget / Funding Limit | Shows contract cost, client direct costs, fees, risk and VAT against available funding. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Client QS; Finance | Client / Board | Pre-contract | At each approval Stage |  |  |  | Expanded recommendation |  | 3.0 Scope, Design & Cost Planning | 3.90 Provisional Sums, Contingency & Value | PSV | PROJ-MCR-CM-PSV-0008_ReconciliationClientBudget | QS | Stage 2 - Award
PC-E-001 | Procurement Strategy | Planning and market engagement | Procurement Strategy Report | Defines package structure, procurement route, competition, design responsibility and award governance. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Procurement; Project Manager | Board / Internal | Pre-construction | Once / major revision |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0001_ProcurementStrategyReport | PCC | Stage 3 - Pre-Con
PC-E-002 | Procurement Strategy | Planning and market engagement | Procurement Schedule / Tender Event Schedule | Links enquiry, tender, analysis, approval, order, design and delivery to need dates. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Planner; QS | Client / Internal | Pre-construction | Weekly |  |  |  | Both source lists |  | 4.0 Procurement & Package Award | 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0002_ProcurementSchedule | PCC | Stage 3 - Pre-Con
PC-E-003 | Procurement Strategy | Planning and market engagement | Subcontract Procurement Tracker | Live package position from scope development through executed order. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Procurement | Internal | Pre-construction | Weekly |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0003_SubcontractProcurementTracker | PCC | Stage 3 - Pre-Con
PC-E-004 | Procurement Strategy | Planning and market engagement | Long Lead Item Tracker | Controls technical approval, deposit, manufacture, inspection, delivery and programme float. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Procurement | Planner; Design Manager | Client / Internal | Pre-construction | Weekly |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0004_LongLeadItemTracker | PCC | Stage 3 - Pre-Con
PC-E-005 | Procurement Strategy | Planning and market engagement | Procurement Responsibility Matrix | Defines package owner, technical lead, approver and signatory. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Procurement; Design Manager | Internal | Pre-construction | Once / team change |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0005_ProcurementResponsibilityMatrix | PCC | Stage 3 - Pre-Con
PC-E-006 | Procurement Strategy | Planning and market engagement | Package Award Schedule | Records target and actual award dates, budget, award value and approval status. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Commercial Manager | Internal | Pre-construction | Weekly |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.10 Procurement Strategy & Schedule | PRS | PROJ-MCR-CM-PRS-0006_PackageAwardSchedule | PCC | Stage 3 - Pre-Con
PC-E-007 | Procurement Strategy | Planning and market engagement | Supply Chain Market Engagement Plan | Identifies bidder pool, engagement timing, market capacity, geographic reach and fallback options. | TBC | Not Started | High | Tier 3 - Internal Control | Procurement | QS | Internal | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0001_SupplyChainMarketEngagementPlan | CA | Stage 3 - Pre-Con
PC-E-008 | Procurement Strategy | Planning and market engagement | Tender List Approval Register | Evidence that bidders were approved before confidential information and enquiries were issued. | TBC | Not Started | Medium | Tier 3 - Internal Control | Procurement | Commercial Manager | Internal | Pre-construction | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0002_TenderListApprovalRegister | CA | Stage 3 - Pre-Con
PC-E-009 | Procurement Strategy | Planning and market engagement | Approved Supply Chain Register | List of authorised suppliers and subcontractors with approved trade categories. | TBC | Not Started | High | Tier 2 - Commercial Review | Procurement | H&S; Finance | Internal | Pre-construction | Monthly |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0003_ApprovedSupplyChainRegister | CA | Stage 3 - Pre-Con
PC-E-010 | Procurement Strategy | Planning and market engagement | Due Diligence / PQQ Records | Financial, technical, compliance, capacity, insurance and safety checks for bidders. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Procurement | Finance; H&S; QS | Internal | Pre-construction | Per bidder / annual refresh |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0004_DueDiligence | CA | Stage 3 - Pre-Con
PC-E-011 | Procurement Strategy | Planning and market engagement | Supply Chain Risk Assessment | Records delivery, capacity, financial, quality, design and programme risk by package. | TBC | Not Started | High | Tier 2 - Commercial Review | Commercial Manager | QS; Project Manager | Internal | Pre-construction | Monthly |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0006_SupplyChainRiskAssessment | CA | Stage 3 - Pre-Con
PC-E-012 | Procurement Strategy | Planning and market engagement | Single-Source / Negotiated Procurement Justification | Documents why competition is not available and demonstrates value for money and approval. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Expanded recommendation | Board / Client | Before enquiry / award | QS; Procurement |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0007_SingleSource | CA | Stage 3 - Pre-Con
PC-E-013 | Procurement Strategy | Planning and market engagement | Modern Slavery, Sanctions and Ethical Procurement Checks | Records mandatory supply-chain compliance and any client-specific declarations. | TBC | Not Started | High | Tier 3 - Internal Control | Procurement | Expanded recommendation | Internal / Client | Before award | Legal; H&S |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.20 Supply Chain Management | SCM | PROJ-MCR-CM-SCM-0008_ModernSlavery | CA | Stage 3 - Pre-Con
PC-E-014 | Procurement Strategy | Planning and market engagement | Social Value / Local Labour Procurement Plan | Allocates contractual social-value, apprenticeship, SME and local-spend obligations to packages. | TBC | Not Started | High | Tier 2 - Commercial Review | Procurement | Project Manager; QS | Client / Internal | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.30 Responsible Procurement | RSP | PROJ-MCR-CM-RSP-0001_SocialValue | PCC | Stage 3 - Pre-Con
PC-E-015 | Procurement Strategy | Planning and market engagement | Sustainable Procurement and Responsible Sourcing Schedule | Captures FSC/PEFC, BES 6001, EPD, recycled content and embodied-carbon evidence requirements. | TBC | Not Started | High | Tier 2 - Commercial Review | Procurement | Sustainability Lead; Design Manager | Internal / Client | Pre-construction | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.30 Responsible Procurement | RSP | PROJ-MCR-CM-RSP-0002_SustainableProcurementResponsibleSourcingSchedule | PCC | Stage 3 - Pre-Con
PC-F-001 | Tendering & Package Award | Package enquiry and adjudication | Package Enquiry / ITT Document Checklist | Controls issue of scope, drawings, specifications, programme, prelims and return schedules. | TBC | Not Started | Critical | Tier 3 - Internal Control | QS | Document Controller | Internal | Before enquiry | Per package |  |  |  | Source Word register |  | 4.0 Procurement & Package Award | 4.40 Package Enquiry | PKE | PROJ-MCR-CM-PKE-0002_PackageEnquiry | QS | Stage 3 - Pre-Con
PC-F-002 | Tendering & Package Award | Package enquiry and adjudication | Tender Return Schedule and Pricing Template | Forces comparable returns and exposes allowances, quantities, rates, exclusions and proposed changes. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Estimator | Internal / Bidder | Before enquiry | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.40 Package Enquiry | PKE | PROJ-MCR-CM-PKE-0004_TenderReturnSchedulePricingTemplate | QS | Stage 3 - Pre-Con
PC-F-003 | Tendering & Package Award | Package enquiry and adjudication | Tender Query and Clarification Log - per package | Maintains a fair, auditable record of clarifications given to bidders. | TBC | Not Started | High | Tier 3 - Internal Control | QS | Design Manager | Internal | Tender period | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.40 Package Enquiry | PKE | PROJ-MCR-CM-PKE-0005_TenderQueryClarificationLog | QS | Stage 3 - Pre-Con
PC-F-004 | Tendering & Package Award | Package enquiry and adjudication | Tender Return Register | Records invitations, returns, withdrawals, late bids and completeness. | TBC | Not Started | High | Tier 2 - Commercial Review | Procurement | QS | Internal | Tender return | Per package |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.50 Package Tender Analysis | PTA | PROJ-MCR-CM-PTA-0001_TenderReturnRegister | QS | Stage 3 - Pre-Con
PC-F-005 | Tendering & Package Award | Package enquiry and adjudication | Tender Analysis Sheet / Tender Comparison Matrix | Levels price, scope, qualifications, programme and commercial terms across bidders. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Commercial Manager | Internal | Tender analysis | Per package |  |  |  | Both source lists |  | 4.0 Procurement & Package Award | 4.50 Package Tender Analysis | PTA | PROJ-MCR-CM-PTA-0002_TenderAnalysisSheet | QS | Stage 3 - Pre-Con
PC-F-006 | Tendering & Package Award | Package enquiry and adjudication | Tender Interview / Mid-Bid Meeting Record | Records clarifications and commitments made during bidder meetings. | TBC | Not Started | High | Tier 3 - Internal Control | QS | Design Manager; Project Manager | Internal | Tender analysis | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0001_TenderInterview | QS | Stage 3 - Pre-Con
PC-F-007 | Tendering & Package Award | Package enquiry and adjudication | Pre-Let / Pre-Award Meeting Minutes | Final record of agreed scope, price, programme, terms, design and outstanding actions before commitment. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Commercial Manager; Project Manager | Internal / Subcontractor | Before award | Per package |  |  |  | Source Word register |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0002_PreLet | QS | Stage 3 - Pre-Con
PC-F-008 | Tendering & Package Award | Package enquiry and adjudication | Commercial Recommendation Report | Documents value-for-money assessment, risk, budget movement and recommendation to award. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | QS | Commercial Manager | Board / Internal | Before award | Per package |  |  |  | Source workbook |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0003_CommercialRecommendationReport | QS | Stage 3 - Pre-Con
PC-F-009 | Tendering & Package Award | Package enquiry and adjudication | Award Approval / DeleStaged Authority Record | Confirms commitment is authorised at the correct value and risk level. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Commercial Director; Finance | Board / Internal | Before award | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0004_AwardApproval | QS | Stage 3 - Pre-Con
PC-F-010 | Tendering & Package Award | Package enquiry and adjudication | Buying Gains / Losses Tracker | Records package award against budget and distinguishes real savings from scope transfer or risk. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | QS | Commercial Manager | Board / Internal | At award | Weekly / monthly |  |  |  | Source Word register |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0005_BuyingGains | QS | Stage 3 - Pre-Con
PC-F-011 | Tendering & Package Award | Package enquiry and adjudication | Post-Tender Negotiation Record | Provides an auditable record of negotiation movements, concessions and final agreed basis. | TBC | Not Started | High | Tier 3 - Internal Control | QS | Commercial Manager | Internal | Before award | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0006_PostTenderNegotiationRecord | QS | Stage 3 - Pre-Con
PC-F-012 | Tendering & Package Award | Package enquiry and adjudication | Bid Validity and Price Hold Confirmation | Confirms offer validity, fixed-price period, inflation terms and conditions before award. | TBC | Not Started | Critical | Tier 3 - Internal Control | QS | Procurement | Internal | Before award | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0007_BidValidityPriceHoldConfirmation | QS | Stage 3 - Pre-Con
PC-F-013 | Tendering & Package Award | Package enquiry and adjudication | Unsuccessful Tenderer Close-Out Record | Records notification and preserves procurement audit trail. | TBC | Not Started | Low | Tier 3 - Internal Control | Procurement | QS | Internal | After award | Per package |  |  |  | Expanded recommendation |  | 4.0 Procurement & Package Award | 4.60 Package Award & Recommendation | PAW | PROJ-MCR-CM-PAW-0008_UnsuccessfulTendererCloseOutRecord | QS | Stage 3 - Pre-Con
PC-G-001 | Subcontract Formation | Orders and downstream risk | Subcontract Order Schedule | Master schedule of package, contractor, value, form, status and execution date. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | QS; Procurement | Internal | Pre-start | Weekly |  |  |  | Source workbook |  | 5.0 Subcontract Formation | 5.10 Order Control | SCO | PROJ-MCR-CM-SCO-0001_SubcontractOrderSchedule | PCC | Stage 3 - Pre-Con
PC-G-002 | Subcontract Formation | Orders and downstream risk | Approved Subcontract / Purchase Order Templates | Standard forms approved for the project and aligned with main-contract obligations. | TBC | Not Started | Critical | Tier 3 - Internal Control | Legal | Commercial Manager | Internal | Pre-construction | Once |  |  |  | Source Word register |  | 0.0 Admin & Document Control | 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0001_ApprovedSubcontract | CA | Stage 3 - Pre-Con
PC-G-003 | Subcontract Formation | Orders and downstream risk | Subcontract Programme and Key Dates Schedule | Incorporates design, approvals, procurement, mobilisation, work and handover milestones. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Planner | Project Manager; QS | Internal / Subcontractor | Before award | Per package |  |  |  | Expanded recommendation |  | 5.0 Subcontract Formation | 5.20 Downstream Terms & Flow-Down | SDT | PROJ-MCR-CM-SDT-0005_SubcontractProgrammeKeyDatesSchedule | QS | Stage 3 - Pre-Con
PC-G-004 | Subcontract Formation | Orders and downstream risk | Subcontract Damages / Delay Recovery Schedule | Aligns downstream delay recovery with upstream exposure and actual likely loss. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Legal; Planner | Internal | Before award | Per package |  |  |  | Expanded recommendation |  | 5.0 Subcontract Formation | 5.20 Downstream Terms & Flow-Down | SDT | PROJ-MCR-CM-SDT-0006_SubcontractDamages | QS | Stage 3 - Pre-Con
PC-G-005 | Subcontract Formation | Orders and downstream risk | Collateral Warranty / Third-Party Rights Flow-Down Schedule | Allocates warranty providers, beneficiaries, form, execution method and delivery date. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Legal; QS | Internal | Before award | Per package |  |  |  | Expanded recommendation |  | 5.0 Subcontract Formation | 5.30 Security & Insurance | SSI | PROJ-MCR-CM-SSI-0001_CollateralWarranty | CA | Stage 3 - Pre-Con
PC-G-006 | Subcontract Formation | Orders and downstream risk | Subcontract Insurance Requirements Schedule | Sets works, PL, EL, PI, product and other cover requirements with expiry monitoring. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Insurance Broker; Procurement | Internal | Before award | Per package |  |  |  | Source Word register |  | 5.0 Subcontract Formation | 5.30 Security & Insurance | SSI | PROJ-MCR-CM-SSI-0002_SubcontractInsuranceRequirementsSchedule | CA | Stage 3 - Pre-Con
PC-G-007 | Subcontract Formation | Orders and downstream risk | Subcontract Bond / Parent Company Guarantee Requirements | Defines security wording, value, expiry and release conditions. | TBC | Not Started | High | Tier 2 - Commercial Review | Commercial Manager | Legal; Finance | Internal | Before award | Per package |  |  |  | Expanded recommendation |  | 5.0 Subcontract Formation | 5.30 Security & Insurance | SSI | PROJ-MCR-CM-SSI-0003_SubcontractBond | CA | Stage 3 - Pre-Con
PC-G-008 | Subcontract Formation | Orders and downstream risk | Letter of Intent Tracker | Controls scope, cap, expiry, authority, insurance and conversion to full order. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | QS; Legal | Internal | Pre-start | Weekly |  |  |  | Source workbook |  | 5.0 Subcontract Formation | 5.10 Order Control | SCO | PROJ-MCR-CM-SCO-0002_LetterIntentTracker | PCC | Stage 3 - Pre-Con
PC-G-009 | Subcontract Formation | Orders and downstream risk | Executed Subcontract Register | Confirms signature status, counterpart, deed execution and storage location. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | Document Controller; Legal | Internal | Pre-start | Weekly |  |  |  | Expanded recommendation |  | 5.0 Subcontract Formation | 5.10 Order Control | SCO | PROJ-MCR-CM-SCO-0003_ExecutedSubcontractRegister | PCC | Stage 3 - Pre-Con
PC-G-010 | Subcontract Formation | Orders and downstream risk | Off-Site Materials and Vesting Procedure | Protects title, identification, insurance and access rights for paid off-site materials. | TBC | Not Started | High | Tier 3 - Internal Control | QS | Legal; Finance | Internal / Subcontractor | Before off-site payment | Per item |  |  |  | Source Word register |  | 5.0 Subcontract Formation | 5.40 Materials & Mobilisation | SMM | PROJ-MCR-CM-SMM-0001_OffSiteMaterialsVestingProcedure | QS | Stage 3 - Pre-Con
PC-H-001 | Cashflow, Payment & Tax | Upstream and downstream cash controls | Client Payment Schedule | Lists application, due, notice, final and payment dates including non-business day rules. | TBC | Not Started | Critical | Tier 3 - Internal Control | QS | Commercial Manager | Internal | Contract execution | Once / contract change |  |  |  | Source Word register |  | 6.0 Cashflow, Payment & Tax | 6.10 Payment Framework | PYF | PROJ-MCR-CM-PYF-0001_ClientPaymentSchedule | QS | Stage 2 - Award
PC-H-002 | Cashflow, Payment & Tax | Upstream and downstream cash controls | Cashflow Forecast (Income and Expenditure) | Forecasts upstream receipts and downstream cash by month and identifies funding gaps. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | QS | Finance; Planner | Board / Internal | Pre-construction | Monthly |  |  |  | Both source lists |  | 6.0 Cashflow, Payment & Tax | 6.20 Cashflow & Funding | CFF | PROJ-MCR-CM-CFF-0001_CashflowForecast | PCC | Stage 3 - Pre-Con
PC-H-003 | Cashflow, Payment & Tax | Upstream and downstream cash controls | Working Capital and Peak Funding Assessment | Quantifies maximum negative cash and finance requirement under realistic payment timings. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Finance | Commercial Manager | Board / Internal | Pre-contract | At major programme or payment change |  |  |  | Expanded recommendation |  | 6.0 Cashflow, Payment & Tax | 6.20 Cashflow & Funding | CFF | PROJ-MCR-CM-CFF-0002_WorkingCapitalPeakFundingAssessment | PCC | Stage 2 - Award
PC-H-004 | Cashflow, Payment & Tax | Upstream and downstream cash controls | Retention Register | Tracks upstream and downstream retention, caps, release triggers and forecast release dates. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | QS | Finance | Board / Internal | Pre-start onward | Monthly |  |  |  | Source workbook |  | 6.0 Cashflow, Payment & Tax | 6.20 Cashflow & Funding | CFF | PROJ-MCR-CM-CFF-0003_RetentionRegister | PCC | Stage 3 - Pre-Con
PC-H-005 | Cashflow, Payment & Tax | Upstream and downstream cash controls | Project Bank Account / Escrow Requirements | Records account rules, beneficiaries, joining deeds and payment processes where applicable. | TBC | Not Started | High | Tier 2 - Commercial Review | Finance | Commercial Manager; Legal | Internal / Client | Pre-start | Monthly |  |  |  | Expanded recommendation |  | 6.0 Cashflow, Payment & Tax | 6.30 Tax & Payment Security | TPS | PROJ-MCR-CM-TPS-0003_ProjectBankAccount | PCC | Stage 3 - Pre-Con
PC-H-006 | Cashflow, Payment & Tax | Upstream and downstream cash controls | Cost Accrual and Invoice Cut-Off Procedure | Defines monthly accruals, GRNs, invoice coding and cost-report cut-off. | TBC | Not Started | High | Tier 3 - Internal Control | Finance | QS | Internal | Pre-start | Monthly |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0001_CostAccrualInvoiceCutOff | CA | Stage 3 - Pre-Con
PC-H-007 | Cashflow, Payment & Tax | Upstream and downstream cash controls | Materials on Site Evidence Requirements | Defines proof required to include materials in upstream applications and downstream valuations. | TBC | Not Started | High | Tier 3 - Internal Control | QS | Project Manager | Internal | Pre-start | Once / each valuation |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0002_MaterialsOnSiteEvidenceRequirements | CA | Stage 3 - Pre-Con
PC-I-001 | Risk, Opportunity & Governance | Commercial governance | Commercial Risk Register | Quantifies exposure, probability, mitigation, owner, allowance and residual risk. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Project Manager; QS | Board / Internal | Pre-construction | Monthly |  |  |  | Both source lists |  | 7.0 Risk, Governance & Entitlement | 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0001_CommercialRiskRegister | PCC | Stage 3 - Pre-Con
PC-I-002 | Risk, Opportunity & Governance | Commercial governance | Risk Mitigation Plan | Turns each material risk into dated actions with accountable owners. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Risk Owners | Internal | Pre-construction | Monthly |  |  |  | Source workbook |  | 7.0 Risk, Governance & Entitlement | 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0002_RiskMitigationPlan | PCC | Stage 3 - Pre-Con
PC-I-003 | Risk, Opportunity & Governance | Commercial governance | Risk Ownership Matrix | Makes responsibility and escalation unambiguous across the project team. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Project Manager | Internal | Pre-construction | Once / team change |  |  |  | Source workbook |  | 7.0 Risk, Governance & Entitlement | 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0003_RiskOwnershipMatrix | PCC | Stage 3 - Pre-Con
PC-I-004 | Risk, Opportunity & Governance | Commercial governance | Opportunity Register | Records savings, recovery opportunities, probability, actions and forecast benefit. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | QS; Design Manager | Board / Internal | Pre-construction | Monthly |  |  |  | Source workbook |  | 7.0 Risk, Governance & Entitlement | 7.10 Risk & Opportunity Registers | RSK | PROJ-MCR-CM-RSK-0004_OpportunityRegister | PCC | Stage 3 - Pre-Con
PC-I-005 | Risk, Opportunity & Governance | Commercial governance | Commercial Risk Workshop Minutes | Provides contemporaneous record of risk challenge, decisions and management actions. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Project Team | Internal | Pre-construction | Monthly / stage Stage |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0001_CommercialRiskWorkshopMinutes | CA | Stage 3 - Pre-Con
PC-I-006 | Risk, Opportunity & Governance | Commercial governance | Commercial Responsibility Matrix (RACI) | Allocates estimating, procurement, cost reporting, change, notices and final-account duties. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Project Manager | Internal | Pre-construction | Once / team change |  |  |  | Source Word register |  | 0.0 Admin & Document Control | 0.30 DeleStaged Authority & Governance | GOV | PROJ-MCR-CM-GOV-0003_CommercialResponsibilityMatrix | CM | Stage 3 - Pre-Con
PC-I-007 | Risk, Opportunity & Governance | Commercial governance | Conflict of Interest Declarations | Records conflicts affecting procurement, appointment or approval decisions. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Director | Procurement; Legal | Internal | Pre-construction | Per decision / annual |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.30 DeleStaged Authority & Governance | GOV | PROJ-MCR-CM-GOV-0004_ConflictInterestDeclarations | CM | Stage 3 - Pre-Con
PC-I-008 | Risk, Opportunity & Governance | Commercial governance | Fraud, Bribery and Gifts/Hospitality Compliance Record | Protects procurement integrity and confirms compliance with company and client requirements. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Director | Procurement; Legal | Internal | Pre-construction | At onboarding / trigger |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.30 DeleStaged Authority & Governance | GOV | PROJ-MCR-CM-GOV-0005_Fraud | CM | Stage 3 - Pre-Con
PC-I-009 | Risk, Opportunity & Governance | Commercial governance | Commercial Lessons Learned / Benchmark Brief | Brings previous project losses, claims and procurement lessons into package strategy. | TBC | Not Started | Medium | Tier 3 - Internal Control | Commercial Manager | Estimator; Project Manager | Internal | Pre-construction | Once / key stage |  |  |  | Expanded recommendation |  | 7.0 Risk, Governance & Entitlement | 7.40 Lessons Learned | LSN | PROJ-MCR-CM-LSN-0001_CommercialLessonsLearned | PCC | Stage 3 - Pre-Con
PC-J-001 | Change, Claims & Entitlement | Entitlement protection | Change Control Procedure | Defines identification, instruction, quotation, approval, implementation and reporting of change. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Design Manager; Project Manager | Internal / Client | Pre-start | Once |  |  |  | Source Word register |  | 0.0 Admin & Document Control | 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0003_ChangeControlProcedure | CA | Stage 3 - Pre-Con
PC-J-002 | Change, Claims & Entitlement | Entitlement protection | Variation / Compensation Event Register | Live record of instructed and anticipated changes, time, cost, status and payment. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | QS | Planner; Design Manager | Client / Internal | Pre-start onward | Live / monthly report |  |  |  | Both source lists |  | 7.0 Risk, Governance & Entitlement | 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0001_Variation | QS | Stage 3 - Pre-Con
PC-J-003 | Change, Claims & Entitlement | Entitlement protection | Client / Architect / Contract Administrator Instruction Register | Records every instruction, authority, issue date and commercial/programme response. | TBC | Not Started | Critical | Tier 3 - Internal Control | QS | Document Controller | Internal | Pre-start onward | Live |  |  |  | Source workbook |  | 7.0 Risk, Governance & Entitlement | 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0003_Client | QS | Stage 3 - Pre-Con
PC-J-004 | Change, Claims & Entitlement | Entitlement protection | Early Warning Register | Records emerging cost/programme risks and required mitigation where contractually applicable. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Project Manager | Commercial Manager; Planner | Internal / Client | Pre-start onward | Weekly |  |  |  | Source workbook |  | 7.0 Risk, Governance & Entitlement | 7.30 Entitlement & Claims Set-Up | ENT | PROJ-MCR-CM-ENT-0003_EarlyWarningRegister | CM | Stage 3 - Pre-Con
PC-J-005 | Change, Claims & Entitlement | Entitlement protection | Extension of Time Procedure and Impact Register | Tracks delay events, notices, cause/effect, programme analysis and submission status. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Planner | Commercial Manager; Project Manager | Internal / Client | Pre-start | Weekly / monthly |  |  |  | Both source lists |  | 7.0 Risk, Governance & Entitlement | 7.30 Entitlement & Claims Set-Up | ENT | PROJ-MCR-CM-ENT-0005_ExtensionTimeProcedureImpactRegister | CM | Stage 3 - Pre-Con
PC-J-006 | Change, Claims & Entitlement | Entitlement protection | Dayworks Procedure, Agreed Rates and Register | Controls authorisation, daily records, signatures, mark-ups, valuation and recovery. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Project Manager | Internal / Client | Pre-start | Live |  |  |  | Both source lists |  | 7.0 Risk, Governance & Entitlement | 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0004_DayworksProcedure | QS | Stage 3 - Pre-Con
PC-J-007 | Change, Claims & Entitlement | Entitlement protection | Contra-Charge Procedure and Register | Controls notice, evidence, valuation and recovery from defaulting supply-chain parties. | TBC | Not Started | High | Tier 3 - Internal Control | QS | Project Manager | Internal | Pre-start onward | Live |  |  |  | Both source lists |  | 7.0 Risk, Governance & Entitlement | 7.20 Change & Variation Control | CVC | PROJ-MCR-CM-CVC-0005_ContraChargeProcedureRegister | QS | Stage 3 - Pre-Con
PC-J-008 | Change, Claims & Entitlement | Entitlement protection | Final Account Strategy Register | Identifies target position, recoveries, concessions, evidence gaps, ownership and negotiation strategy. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | QS; Legal | Board / Internal | Pre-start | Monthly / quarterly |  |  |  | Both source lists |  | 7.0 Risk, Governance & Entitlement | 7.30 Entitlement & Claims Set-Up | ENT | PROJ-MCR-CM-ENT-0006_FinalAccountStrategyRegister | CM | Stage 3 - Pre-Con
PC-J-009 | Change, Claims & Entitlement | Entitlement protection | Claims Legal Privilege and Review Protocol | Defines when legal advice is sought and how privileged material is controlled. | TBC | Not Started | High | Tier 3 - Internal Control | Legal | Commercial Director | Internal | Pre-start | Once / trigger |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0006_ClaimsLegalPrivilegeReviewProtocol | CA | Stage 3 - Pre-Con
PC-K-001 | Programme & Delay Commercials | Programme commercial controls | Accepted / Contract Baseline Programme | Preserves the programme against which delay, progress and compensation are assessed. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Planner | Project Manager; Commercial Manager | Client / Internal | Pre-start | Once / formal revision |  |  |  | Expanded recommendation |  | 8.0 Programme & Delay Commercials | 8.10 Baseline Programme & Constraints | PGM | PROJ-MCR-CM-PGM-0001_Accepted | PCC | Stage 3 - Pre-Con
PC-K-002 | Programme & Delay Commercials | Programme commercial controls | Programme Assumptions and Constraints Register | Records access, working hours, approvals, possessions, interfaces and client dependencies. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Planner | Project Manager; QS | Internal / Client | Pre-start | Live |  |  |  | Expanded recommendation |  | 8.0 Programme & Delay Commercials | 8.10 Baseline Programme & Constraints | PGM | PROJ-MCR-CM-PGM-0002_ProgrammeAssumptionsConstraintsRegister | PCC | Stage 3 - Pre-Con
PC-K-003 | Programme & Delay Commercials | Programme commercial controls | Sectional Completion and Key Dates Schedule | Aligns contractual milestones, LAD exposure, access and package obligations. | TBC | Not Started | Critical | Tier 3 - Internal Control | Planner | Commercial Manager | Internal | Pre-start | Live |  |  |  | Expanded recommendation |  | 8.0 Programme & Delay Commercials | 8.10 Baseline Programme & Constraints | PGM | PROJ-MCR-CM-PGM-0003_SectionalCompletionKeyDatesSchedule | PCC | Stage 3 - Pre-Con
PC-K-004 | Programme & Delay Commercials | Programme commercial controls | Delay Notice and EOT Submission Templates | Provides contract-compliant notices and structured evidence requirements before events occur. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Planner; Legal | Internal | Pre-start | Once |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0004_DelayNoticeEOTSubmissionTemplates | CA | Stage 3 - Pre-Con
PC-K-005 | Programme & Delay Commercials | Programme commercial controls | Float Ownership and Concurrent Delay Position Note | Records project approach to float, concurrency and mitigation before disputes arise. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Planner; Legal | Internal | Pre-start | Once / contract change |  |  |  | Expanded recommendation |  | 8.0 Programme & Delay Commercials | 8.20 Delay & LADs Commercials | DLY | PROJ-MCR-CM-DLY-0002_FloatOwnershipConcurrentDelayPosition | PCC | Stage 3 - Pre-Con
PC-K-006 | Programme & Delay Commercials | Programme commercial controls | Programme Risk Allowance / Schedule Risk Analysis | Quantifies schedule uncertainty and its commercial consequences. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Planner | Commercial Manager | Board / Internal | Pre-construction | At baseline / major change |  |  |  | Expanded recommendation |  | 8.0 Programme & Delay Commercials | 8.20 Delay & LADs Commercials | DLY | PROJ-MCR-CM-DLY-0003_ProgrammeRiskAllowance | PCC | Stage 3 - Pre-Con
PC-L-001 | Insurance, Security & Warranties | Risk transfer and security | Main Contract Insurance Schedule and Evidence | Confirms correct works, existing structures, PL, EL, PI and other cover before work starts. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Insurance Broker; Legal | Client / Board | Pre-start | At inception / renewal |  |  |  | Both source lists |  | 9.0 Insurance, Security & Warranties | 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0001_MainContractInsuranceScheduleEvidence | CA | Stage 3 - Pre-Con
PC-L-002 | Insurance, Security & Warranties | Risk transfer and security | Insurance Responsibility Matrix | Allocates policies, insured parties, deductibles, limits and evidence responsibilities. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Legal; Project Manager | Internal | Pre-start | Once / change |  |  |  | Expanded recommendation |  | 9.0 Insurance, Security & Warranties | 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0002_InsuranceResponsibilityMatrix | CA | Stage 3 - Pre-Con
PC-L-003 | Insurance, Security & Warranties | Risk transfer and security | Performance Bond Tracker | Tracks wording, issuer, value, expiry, reduction and release. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Finance; Legal | Client / Board | Pre-start | Monthly |  |  |  | Source workbook |  | 9.0 Insurance, Security & Warranties | 9.20 Bonds & Guarantees | BND | PROJ-MCR-CM-BND-0001_PerformanceBondTracker | CA | Stage 3 - Pre-Con
PC-L-004 | Insurance, Security & Warranties | Risk transfer and security | Parent Company Guarantee Tracker | Tracks required PCGs, execution, validity, release and corporate approvals. | TBC | Not Started | High | Tier 2 - Commercial Review | Commercial Manager | Legal; Finance | Internal / Client | Pre-start | Monthly |  |  |  | Expanded recommendation |  | 9.0 Insurance, Security & Warranties | 9.20 Bonds & Guarantees | BND | PROJ-MCR-CM-BND-0002_ParentCompanyGuaranteeTracker | CA | Stage 3 - Pre-Con
PC-L-005 | Insurance, Security & Warranties | Risk transfer and security | Collateral Warranty Matrix | Tracks providers, beneficiaries, wording, execution route, status and delivery date. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Legal; QS | Client / Internal | Pre-start | Monthly |  |  |  | Both source lists |  | 9.0 Insurance, Security & Warranties | 9.30 Warranties & Third-Party Rights | WTR | PROJ-MCR-CM-WTR-0001_CollateralWarrantyMatrix | CA | Stage 3 - Pre-Con
PC-L-006 | Insurance, Security & Warranties | Risk transfer and security | Third-Party Rights Schedule | Identifies rights granted, beneficiaries, step-in rights and equivalent subcontract flow-down. | TBC | Not Started | High | Tier 2 - Commercial Review | Legal | Commercial Manager | Internal / Client | Pre-start | Monthly |  |  |  | Expanded recommendation |  | 9.0 Insurance, Security & Warranties | 9.30 Warranties & Third-Party Rights | WTR | PROJ-MCR-CM-WTR-0002_ThirdPartyRightsSchedule | CA | Stage 3 - Pre-Con
PC-L-007 | Insurance, Security & Warranties | Risk transfer and security | Warranty Register | Tracks product, workmanship, design and specialist warranties required for handover. | TBC | Not Started | High | Tier 2 - Commercial Review | QS | Design Manager; Document Controller | Internal | Pre-construction | Monthly |  |  |  | Source workbook |  | 9.0 Insurance, Security & Warranties | 9.30 Warranties & Third-Party Rights | WTR | PROJ-MCR-CM-WTR-0003_WarrantyRegister | CA | Stage 3 - Pre-Con
PC-L-008 | Insurance, Security & Warranties | Risk transfer and security | Professional Indemnity Insurance Schedule | Tracks designers, subcontract designers, limits, expiry and required run-off period. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Design Manager | Legal; Commercial Manager | Internal / Client | Pre-start | Quarterly / renewal |  |  |  | Expanded recommendation |  | 9.0 Insurance, Security & Warranties | 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0004_ProfessionalIndemnityInsuranceSchedule | CA | Stage 3 - Pre-Con
PC-L-009 | Insurance, Security & Warranties | Risk transfer and security | Latent Defects / Structural Warranty Requirements | Records provider inspections, fees, technical requirements and certification milestones. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Design Manager; Project Manager | Client / Internal | Pre-start | Monthly |  |  |  | Expanded recommendation |  | 9.0 Insurance, Security & Warranties | 9.10 Project Insurances | INS | PROJ-MCR-CM-INS-0005_LatentDefects | CA | Stage 3 - Pre-Con
PC-M-001 | Property, Statutory & Third Parties | Consents and external obligations | Planning Permission and Condition Cost Register | Tracks discharge conditions, obligations, fees, works and cost owners. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Design Manager; Planner | Internal / Client | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.10 Planning & Statutory Obligations | STA | PROJ-MCR-CM-STA-0001_PlanningPermissionConditionCostRegister | PCC | Stage 3 - Pre-Con
PC-M-002 | Property, Statutory & Third Parties | Consents and external obligations | Section 106 / Community Infrastructure Levy Schedule | Records financial contributions, triggers, indexation, works obligations and responsibility. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Legal; Client | Client / Board | Pre-contract | At trigger / monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.10 Planning & Statutory Obligations | STA | PROJ-MCR-CM-STA-0002_Section106 | PCC | Stage 2 - Award
PC-M-003 | Property, Statutory & Third Parties | Consents and external obligations | Building Regulations / Building Control Fees and Requirements | Captures approval route, fees, inspections, Stageway obligations and design implications. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Design Manager | Commercial Manager | Internal / Client | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.10 Planning & Statutory Obligations | STA | PROJ-MCR-CM-STA-0003_BuildingRegulations | PCC | Stage 3 - Pre-Con
PC-M-004 | Property, Statutory & Third Parties | Consents and external obligations | Party Wall Awards / Neighbour Agreements Register | Tracks notices, awards, surveyor fees, access constraints, protections and contractor obligations. | TBC | Not Started | High | Tier 2 - Commercial Review | Project Manager | Legal; Commercial Manager | Internal / Client | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0001_PartyWallAwards | PCC | Stage 3 - Pre-Con
PC-M-005 | Property, Statutory & Third Parties | Consents and external obligations | Rights of Light / Oversailing / Crane Licence Register | Records third-party rights, licences, fees, conditions and programme restrictions. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Project Manager | Legal; Planner | Board / Internal | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0002_RightsLight | PCC | Stage 3 - Pre-Con
PC-M-006 | Property, Statutory & Third Parties | Consents and external obligations | Landlord / Tenant / Lease Interface Schedule | Identifies lease obligations, approvals, landlord works, tenant works and cost responsibilities. | TBC | Not Started | High | Tier 2 - Commercial Review | Commercial Manager | Legal; Design Manager | Internal / Client | Pre-construction | Live |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0003_Landlord | PCC | Stage 3 - Pre-Con
PC-M-007 | Property, Statutory & Third Parties | Consents and external obligations | Highways / Section 278 / Section 38 Obligations Schedule | Records scope, bonds, fees, approvals, commuted sums and adoption requirements. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Civils Manager; Legal | Client / Internal | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0001_Highways | PCC | Stage 3 - Pre-Con
PC-M-008 | Property, Statutory & Third Parties | Consents and external obligations | Drainage / Section 104 and Water Authority Schedule | Records applications, bonds, inspections, diversions, adoption and connection charges. | TBC | Not Started | High | Tier 2 - Commercial Review | Commercial Manager | Civils Manager; MEP Manager | Internal / Client | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0002_Drainage | PCC | Stage 3 - Pre-Con
PC-M-009 | Property, Statutory & Third Parties | Consents and external obligations | Utility Search, Diversion and Connection Register | Captures existing services risk, quotations, lead times, capacity, diversions and permanent connections. | TBC | Not Started | Critical | Tier 2 - Commercial Review | MEP Manager | QS; Planner | Internal / Client | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0003_UtilitySearch | PCC | Stage 3 - Pre-Con
PC-M-010 | Property, Statutory & Third Parties | Consents and external obligations | Environmental Permits / Licences Cost Schedule | Records permits, consents, monitoring, fees and compliance resource. | TBC | Not Started | High | Tier 3 - Internal Control | Project Manager | Environmental Lead; QS | Internal | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.20 Utilities & Infrastructure | UTL | PROJ-MCR-CM-UTL-0004_EnvironmentalPermits | PCC | Stage 3 - Pre-Con
PC-M-011 | Property, Statutory & Third Parties | Consents and external obligations | Access, Easement and Wayleave Register | Records rights needed for access, services, compounds and permanent infrastructure. | TBC | Not Started | High | Tier 2 - Commercial Review | Project Manager | Legal; Planner | Internal / Client | Pre-construction | Monthly |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.30 Third-Party & Neighbour Rights | TPR | PROJ-MCR-CM-TPR-0004_Access | PCC | Stage 3 - Pre-Con
PC-M-012 | Property, Statutory & Third Parties | Consents and external obligations | Client Direct Suppliers / Nominated Parties Interface Schedule | Defines scope, attendance, programme, warranty, payment and liability interfaces. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Design Manager; Project Manager | Internal / Client | Pre-construction | Live |  |  |  | Expanded recommendation |  | 10.0 Property, Statutory & Third Parties | 10.40 Ground & Interface Risk | GIR | PROJ-MCR-CM-GIR-0002_ClientDirectSuppliers | CM | Stage 3 - Pre-Con
PC-N-001 | Reporting & Project Controls | Commercial reporting system | Monthly Commercial Report Template | Standard report for cost, value, cash, procurement, risk, change and forecast. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | QS; Finance | Board / Internal | Pre-start | Monthly |  |  |  | Both source lists |  | 0.0 Admin & Document Control | 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0005_MonthlyCommercialReportTemplate | CA | Stage 3 - Pre-Con
PC-N-002 | Reporting & Project Controls | Commercial reporting system | CVR Reporting Calendar and Template | Defines monthly cut-off, responsibilities, review dates and approval route. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | QS; Finance | Internal | Pre-start | Monthly |  |  |  | Source Word register |  | 0.0 Admin & Document Control | 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0006_CVRReportingCalendarTemplate | CA | Stage 3 - Pre-Con
PC-N-003 | Reporting & Project Controls | Commercial reporting system | Cost Value Reconciliation Template | Compares budget, commitments, accruals, actual cost, value, risk and forecast margin. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Commercial Manager; Finance | Internal | Pre-start | Monthly |  |  |  | Source workbook |  | 0.0 Admin & Document Control | 0.20 Standard Templates | TMP | PROJ-MCR-CM-TMP-0007_CostValueReconciliationTemplate | CA | Stage 3 - Pre-Con
PC-N-004 | Reporting & Project Controls | Commercial reporting system | Cost Forecast / Forecast Final Cost Report | Forecasts remaining commitments and final cost by package and cost code. | TBC | Not Started | Critical | Tier 2 - Commercial Review | QS | Commercial Manager | Internal | Pre-start | Monthly |  |  |  | Source workbook |  | 11.0 Commercial Reporting & Controls | 11.20 Cost & Procurement Reporting | RPC | PROJ-MCR-CM-RPC-0001_CostForecast | PCC | Stage 3 - Pre-Con
PC-N-005 | Reporting & Project Controls | Commercial reporting system | Client Commercial Reporting Format | Agrees report content, cut-off, narrative, evidence, KPIs and meeting cycle. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | Client QS | Client / Internal | Pre-start | Once / revision |  |  |  | Source workbook |  | 11.0 Commercial Reporting & Controls | 11.10 Reporting Framework | RPT | PROJ-MCR-CM-RPT-0002_ClientCommercialReportingFormat | PCC | Stage 3 - Pre-Con
PC-N-006 | Reporting & Project Controls | Commercial reporting system | Procurement Status Report | Summarises tender, approval, award, execution, long-lead and risk position. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | Commercial Manager | QS; Procurement | Client / Board | Pre-construction | Monthly |  |  |  | Source workbook |  | 11.0 Commercial Reporting & Controls | 11.20 Cost & Procurement Reporting | RPC | PROJ-MCR-CM-RPC-0002_ProcurementStatusReport | PCC | Stage 3 - Pre-Con
PC-N-007 | Reporting & Project Controls | Commercial reporting system | Commercial KPI Schedule | Defines measures for buying, margin, cash, change recovery, notices, orders and final account. | TBC | Not Started | Medium | Tier 1 - Board / Client Visibility | Commercial Director | Commercial Manager | Board / Internal | Pre-start | Monthly |  |  |  | Expanded recommendation |  | 11.0 Commercial Reporting & Controls | 11.10 Reporting Framework | RPT | PROJ-MCR-CM-RPT-0003_CommercialKPISchedule | PCC | Stage 3 - Pre-Con
PC-N-008 | Reporting & Project Controls | Commercial reporting system | Commercial Meeting Calendar and Terms of Reference | Defines meetings, attendees, decisions, actions, reporting and escalation. | TBC | Not Started | Medium | Tier 3 - Internal Control | Commercial Manager | Project Director | Internal | Pre-start | Once / team change |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0002_CommercialMeetingCalendarTermsReference | CA | Stage 3 - Pre-Con
PC-N-009 | Reporting & Project Controls | Commercial reporting system | Decision and Approval Register | Records client and internal approvals affecting scope, cost, programme or risk. | TBC | Not Started | High | Tier 2 - Commercial Review | Commercial Manager | Document Controller | Internal / Client | Pre-construction | Live |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0003_DecisionApprovalRegister | CA | Stage 3 - Pre-Con
PC-N-010 | Reporting & Project Controls | Commercial reporting system | Commercial Action Tracker | Tracks actions from reports, risk reviews, procurement meetings and approvals. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Commercial Team | Internal | Pre-construction | Weekly |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.40 Meetings, Contacts & Decisions | MTG | PROJ-MCR-CM-MTG-0004_CommercialActionTracker | CA | Stage 3 - Pre-Con
PC-N-011 | Reporting & Project Controls | Commercial reporting system | Audit Trail / Document Control Protocol | Defines numbering, revision, approval, issue, superseded status and storage. | TBC | Not Started | Critical | Tier 3 - Internal Control | Document Controller | Commercial Manager | Internal | Pre-start | Once / audit monthly |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0007_AuditTrail | CA | Stage 3 - Pre-Con
PC-N-012 | Reporting & Project Controls | Commercial reporting system | Commercial File Structure and Naming Convention | Creates a consistent, searchable evidence base for every package and control. | TBC | Not Started | High | Tier 3 - Internal Control | Document Controller | Commercial Team | Internal | Pre-start | Once |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0008_CommercialFileStructureNamingConvention | CA | Stage 3 - Pre-Con
PC-N-013 | Reporting & Project Controls | Commercial reporting system | Data Access, Confidentiality and Retention Rules | Controls commercially sensitive bids, rates, personal data and legal retention periods. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Legal; IT | Internal | Pre-start | Once / annual review |  |  |  | Expanded recommendation |  | 0.0 Admin & Document Control | 0.10 Commercial Procedures & Protocols | PROC | PROJ-MCR-CM-PROC-0009_DataAccess | CA | Stage 3 - Pre-Con
PC-O-001 | Mobilisation & Delivery Handover | Pre-construction completion | Estimating-to-Delivery Handover Record | Formally transfers tender scope, assumptions, qualifications, risks and opportunities to delivery. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Estimator; QS; Project Manager | Board / Internal | Pre-start | Once |  |  |  | Source Word register |  | 12.0 Mobilisation & Pre-Start Handover | 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0001_EstimatingDeliveryHandoverRecord | CM | Stage 3 - Pre-Con
PC-O-002 | Mobilisation & Delivery Handover | Pre-construction completion | Pre-Construction Commercial Readiness Review | Stage review confirming contract, budget, procurement, orders, cash, risk and controls are ready. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Director | Commercial Manager; Project Director | Board / Internal | Before site start | Once |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0001_PreConstructionCommercialReadinessReview | CM | Stage 3 - Pre-Con
PC-O-003 | Mobilisation & Delivery Handover | Pre-construction completion | Commercial Mobilisation Checklist | Confirms systems, cost codes, templates, calendars, folders, authority and team responsibilities. | TBC | Not Started | Critical | Tier 3 - Internal Control | Commercial Manager | QS; Finance; Document Controller | Internal | Before site start | Once |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0002_CommercialMobilisationChecklist | CM | Stage 3 - Pre-Con
PC-O-004 | Mobilisation & Delivery Handover | Pre-construction completion | Package Readiness / Release-to-Procure Checklist | Confirms scope, design, budget, bidder list, programme and approvals before enquiry. | TBC | Not Started | Critical | Tier 3 - Internal Control | QS | Design Manager; Planner | Internal | Pre-construction | Per package |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.30 Package Readiness | PKR | PROJ-MCR-CM-PKR-0001_PackageReadiness | QS | Stage 3 - Pre-Con
PC-O-005 | Mobilisation & Delivery Handover | Pre-construction completion | Package Release-to-Start Checklist | Confirms order, scope, programme, design, insurance, RAMS, bonds and warranties before mobilisation. | TBC | Not Started | Critical | Tier 3 - Internal Control | QS | Project Manager; H&S | Internal | Pre-start | Per package |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.30 Package Readiness | PKR | PROJ-MCR-CM-PKR-0002_PackageReleaseStartChecklist | QS | Stage 3 - Pre-Con
PC-O-006 | Mobilisation & Delivery Handover | Pre-construction completion | Outstanding Commercial Decisions Register | Lists unresolved decisions, cost exposure, owner, deadline and default assumption. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Manager | Project Director; Client QS | Client / Board | Before site start | Weekly |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.40 Outstanding Commercial Exposure | EXP | PROJ-MCR-CM-EXP-0001_OutstandingCommercialDecisionsRegister | PCC | Stage 3 - Pre-Con
PC-O-007 | Mobilisation & Delivery Handover | Pre-construction completion | Open Qualifications / Assumptions Close-Out Schedule | Confirms each tender assumption is incorporated, agreed, priced or escalated before commencement. | TBC | Not Started | Critical | Tier 2 - Commercial Review | Commercial Manager | Estimator; Legal | Internal / Client | Before site start | Weekly |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0002_OpenQualifications | CM | Stage 3 - Pre-Con
PC-O-008 | Mobilisation & Delivery Handover | Pre-construction completion | Unplaced Orders and Exposure Report | Shows uncommitted scope, budget, forecast, procurement date and programme exposure. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | QS | Commercial Manager; Planner | Board / Internal | Before site start | Weekly |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.40 Outstanding Commercial Exposure | EXP | PROJ-MCR-CM-EXP-0002_UnplacedOrdersExposureReport | PCC | Stage 3 - Pre-Con
PC-O-009 | Mobilisation & Delivery Handover | Pre-construction completion | Advance Orders / Deposits / Free-Issue Materials Schedule | Tracks early commitments, security, ownership, delivery and budget treatment. | TBC | Not Started | High | Tier 1 - Board / Client Visibility | QS | Procurement; Finance | Board / Internal | Pre-start | Weekly |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.40 Outstanding Commercial Exposure | EXP | PROJ-MCR-CM-EXP-0003_AdvanceOrders | PCC | Stage 3 - Pre-Con
PC-O-010 | Mobilisation & Delivery Handover | Pre-construction completion | Opening Forecast and Cashflow Approval | Formal approval of starting margin, forecast cost, cash and risk position. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Director | Commercial Manager; Finance | Board / Internal | Before site start | Once |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0003_OpeningForecastCashflowApproval | CM | Stage 3 - Pre-Con
PC-O-011 | Mobilisation & Delivery Handover | Pre-construction completion | Pre-Start Commercial Briefing Record | Evidence that delivery staff understand payment, notices, change, records, scope and authority rules. | TBC | Not Started | High | Tier 3 - Internal Control | Commercial Manager | Project Manager; QS | Internal | Before site start | Once / new staff |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0004_PreStartCommercialBriefingRecord | CM | Stage 3 - Pre-Con
PC-O-012 | Mobilisation & Delivery Handover | Pre-construction completion | Final Account Strategy Note | Sets recoveries, evidence needs, negotiation position and close-out priorities from day one. | TBC | Not Started | High | Tier 2 - Commercial Review | Commercial Manager | QS; Legal | Internal | Before site start | Quarterly update |  |  |  | Source Word register |  | 12.0 Mobilisation & Pre-Start Handover | 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0003_FinalAccountStrategyNote | CM | Stage 3 - Pre-Con
PC-O-013 | Mobilisation & Delivery Handover | Pre-construction completion | Handover Deliverables and Warranty Procurement Matrix | Ensures O&M, commissioning, training, certificates and warranties are included in orders. | TBC | Not Started | High | Tier 2 - Commercial Review | Design Manager | QS; Document Controller | Internal | Before site start | Monthly |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.20 Estimating-to-Delivery Handover | HND | PROJ-MCR-CM-HND-0004_HandoverDeliverablesWarrantyProcurementMatrix | CM | Stage 3 - Pre-Con
PC-O-014 | Mobilisation & Delivery Handover | Pre-construction completion | Commercial Pack Approval and Issue Record | Records reviewer, approval date, revision and controlled issue of the pre-construction pack. | TBC | Not Started | Critical | Tier 1 - Board / Client Visibility | Commercial Director | Commercial Manager; Document Controller | Board / Internal | Pre-start Stage | Once / revision |  |  |  | Expanded recommendation |  | 12.0 Mobilisation & Pre-Start Handover | 12.10 Commercial Readiness | RDY | PROJ-MCR-CM-RDY-0005_CommercialPackApprovalIssueRecord | CM | Stage 3 - Pre-Con

## Folder Coverage
Folder Coverage — items per Level 1 folder
L1 Code | Level 1 Folder | Items
0.0 | Admin & Document Control | 19
1.0 | Tender & Bid Baseline | 11
2.0 | Contract Formation | 14
3.0 | Scope, Design & Cost Planning | 33
4.0 | Procurement & Package Award | 28
5.0 | Subcontract Formation | 9
6.0 | Cashflow, Payment & Tax | 5
7.0 | Risk, Governance & Entitlement | 12
8.0 | Programme & Delay Commercials | 5
9.0 | Insurance, Security & Warranties | 9
10.0 | Property, Statutory & Third Parties | 12
11.0 | Commercial Reporting & Controls | 4
12.0 | Mobilisation & Pre-Start Handover | 14
| TOTAL | 175

## Dashboard
Pre-Construction Commercial Pack - Control Dashboard
Extensive master checklist. Set “Include in Pack?” to Yes / No after project review; do not treat every item as automatically applicable.
Control | Count |  | Progress | Result | Stage | Documents
Total documents | 175 |  | Applicability reviewed | 0% | Stage 1 - Bid | 11
Included - Yes | 0 |  | Completed | 0 | Stage 2 - Award | 19
Excluded - No | 0 |  | In progress | 0 | Stage 3 - Pre-Con | 145
Still TBC | 175 |  | Overdue open items | 0 | TOTAL | 175
Critical priority | 91 |  | Source items retained | 72
Workstream | Total | Include Yes | Still TBC
Tender & Bid Baseline | 11 | 0 | 11
Contract Formation | 14 | 0 | 14
Scope & Design Cost Control | 13 | 0 | 13
Cost Planning & Budget | 20 | 0 | 20
Procurement Strategy | 15 | 0 | 15
Tendering & Package Award | 13 | 0 | 13
Subcontract Formation | 10 | 0 | 10
Cashflow, Payment & Tax | 7 | 0 | 7
Risk, Opportunity & Governance | 9 | 0 | 9
Change, Claims & Entitlement | 9 | 0 | 9
Programme & Delay Commercials | 6 | 0 | 6
Insurance, Security & Warranties | 9 | 0 | 9
Property, Statutory & Third Parties | 12 | 0 | 12
Reporting & Project Controls | 13 | 0 | 13
Mobilisation & Delivery Handover | 14 | 0 | 14
Workstream | Stage 1 - Bid | Stage 2 - Award | Stage 3 - Pre-Con | Total | DOCUMENTS BY WORKSTREAM AND STAGE
Tender & Bid Baseline | 11 | 0 | 0 | 11
Contract Formation | 0 | 14 | 0 | 14
Scope & Design Cost Control | 0 | 0 | 13 | 13
Cost Planning & Budget | 0 | 2 | 18 | 20
Procurement Strategy | 0 | 0 | 15 | 15
Tendering & Package Award | 0 | 0 | 13 | 13
Subcontract Formation | 0 | 0 | 10 | 10
Cashflow, Payment & Tax | 0 | 2 | 5 | 7
Risk, Opportunity & Governance | 0 | 0 | 9 | 9
Change, Claims & Entitlement | 0 | 0 | 9 | 9
Programme & Delay Commercials | 0 | 0 | 6 | 6
Insurance, Security & Warranties | 0 | 0 | 9 | 9
Property, Statutory & Third Parties | 0 | 1 | 11 | 12
Reporting & Project Controls | 0 | 0 | 13 | 13
Mobilisation & Delivery Handover | 0 | 0 | 14 | 14

## Guidance & Lookups
How to Use This Register | [6 empty] | Owner Lookup
Commercial Director
Field | Required use | Do not do | Control owner | Pre-start minimum Stage | Why | Owner | Commercial Manager
Include in Pack? | Set Yes, No or TBC after contract and project review. | Do not leave Critical items at TBC when mobilising. | Commercial Manager | Executed contract or controlled LOI | No work beyond authorised scope/value. | Commercial Director | QS
Status | Record progress of included items. | Do not use Complete unless approved evidence is filed. | Document owner | Tender-to-contract reconciliation | No lost qualification or silent scope movement. | Commercial Manager | Estimator
Priority | Use Critical for controls whose absence creates immediate entitlement, cash or commitment exposure. | Do not downgrade to hide overdue work. | Commercial Manager | Opening CVR and cashflow approved | Margin and funding baseline agreed. | Commercial Manager / Finance | Procurement
Due Date | Link to the actual contract, procurement or mobilisation Stage. | Do not use arbitrary dates disconnected from programme. | Document owner | Risk and entitlement registers live | Exposure and recovery actions allocated. | Commercial Manager | Planner
Storage Link / File Ref | Enter controlled CDE path, SharePoint link or document number. | Do not rely on personal inboxes or local drives. | Document Controller | Payment and notice calendars live | No missed statutory or contractual deadlines. | QS | Project Manager
Notes / Action | Record exclusion rationale, missing inputs, decision required and next action. | Do not write “N/A” without a reason. | Document owner | Procurement and long-lead schedules aligned | Packages can meet programme dates. | Planner / QS | Project Director
Source / Basis | Shows whether the item came from the supplied registers or was added as an expanded recommendation. | Do not treat source status as proof of applicability. | Commercial Manager | Critical orders executed | No uninsured or unauthorised mobilisation. | Commercial Manager | Design Manager
|  |  |  | Scope and design interfaces allocated | No package gaps or duplicated allowances. | Design Manager / QS | Document Controller
|  |  |  | Commercial handover complete | Delivery team understands the priced position. | Commercial Manager | Finance
Governance Tier | Primary audience | Purpose | Typical content |  |  |  | Legal
Tier 1 - Board / Client Visibility | Board, client, funder or executive approval | Material financial exposure, approvals and external governance. | Contract, cost reports, risk, cash, major awards, security. |  |  |  | H&S
Tier 2 - Commercial Review | Commercial manager, monitoring surveyor, project leadership | Detailed review evidence supporting value, risk and entitlement. | Cost plans, tender analysis, scope comparison, change and forecasts. |  |  |  | MEP Manager
Tier 3 - Internal Control | Meridian project and support teams | Internal control, audit trail and day-to-day administration. | Trackers, calendars, templates, filing and authority controls. |  |  |  | Civils Manager
Environmental Lead
Sustainability Lead
BIM Manager
Temporary Works Coordinator