## Read Me
Construction Team — Pre-Construction Readiness Register
Project | PROJ
What this is | The construction team's pre-construction readiness deliverables, in the same 9-tab structure and house style as the Commercial and Design registers so the three form one PCSA document-control pack.
IMPORTANT — status of this list | Unlike the Commercial and Design registers (which reformat real source content), this register is a GENERATED standard construction document set — no construction-team source list was provided. Treat it as a starting template for the construction/operations team to review, correct and own before issue.
Spine | Same three procurement gates as the other registers: Stage 1 - Bid & Tender, Stage 2 - Contract Award, Stage 3 - Pre-Construction. This is a PRE-CONSTRUCTION readiness register, not a build-phase document register.
Scope note | Covers the production / site / logistics / temporary-works / H&S / programme domain — deliberately distinct from the Commercial (money/contract) and Design (drawings/specs) registers. If you need the build-phase set (RAMS per activity, ITPs, permits, progress records, snagging, O&M/handover) phased Mobilisation -> Construction -> Completion, that is a separate register.
Sheets | Read Me / Stage 1-3 checklists (views) / Construction Folder Structure / Master Register (single source of truth) / Folder Coverage / Dashboard (live counts) / Guidance & Lookups.
Naming (proposed) | PROJ-CDR-[TYPE]-[####]_[Title]. CDR = Construction Delivery Register; each L2 folder has a unique TYPE. Proposed convention — confirm before issuing.
Input fields | Include in Pack?, Priority, Delivery Status, Target Date, Document Reference, Revision and Comments are controlled input fields (dropdowns where relevant). Delivery Status defaults to Planned; set the rest live.
Owners | Owner / Lead Party uses construction roles (PM, Construction Manager, Planner, TWC, H&S Manager, Quality Manager, Procurement). Confirm the named holders on appointment.

## Stage 1 - Bid & Tender
Stage 1 - Bid & Tender
10 deliverables · Rev P01
Construction team's inputs to the tender/bid — buildability, methodology, logistics and temporary-works/H&S assumptions the bid is built on. Filtered view of the Master Register — edit items there, not here.
Ref | Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party | Delivery Status | TYPE | Proposed File Name | Comments / Key Actions
1.01 | Tender / Outline Construction Programme | Sets the tendered construction sequence, durations and key milestones the bid is priced against. | Meridian Planner | Planned | TPM | PROJ-CDR-TPM-0001_TenderOutlineConstructionP | Baseline for the contract programme at award; keep the logic file.
1.02 | Construction Methodology & Sequencing Statement | Describes how the works will be built, in what order, and the principal construction assumptions. | Meridian Construction Manager | Planned | TPM | PROJ-CDR-TPM-0002_ConstructionMethodologySeq | Aligns with tender programme; flag any assumptions that carry commercial risk.
1.03 | Buildability & Constructability Review | Records buildability input into the tender design and any efficiency / VE opportunities. | Meridian Construction Manager | Planned | TPM | PROJ-CDR-TPM-0003_BuildabilityConstructabili | Feed outputs into the design register VE items.
1.04 | Site Logistics & Access Strategy (Tender) | Establishes site access, compound, storage, deliveries and craneage assumptions for the bid. | Meridian Construction Manager | Planned | SLE | PROJ-CDR-SLE-0001_SiteLogisticsAccessStrateg | Confirm against highways/neighbour constraints.
1.05 | Site Establishment & Preliminaries Basis | Defines the site set-up and preliminaries assumptions priced in the tender. | Meridian / Commercial | Planned | SLE | PROJ-CDR-SLE-0002_SiteEstablishmentPrelimina | Reconcile with the commercial preliminaries budget.
1.06 | Plant, Crane & Hoisting Strategy (Tender) | Sets out the principal plant, crane and material-movement strategy assumed at tender. | Meridian Construction Manager | Planned | SLE | PROJ-CDR-SLE-0003_PlantCraneHoistingStrategy
1.07 | Temporary Works Assumptions & Design Approach | Identifies the temporary works foreseen and the intended design/approval approach. | Temporary Works Coordinator | Planned | TWS | PROJ-CDR-TWS-0001_TemporaryWorksAssumptionsD | Confirm TWC appointment carries into Stage 2.
1.08 | Outline Construction Phase H&S / CDM Approach | Sets the tender-stage construction H&S and CDM approach and principal-contractor duties. | Meridian H&S Manager | Planned | TWS | PROJ-CDR-TWS-0002_OutlineConstructionPhaseHS | Develops into the Construction Phase Plan at award.
1.09 | Key Construction Risks & Mitigation Schedule (Tender) | Captures the principal construction risks priced and how they are to be managed. | Meridian Construction Manager | Planned | CRA | PROJ-CDR-CRA-0001_KeyConstructionRisksMitiga | Cross-check against the commercial risk register.
1.10 | Logistics, Traffic & Neighbour Constraints Assumptions | Records traffic management, working-hours and neighbour constraints assumed in the bid. | Meridian Construction Manager | Planned | CRA | PROJ-CDR-CRA-0002_LogisticsTrafficNeighbourC

## Stage 2 - Contract Award
Stage 2 - Contract Award
12 deliverables · Rev P01
Construction mobilisation and delivery-planning produced on appointment to the PCSA — construction programme, CPP, site setup, temporary works, procurement. Filtered view of the Master Register — edit items there, not here.
Ref | Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party | Delivery Status | TYPE | Proposed File Name | Comments / Key Actions
2.01 | Contract / Baseline Construction Programme | The contract-baselined construction programme against which progress is measured. | Meridian Planner | Planned | CPR | PROJ-CDR-CPR-0001_ContractBaselineConstructi | Baseline and lock; issue under the contract.
2.02 | Construction Phase Plan (CPP) - Draft | The developing CDM construction phase plan for the works. | Meridian H&S Manager | Planned | CPR | PROJ-CDR-CPR-0002_ConstructionPhasePlanCPPDr | Must be adequate before any works start.
2.03 | Mobilisation Plan & Programme | Sequences site set-up, procurement and readiness activities up to start on site. | Meridian Project Manager | Planned | CPR | PROJ-CDR-CPR-0003_MobilisationPlanProgramme
2.04 | Site Establishment Design & Layout | The developed site compound, welfare, access and storage layout design. | Meridian Construction Manager | Planned | SSL | PROJ-CDR-SSL-0001_SiteEstablishmentDesignLay
2.05 | Developed Site Logistics & Traffic Management Plan | Coordinates deliveries, craneage, access and traffic management for the build. | Meridian Construction Manager | Planned | SSL | PROJ-CDR-SSL-0002_DevelopedSiteLogisticsTraf | Liaise with highways/LPA where required.
2.06 | Enabling Works & Utilities Plan | Plans enabling works, diversions and temporary/permanent utility connections. | Meridian / Utility Designers | Planned | SSL | PROJ-CDR-SSL-0003_EnablingWorksUtilitiesPlan | Depends on utility capacities from the design register.
2.07 | Temporary Works Register & TWC Appointment | Establishes the temporary works register, roles and approval process. | Temporary Works Coordinator | Planned | TWM | PROJ-CDR-TWM-0001_TemporaryWorksRegisterTWCA | No TW to proceed without a design check certificate.
2.08 | Key Package Method Statements (RAMS Framework) | Sets the method-statement/RAMS framework for principal construction packages. | Meridian Construction Manager | Planned | TWM | PROJ-CDR-TWM-0002_KeyPackageMethodStatements
2.09 | Construction Procurement & Package Award Schedule | Schedules construction package procurement and award against the programme need-by dates. | Meridian / Commercial | Planned | CPS | PROJ-CDR-CPS-0001_ConstructionProcurementPac | Align with commercial procurement register.
2.10 | Long-Lead & Enabling Subcontract Orders | Places long-lead and enabling orders early enough to protect the programme. | Meridian / Commercial | Planned | CPS | PROJ-CDR-CPS-0002_LongLeadEnablingSubcontrac
2.11 | Site H&S Management Arrangements | Defines site safety management, supervision and induction arrangements. | Meridian H&S Manager | Planned | SHE | PROJ-CDR-SHE-0001_SiteHSManagementArrangemen
2.12 | Construction Environmental Management Plan (CEMP) | Sets site environmental controls, discharge, noise, dust and waste management. | Meridian H&S / Environmental | Planned | SHE | PROJ-CDR-SHE-0002_ConstructionEnvironmentalM | Check planning conditions for environmental triggers.

## Stage 3 - Pre-Construction
Stage 3 - Pre-Construction
15 deliverables · Rev P01
Construction readiness delivered at pre-con completion — final CPP and programme, quality/ITP framework, temporary-works designs, permits, and the go/no-go readiness report. Filtered view of the Master Register — edit items there, not here.
Ref | Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party | Delivery Status | TYPE | Proposed File Name | Comments / Key Actions
3.01 | Construction Phase Plan (CPP) - Final / Issued | The issued CDM construction phase plan controlling the works. | Meridian H&S Manager | Planned | CFP | PROJ-CDR-CFP-0001_ConstructionPhasePlanCPPFi | Must be issued before start on site.
3.02 | Final Baselined Construction Programme | The final, resourced and baselined construction programme for delivery. | Meridian Planner | Planned | CFP | PROJ-CDR-CFP-0002_FinalBaselinedConstruction
3.03 | Project Quality Management Plan | Defines the quality management system, roles and control points for the build. | Meridian Quality Manager | Planned | QIN | PROJ-CDR-QIN-0001_ProjectQualityManagementPl
3.04 | Inspection & Test Plans (ITP) Framework | Establishes ITPs, hold/witness points and sign-off routes for key trades. | Meridian Quality Manager | Planned | QIN | PROJ-CDR-QIN-0002_InspectionTestPlansITPFram | Populate per package as procured.
3.05 | Materials & Sample Approval Process | Controls product, material and benchmark approval before order/installation. | Meridian Quality Manager | Planned | QIN | PROJ-CDR-QIN-0003_MaterialsSampleApprovalPro | Links to design technical submittal register.
3.06 | Temporary Works Designs & Approved Register | The temporary works designs, checks and approved register for construction. | Temporary Works Coordinator | Planned | TWD | PROJ-CDR-TWD-0001_TemporaryWorksDesignsAppro | No TW loaded without design check certificate.
3.07 | Excavation, Groundworks & Craneage TW Designs | Specific temporary works designs for excavation, groundworks and lifting. | Temporary Works Coordinator | Planned | TWD | PROJ-CDR-TWD-0002_ExcavationGroundworksCrane
3.08 | Permit-to-Work Systems Setup | Establishes permit-to-work controls for high-risk activities. | Meridian H&S Manager | Planned | HSP | PROJ-CDR-HSP-0001_PermitToWorkSystemsSetup
3.09 | Fire & Emergency Plan (Construction) | Sets construction-phase fire, emergency and evacuation arrangements. | Meridian H&S Manager | Planned | HSP | PROJ-CDR-HSP-0002_FireEmergencyPlanConstruct
3.10 | Site Waste Management Plan | Plans waste segregation, disposal and recording for the build. | Meridian H&S / Environmental | Planned | HSP | PROJ-CDR-HSP-0003_SiteWasteManagementPlan
3.11 | Subcontract Orders Placed (Key / Long-Lead) | Confirms key and long-lead subcontract/supply orders are executed. | Meridian / Commercial | Planned | SPS | PROJ-CDR-SPS-0001_SubcontractOrdersPlacedKey | Track against programme need-by dates.
3.12 | Construction Procurement Status & Gap Report | Reports procurement status and any package gaps threatening start on site. | Meridian / Commercial | Planned | SPS | PROJ-CDR-SPS-0002_ConstructionProcurementSta
3.13 | Testing, Commissioning & Handover Strategy (Construction) | Defines the construction-side commissioning, testing and handover approach. | Meridian / Commissioning | Planned | CHR | PROJ-CDR-CHR-0001_TestingCommissioningHandov | Coordinate with design handover strategy.
3.14 | O&M / As-Built Information Requirements Setup | Sets the O&M, as-built and handover information requirements from the outset. | Meridian / Design Team | Planned | CHR | PROJ-CDR-CHR-0002_OMAsBuiltInformationRequir
3.15 | Pre-Construction Readiness & Go/No-Go Report | Confirms all pre-start conditions are met and authorises start on site. | Meridian Project Manager | Planned | CHR | PROJ-CDR-CHR-0003_PreConstructionReadinessGo | The pre-start gate — nothing starts until this is signed off.

## Construction Folder Structure
Construction Delivery — Folder Structure (Proposed)
L1 = procurement stage; L2 = deliverable grouping. Aligned to the 3-stage spine. Confirm before adopting.
L1 Code | Level 1 Folder (Stage) | L2 Code | Level 2 Folder | TYPE | Lead Owner | Items
1.0 | Stage 1 - Bid & Tender
|  | 1.10 | Tender Programme & Methodology | TPM | Meridian Construction Manager | 3
|  | 1.20 | Site Logistics & Establishment (Tender) | SLE | Meridian Construction Manager | 3
|  | 1.30 | Temporary Works & Safety (Tender) | TWS | Temporary Works Coordinator | 2
|  | 1.40 | Construction Risk & Assumptions | CRA | Meridian Construction Manager | 2
2.0 | Stage 2 - Contract Award
|  | 2.10 | Construction Programme & Planning | CPR | Meridian Planner | 3
|  | 2.20 | Site Setup & Logistics | SSL | Meridian Construction Manager | 3
|  | 2.30 | Temporary Works & Methodology | TWM | Temporary Works Coordinator | 2
|  | 2.40 | Construction Procurement & Subcontract | CPS | Meridian | 2
|  | 2.50 | Site H&S & Environmental | SHE | Meridian H&S Manager | 2
3.0 | Stage 3 - Pre-Construction
|  | 3.10 | Construction Phase Plan & Programme (Final) | CFP | Meridian H&S Manager | 2
|  | 3.20 | Quality & Inspection | QIN | Meridian Quality Manager | 3
|  | 3.30 | Temporary Works (Design & Approval) | TWD | Temporary Works Coordinator | 2
|  | 3.40 | Health, Safety & Permits | HSP | Meridian H&S Manager | 3
|  | 3.50 | Subcontract & Procurement (Complete) | SPS | Meridian | 2
|  | 3.60 | Commissioning & Handover Readiness | CHR | Meridian | 3

## Master Register
PROJ Canalside Regency — Construction Pre-Construction Master Register
Ref | Stage | Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party | Include in Pack? | Priority | Delivery Status | Target Date | Document Reference | Revision | Comments / Key Actions | Level 1 Folder | Level 2 Folder | TYPE | Proposed File Name
1.01 | Stage 1 - Bid & Tender | Tender / Outline Construction Programme | Sets the tendered construction sequence, durations and key milestones the bid is priced against. | Meridian Planner | TBC |  | Planned |  |  |  | Baseline for the contract programme at award; keep the logic file. | Stage 1 - Bid & Tender | 1.10 Tender Programme & Methodology | TPM | PROJ-CDR-TPM-0001_TenderOutlineConstructionP
1.02 | Stage 1 - Bid & Tender | Construction Methodology & Sequencing Statement | Describes how the works will be built, in what order, and the principal construction assumptions. | Meridian Construction Manager | TBC |  | Planned |  |  |  | Aligns with tender programme; flag any assumptions that carry commercial risk. | Stage 1 - Bid & Tender | 1.10 Tender Programme & Methodology | TPM | PROJ-CDR-TPM-0002_ConstructionMethodologySeq
1.03 | Stage 1 - Bid & Tender | Buildability & Constructability Review | Records buildability input into the tender design and any efficiency / VE opportunities. | Meridian Construction Manager | TBC |  | Planned |  |  |  | Feed outputs into the design register VE items. | Stage 1 - Bid & Tender | 1.10 Tender Programme & Methodology | TPM | PROJ-CDR-TPM-0003_BuildabilityConstructabili
1.04 | Stage 1 - Bid & Tender | Site Logistics & Access Strategy (Tender) | Establishes site access, compound, storage, deliveries and craneage assumptions for the bid. | Meridian Construction Manager | TBC |  | Planned |  |  |  | Confirm against highways/neighbour constraints. | Stage 1 - Bid & Tender | 1.20 Site Logistics & Establishment (Tender) | SLE | PROJ-CDR-SLE-0001_SiteLogisticsAccessStrateg
1.05 | Stage 1 - Bid & Tender | Site Establishment & Preliminaries Basis | Defines the site set-up and preliminaries assumptions priced in the tender. | Meridian / Commercial | TBC |  | Planned |  |  |  | Reconcile with the commercial preliminaries budget. | Stage 1 - Bid & Tender | 1.20 Site Logistics & Establishment (Tender) | SLE | PROJ-CDR-SLE-0002_SiteEstablishmentPrelimina
1.06 | Stage 1 - Bid & Tender | Plant, Crane & Hoisting Strategy (Tender) | Sets out the principal plant, crane and material-movement strategy assumed at tender. | Meridian Construction Manager | TBC |  | Planned |  |  |  |  | Stage 1 - Bid & Tender | 1.20 Site Logistics & Establishment (Tender) | SLE | PROJ-CDR-SLE-0003_PlantCraneHoistingStrategy
1.07 | Stage 1 - Bid & Tender | Temporary Works Assumptions & Design Approach | Identifies the temporary works foreseen and the intended design/approval approach. | Temporary Works Coordinator | TBC |  | Planned |  |  |  | Confirm TWC appointment carries into Stage 2. | Stage 1 - Bid & Tender | 1.30 Temporary Works & Safety (Tender) | TWS | PROJ-CDR-TWS-0001_TemporaryWorksAssumptionsD
1.08 | Stage 1 - Bid & Tender | Outline Construction Phase H&S / CDM Approach | Sets the tender-stage construction H&S and CDM approach and principal-contractor duties. | Meridian H&S Manager | TBC |  | Planned |  |  |  | Develops into the Construction Phase Plan at award. | Stage 1 - Bid & Tender | 1.30 Temporary Works & Safety (Tender) | TWS | PROJ-CDR-TWS-0002_OutlineConstructionPhaseHS
1.09 | Stage 1 - Bid & Tender | Key Construction Risks & Mitigation Schedule (Tender) | Captures the principal construction risks priced and how they are to be managed. | Meridian Construction Manager | TBC |  | Planned |  |  |  | Cross-check against the commercial risk register. | Stage 1 - Bid & Tender | 1.40 Construction Risk & Assumptions | CRA | PROJ-CDR-CRA-0001_KeyConstructionRisksMitiga
1.10 | Stage 1 - Bid & Tender | Logistics, Traffic & Neighbour Constraints Assumptions | Records traffic management, working-hours and neighbour constraints assumed in the bid. | Meridian Construction Manager | TBC |  | Planned |  |  |  |  | Stage 1 - Bid & Tender | 1.40 Construction Risk & Assumptions | CRA | PROJ-CDR-CRA-0002_LogisticsTrafficNeighbourC
2.01 | Stage 2 - Contract Award | Contract / Baseline Construction Programme | The contract-baselined construction programme against which progress is measured. | Meridian Planner | TBC |  | Planned |  |  |  | Baseline and lock; issue under the contract. | Stage 2 - Contract Award | 2.10 Construction Programme & Planning | CPR | PROJ-CDR-CPR-0001_ContractBaselineConstructi
2.02 | Stage 2 - Contract Award | Construction Phase Plan (CPP) - Draft | The developing CDM construction phase plan for the works. | Meridian H&S Manager | TBC |  | Planned |  |  |  | Must be adequate before any works start. | Stage 2 - Contract Award | 2.10 Construction Programme & Planning | CPR | PROJ-CDR-CPR-0002_ConstructionPhasePlanCPPDr
2.03 | Stage 2 - Contract Award | Mobilisation Plan & Programme | Sequences site set-up, procurement and readiness activities up to start on site. | Meridian Project Manager | TBC |  | Planned |  |  |  |  | Stage 2 - Contract Award | 2.10 Construction Programme & Planning | CPR | PROJ-CDR-CPR-0003_MobilisationPlanProgramme
2.04 | Stage 2 - Contract Award | Site Establishment Design & Layout | The developed site compound, welfare, access and storage layout design. | Meridian Construction Manager | TBC |  | Planned |  |  |  |  | Stage 2 - Contract Award | 2.20 Site Setup & Logistics | SSL | PROJ-CDR-SSL-0001_SiteEstablishmentDesignLay
2.05 | Stage 2 - Contract Award | Developed Site Logistics & Traffic Management Plan | Coordinates deliveries, craneage, access and traffic management for the build. | Meridian Construction Manager | TBC |  | Planned |  |  |  | Liaise with highways/LPA where required. | Stage 2 - Contract Award | 2.20 Site Setup & Logistics | SSL | PROJ-CDR-SSL-0002_DevelopedSiteLogisticsTraf
2.06 | Stage 2 - Contract Award | Enabling Works & Utilities Plan | Plans enabling works, diversions and temporary/permanent utility connections. | Meridian / Utility Designers | TBC |  | Planned |  |  |  | Depends on utility capacities from the design register. | Stage 2 - Contract Award | 2.20 Site Setup & Logistics | SSL | PROJ-CDR-SSL-0003_EnablingWorksUtilitiesPlan
2.07 | Stage 2 - Contract Award | Temporary Works Register & TWC Appointment | Establishes the temporary works register, roles and approval process. | Temporary Works Coordinator | TBC |  | Planned |  |  |  | No TW to proceed without a design check certificate. | Stage 2 - Contract Award | 2.30 Temporary Works & Methodology | TWM | PROJ-CDR-TWM-0001_TemporaryWorksRegisterTWCA
2.08 | Stage 2 - Contract Award | Key Package Method Statements (RAMS Framework) | Sets the method-statement/RAMS framework for principal construction packages. | Meridian Construction Manager | TBC |  | Planned |  |  |  |  | Stage 2 - Contract Award | 2.30 Temporary Works & Methodology | TWM | PROJ-CDR-TWM-0002_KeyPackageMethodStatements
2.09 | Stage 2 - Contract Award | Construction Procurement & Package Award Schedule | Schedules construction package procurement and award against the programme need-by dates. | Meridian / Commercial | TBC |  | Planned |  |  |  | Align with commercial procurement register. | Stage 2 - Contract Award | 2.40 Construction Procurement & Subcontract | CPS | PROJ-CDR-CPS-0001_ConstructionProcurementPac
2.10 | Stage 2 - Contract Award | Long-Lead & Enabling Subcontract Orders | Places long-lead and enabling orders early enough to protect the programme. | Meridian / Commercial | TBC |  | Planned |  |  |  |  | Stage 2 - Contract Award | 2.40 Construction Procurement & Subcontract | CPS | PROJ-CDR-CPS-0002_LongLeadEnablingSubcontrac
2.11 | Stage 2 - Contract Award | Site H&S Management Arrangements | Defines site safety management, supervision and induction arrangements. | Meridian H&S Manager | TBC |  | Planned |  |  |  |  | Stage 2 - Contract Award | 2.50 Site H&S & Environmental | SHE | PROJ-CDR-SHE-0001_SiteHSManagementArrangemen
2.12 | Stage 2 - Contract Award | Construction Environmental Management Plan (CEMP) | Sets site environmental controls, discharge, noise, dust and waste management. | Meridian H&S / Environmental | TBC |  | Planned |  |  |  | Check planning conditions for environmental triggers. | Stage 2 - Contract Award | 2.50 Site H&S & Environmental | SHE | PROJ-CDR-SHE-0002_ConstructionEnvironmentalM
3.01 | Stage 3 - Pre-Construction | Construction Phase Plan (CPP) - Final / Issued | The issued CDM construction phase plan controlling the works. | Meridian H&S Manager | TBC |  | Planned |  |  |  | Must be issued before start on site. | Stage 3 - Pre-Construction | 3.10 Construction Phase Plan & Programme (Final) | CFP | PROJ-CDR-CFP-0001_ConstructionPhasePlanCPPFi
3.02 | Stage 3 - Pre-Construction | Final Baselined Construction Programme | The final, resourced and baselined construction programme for delivery. | Meridian Planner | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.10 Construction Phase Plan & Programme (Final) | CFP | PROJ-CDR-CFP-0002_FinalBaselinedConstruction
3.03 | Stage 3 - Pre-Construction | Project Quality Management Plan | Defines the quality management system, roles and control points for the build. | Meridian Quality Manager | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.20 Quality & Inspection | QIN | PROJ-CDR-QIN-0001_ProjectQualityManagementPl
3.04 | Stage 3 - Pre-Construction | Inspection & Test Plans (ITP) Framework | Establishes ITPs, hold/witness points and sign-off routes for key trades. | Meridian Quality Manager | TBC |  | Planned |  |  |  | Populate per package as procured. | Stage 3 - Pre-Construction | 3.20 Quality & Inspection | QIN | PROJ-CDR-QIN-0002_InspectionTestPlansITPFram
3.05 | Stage 3 - Pre-Construction | Materials & Sample Approval Process | Controls product, material and benchmark approval before order/installation. | Meridian Quality Manager | TBC |  | Planned |  |  |  | Links to design technical submittal register. | Stage 3 - Pre-Construction | 3.20 Quality & Inspection | QIN | PROJ-CDR-QIN-0003_MaterialsSampleApprovalPro
3.06 | Stage 3 - Pre-Construction | Temporary Works Designs & Approved Register | The temporary works designs, checks and approved register for construction. | Temporary Works Coordinator | TBC |  | Planned |  |  |  | No TW loaded without design check certificate. | Stage 3 - Pre-Construction | 3.30 Temporary Works (Design & Approval) | TWD | PROJ-CDR-TWD-0001_TemporaryWorksDesignsAppro
3.07 | Stage 3 - Pre-Construction | Excavation, Groundworks & Craneage TW Designs | Specific temporary works designs for excavation, groundworks and lifting. | Temporary Works Coordinator | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.30 Temporary Works (Design & Approval) | TWD | PROJ-CDR-TWD-0002_ExcavationGroundworksCrane
3.08 | Stage 3 - Pre-Construction | Permit-to-Work Systems Setup | Establishes permit-to-work controls for high-risk activities. | Meridian H&S Manager | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.40 Health, Safety & Permits | HSP | PROJ-CDR-HSP-0001_PermitToWorkSystemsSetup
3.09 | Stage 3 - Pre-Construction | Fire & Emergency Plan (Construction) | Sets construction-phase fire, emergency and evacuation arrangements. | Meridian H&S Manager | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.40 Health, Safety & Permits | HSP | PROJ-CDR-HSP-0002_FireEmergencyPlanConstruct
3.10 | Stage 3 - Pre-Construction | Site Waste Management Plan | Plans waste segregation, disposal and recording for the build. | Meridian H&S / Environmental | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.40 Health, Safety & Permits | HSP | PROJ-CDR-HSP-0003_SiteWasteManagementPlan
3.11 | Stage 3 - Pre-Construction | Subcontract Orders Placed (Key / Long-Lead) | Confirms key and long-lead subcontract/supply orders are executed. | Meridian / Commercial | TBC |  | Planned |  |  |  | Track against programme need-by dates. | Stage 3 - Pre-Construction | 3.50 Subcontract & Procurement (Complete) | SPS | PROJ-CDR-SPS-0001_SubcontractOrdersPlacedKey
3.12 | Stage 3 - Pre-Construction | Construction Procurement Status & Gap Report | Reports procurement status and any package gaps threatening start on site. | Meridian / Commercial | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.50 Subcontract & Procurement (Complete) | SPS | PROJ-CDR-SPS-0002_ConstructionProcurementSta
3.13 | Stage 3 - Pre-Construction | Testing, Commissioning & Handover Strategy (Construction) | Defines the construction-side commissioning, testing and handover approach. | Meridian / Commissioning | TBC |  | Planned |  |  |  | Coordinate with design handover strategy. | Stage 3 - Pre-Construction | 3.60 Commissioning & Handover Readiness | CHR | PROJ-CDR-CHR-0001_TestingCommissioningHandov
3.14 | Stage 3 - Pre-Construction | O&M / As-Built Information Requirements Setup | Sets the O&M, as-built and handover information requirements from the outset. | Meridian / Design Team | TBC |  | Planned |  |  |  |  | Stage 3 - Pre-Construction | 3.60 Commissioning & Handover Readiness | CHR | PROJ-CDR-CHR-0002_OMAsBuiltInformationRequir
3.15 | Stage 3 - Pre-Construction | Pre-Construction Readiness & Go/No-Go Report | Confirms all pre-start conditions are met and authorises start on site. | Meridian Project Manager | TBC |  | Planned |  |  |  | The pre-start gate — nothing starts until this is signed off. | Stage 3 - Pre-Construction | 3.60 Commissioning & Handover Readiness | CHR | PROJ-CDR-CHR-0003_PreConstructionReadinessGo

## Folder Coverage
Folder Coverage — items per stage
L1 Code | Level 1 Folder (Stage) | Items
1.0 | Stage 1 - Bid & Tender | 10
2.0 | Stage 2 - Contract Award | 12
3.0 | Stage 3 - Pre-Construction | 15
| TOTAL | 37

## Dashboard
PROJ Construction Pre-Construction — Dashboard
Live counts off the Master Register. Set Include / Priority / Delivery Status / Target Date there and these update.
Control | Count | Delivery Status | Count
Total deliverables | 37 | Planned | 37
Included - Yes | 0 | In development | 0
Excluded - No | 0 | Submitted / review | 0
Still TBC | 37 | Complete | 0
Critical priority | 0 | Percent complete | 0%
Deliverables by owner / lead party |  |  |  | Deliverables by stage
Owner / Lead Party | Documents |  |  | Stage | Documents
Meridian / Commercial | 5 |  |  | Stage 1 - Bid & Tender | 10
Meridian / Commissioning | 1 |  |  | Stage 2 - Contract Award | 12
Meridian / Design Team | 1 |  |  | Stage 3 - Pre-Construction | 15
Meridian / Utility Designers | 1 |  |  | TOTAL | 37
Meridian Construction Manager | 9
Meridian H&S / Environmental | 2
Meridian H&S Manager | 6
Meridian Planner | 3
Meridian Project Manager | 2
Meridian Quality Manager | 3
Temporary Works Coordinator | 4

## Guidance & Lookups
How to Use This Register
Field | Required use | Do not do | Owner / Lead Party Lookup | Values
Stage | Set by gate: 1 Bid & Tender / 2 Contract Award / 3 Pre-Construction. | Do not leave a deliverable unstaged. | Meridian / Commercial | Yes
Include in Pack? | Set Yes / No / TBC once applicability is confirmed. | Do not leave items at TBC once scope is fixed. | Meridian / Commissioning | No
Delivery Status | Planned / In Development / Submitted-Review / Complete against actual status. | Do not mark Complete before formal issue/acceptance. | Meridian / Design Team | TBC
Priority | Critical / High / Medium by construction risk and programme need-by. | Do not invent criticality; tie it to the programme. | Meridian / Utility Designers | Critical
Owner / Lead Party | Construction roles — confirm the named holders on appointment. | Do not leave safety-critical items (CPP, TW) unassigned. | Meridian Construction Manager | High
Target Date | Link to the mobilisation / construction programme need-by date. | Do not use arbitrary dates disconnected from programme. | Meridian H&S / Environmental | Medium
Content status | This is a generated standard set — review and adjust for PROJ. | Do not issue as the construction team's register without their sign-off. | Meridian H&S Manager | Planned
|  |  | Meridian Planner | In Development
|  |  | Meridian Project Manager | Submitted / Review
|  |  | Meridian Quality Manager | Complete
Temporary Works Coordinator