## Read Me
Pre-Construction Document Delivery Register
Project | PROJ
What this is | Controlled index of all 74 pre-construction design and information deliverables, in the same structure and house style as the Pre-Construction Commercial Register so the two form one document-control pack.
Spine | Divided into three procurement gates matching the commercial register: Stage 1 - Bid & Tender, Stage 2 - Contract Award, Stage 3 - Pre-Construction. The earlier A-E lifecycle sections have been removed.
Stage 1 - Bid & Tender | Documents submitted or required as part of the tender/bid to secure the project. NOTE: this stage spans both Meridian's own tender submissions and the client-issued tender information the bid is priced against (much of it Client-owned). Filter on the Owner column if you need only Meridian submissions.
Stage 2 - Contract Award | Documents submitted once the contract is awarded and Meridian is appointed to undertake the PCSA — the pre-con execution and delivery-control set (PEP, RACI, WBS, design programme, procurement/long-lead, technical-submission schedule). Deliberately lean: at appointment you issue how you'll run pre-con, not the design itself.
Stage 3 - Pre-Construction | Documents delivered on completion of pre-con — coordinated design, IFC technical packages, building-control compliance, procurement/work packages, final contract documents, commissioning and readiness.
Sheets | Read Me / Stage 1-3 checklists (views) / Design Folder Structure / Master Register (single source of truth, all 74) / Folder Coverage / Dashboard (live counts) / Guidance & Lookups.
Naming (proposed) | PROJ-DDR-[TYPE]-[####]_[Title]. DDR = Design Delivery Register; each L2 folder has a unique TYPE. Proposed convention — confirm before issuing. Meridian-commercial (MCR-CM) codes are deliberately NOT used, as most items are Client/design-team owned.
Input fields | Include in Pack?, Status, Priority, Due Date, Contributors, Storage Link and Notes are controlled input fields (dropdowns where relevant) — blank/defaulted, to be completed live. Not pre-populated with assumed values.
Judgment calls | Stage assignment on boundary items is a call, not a fact. Watch: 3.02 planning-conditions tracker (S1 as baseline vs S3 discharge), 3.14/3.18/3.19 final ER & design-responsibility (placed S3 as contract-completion docs), 4.03 technical-submission schedule (S2 as a control). Move any of these in the Master Register and every view/count updates. Ref numbers (0.01-4.21) are the design team's own — preserved, do not overwrite.

## Stage 1 - Bid & Tender
Stage 1 - Bid & Tender
20 deliverables · Rev P01
Documents submitted or required as part of the tender/bid process to secure the project. Spans both Meridian's tender submissions AND the client-issued tender information the bid is priced against. Filtered view of the Master Register — edit items there, not here.
Ref | Pre-Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party | Folder (L2) | TYPE | Proposed File Name
0.01 | Development Business Case and Development Appraisal | Confirms the commercial case, development value and delivery assumptions. | Client | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0001_DevelopmentBusinessCaseAndDe
0.02 | Client Strategic Brief | Defines Client's required project outcomes and success criteria. | Client | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0002_ClientStrategicBrief
0.03 | Site Acquisition and Due Diligence Summary | Consolidates material site, title and development constraints. | Client | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0003_SiteAcquisitionAndDueDiligen
0.04 | Feasibility and Development Options Appraisal | Records the options considered and why the approved development solution was selected. | Client | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0004_FeasibilityAndDevelopmentOpt
0.05 | Planning and Development Capacity Appraisal | Records the planning policy and capacity basis preceding the approved permission. | Client | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0005_PlanningAndDevelopmentCapaci
0.06 | Initial Development Programme | Sets the overall development, approvals, procurement and construction milestones. | Client | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0007_InitialDevelopmentProgramme
0.07 | Development Risk, Abnormals and Procurement Strategy | Combines the principal development risks with the intended procurement and contract route. | Client | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0008_DevelopmentRiskAbnormalsAndP
1.01 | Developed Project Brief | Translates Client's objectives into coordinated, measurable project requirements. | Client | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0001_DevelopedProjectBrief
1.02 | Development Specification and Quality Brief | Defines the intended development-wide quality and performance standard. | Client | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0002_DevelopmentSpecificationAndQ
1.03 | Accommodation, Apartment Type and Area Schedule | Controls the approved unit mix and project area data. | Client | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0003_AccommodationApartmentTypeAn
1.09 | Survey Requirements and Existing Information Register | Records required surveys and the status/reliability of existing information. | Client | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0001_SurveyRequirementsAndExistin
1.10 | Planning and Statutory Approval Information Register | Creates the controlled index of the approved planning and statutory information. | Client | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0002_PlanningAndStatutoryApproval
1.11 | Building Control Route and Transitional Regulations Record | Records why the project proceeds under the confirmed previous/transitional regulations route. | Client | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0003_BuildingControlRouteAndTrans
1.12 | Utilities, Sustainability, Energy and EPC Brief | Defines utility capacity, infrastructure and performance requirements. | Client | 1.40 Utilities & Sustainability Brief | UTB | PROJ-DDR-UTB-0001_UtilitiesSustainabilityEnerg
1.13 | Pre-Construction Information and CDM Design Risk Register | Provides existing safety information and records significant design risks. | Client / CDM Principal Designer | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0004_PreConstructionInformationAn
1.14 | Outline Employer's Requirements | Establishes the structure and content of Client's contractual requirements. | Client | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0004_OutlineEmployerSRequirements
2.02 | Planning Application and Supporting Documents Register | Indexes the historic application that achieved planning permission. | Client | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0005_PlanningApplicationAndSuppor
2.05 | MEP Concept and Heating, Cooling and Ventilation Options Appraisal | Defines the building-services strategy and records the system-selection decision. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0004_MEPConceptAndHeatingCoolingA
3.01 | Planning Decision Notice and Approved Drawing/Document Register | Establishes the definitive planning-approved baseline. | Client | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0006_PlanningDecisionNoticeAndApp
3.02 | Planning Conditions, Section 106 and CIL Tracker | Controls every planning condition and obligation by trigger date. | Client | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0007_PlanningConditionsSection106

## Stage 2 - Contract Award
Stage 2 - Contract Award
19 deliverables · Rev P01
Documents submitted once the contract is awarded and Meridian is appointed to undertake the PCSA — the pre-construction execution and delivery-control set. Filtered view of the Master Register — edit items there, not here.
Ref | Pre-Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party | Folder (L2) | TYPE | Proposed File Name
1.04 | Project Execution Plan, Organisation and Appointment Schedule | Defines project governance, reporting, appointments and decision routes. | Client initially / Meridian post-appointment | 2.10 Pre-Con Execution & Governance | PEG | PROJ-DDR-PEG-0001_ProjectExecutionPlanOrganisa
1.05 | Design Responsibility Matrix and RACI | Allocates design, coordination, review and acceptance responsibility. | Client initially / Meridian post-appointment | 2.10 Pre-Con Execution & Governance | PEG | PROJ-DDR-PEG-0002_DesignResponsibilityMatrixAn
1.06 | Work Breakdown Structure and Scope Breakdown | Structures the project by system, trade, package and deliverable. | Client initially / Meridian post-appointment | 2.10 Pre-Con Execution & Governance | PEG | PROJ-DDR-PEG-0003_WorkBreakdownStructureAndSco
1.07 | Design Programme and Information Release Schedule | Baselines design deliverables and approval periods against project need-by dates. | Meridian | 2.20 Design Programme & Procurement | DPP | PROJ-DDR-DPP-0001_DesignProgrammeAndInformatio
1.08 | Design Procurement and Long-Lead Schedule | Links appointments and procurement to required design outputs. | Meridian | 2.20 Design Programme & Procurement | DPP | PROJ-DDR-DPP-0002_DesignProcurementAndLongLead
2.01 | Concept Design Report and Concept Drawing Set | Records the coordinated concept response to the Project Brief. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0001_ConceptDesignReportAndConcep
2.03 | Updated Accommodation and Development Area Schedule | Confirms the concept-stage unit and area data. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0002_UpdatedAccommodationAndDevel
2.04 | Structural, Civil and Drainage Concept Strategy | Defines the structural form, foundations, drainage and civil engineering basis. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0003_StructuralCivilAndDrainageCo
2.06 | Outline Fire and Life-Safety Strategy | Defines the concept fire-safety basis for the non-HRB residential building. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0005_OutlineFireAndLifeSafetyStra
2.07 | Energy, SAP, EPC, Overheating and Acoustic Performance Strategy | Combines key performance studies that influence the fabric and MEP design. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0006_EnergySAPEPCOverheatingAndAc
2.08 | Access, External Works, Landscape, Parking, Refuse and Security Strategy | Coordinates the main site and inclusive-access requirements. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0007_AccessExternalWorksLandscape
2.09 | Utilities, EV Charging, Solar PV and Incoming Services Strategy | Defines capacities, connection routes and energy-infrastructure requirements. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0008_UtilitiesEVChargingSolarPVAn
2.10 | Outline Specification and Updated Development Specification | Defines the concept performance and quality requirements. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0009_OutlineSpecificationAndUpdat
2.11 | Concept Cost, Value Engineering and Funding Technical Pack | Tests the concept against cost and funding requirements. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0010_ConceptCostValueEngineeringA
2.12 | Design Strategy Compliance, Risk and Readiness Report | Records whether the concept is sufficiently complete to proceed. | Client | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0011_DesignStrategyComplianceRisk
3.15 | Statement of Works, Schedule of Works and Tender Scope Documents | Defines the works and tender information at project/package level. | Client | 1.60 Tender Scope & Contractor's Proposals | TEN | PROJ-DDR-TEN-0001_StatementOfWorksScheduleOfWo
3.16 | Tender Contractor's Proposals | Sets out Meridian's tender response to the Employer's Requirements. | Meridian | 1.60 Tender Scope & Contractor's Proposals | TEN | PROJ-DDR-TEN-0002_TenderContractorSProposals
3.17 | ER/CP Compliance, Qualification and Departure Schedule | Reconciles the Contractor's Proposals against every relevant ER requirement. | Meridian | 1.60 Tender Scope & Contractor's Proposals | TEN | PROJ-DDR-TEN-0003_ERCPComplianceQualificationA
4.03 | Master Design Delivery and Technical Submission Schedule | Controls all Technical Design , Design review and approval dates. | Meridian | 2.20 Design Programme & Procurement | DPP | PROJ-DDR-DPP-0003_MasterDesignDeliveryAndTechn

## Stage 3 - Pre-Construction
Stage 3 - Pre-Construction
34 deliverables · Rev P01
Documents delivered on completion of the pre-construction phase — the coordinated and technical information that readies the works for construction, including the final contract documents. Filtered view of the Master Register — edit items there, not here.
Ref | Pre-Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party | Folder (L2) | TYPE | Proposed File Name
3.03 | Spatial Coordination Report | Records the coordinated design status and unresolved interfaces. | Meridian | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0001_SpatialCoordinationReport
3.04 | Coordinated Architectural Design Package | Provides the controlled spatial and planning-compliant architectural design. | Meridian | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0002_CoordinatedArchitecturalDesi
3.05 | Coordinated Structural, Civil, Drainage and Levels Package | Coordinates primary engineering, drainage and external levels. | Relevant engineers | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0003_CoordinatedStructuralCivilDr
3.06 | Coordinated MEP and Final Heating/Ventilation Strategy | Coordinates services in space and freezes the principal systems. | MEP Designer | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0004_CoordinatedMEPAndFinalHeatin
3.07 | Developed Fire, Compartmentation and Building Regulations Compliance Package | Coordinates the fire and Building Regulations design basis. | Relevant designers | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0005_DevelopedFireCompartmentatio
3.08 | SOCOTEC Submission, Comments and Actions Register | Controls Building Control information and responses. | Client / Meridian | 3.30 Building Control & Compliance | BCC | PROJ-DDR-BCC-0001_SOCOTECSubmissionCommentsAnd
3.09 | Apartment Type, Area, Sales and Purchaser Information Pack | Maintains one controlled residential product and sales basis. | Client | 3.20 Detailed Specs, Product & Sales | SPC | PROJ-DDR-SPC-0001_ApartmentTypeAreaSalesAndPur
3.10 | External Works, Landscape, Parking, Refuse and Access Package | Coordinates the approved site design and interfaces. | Client | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0006_ExternalWorksLandscapeParkin
3.11 | Utilities, EV, PV and Incoming Services Coordination Pack | Coordinates connection requirements with the building and site design. | Client / Meridian | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0007_UtilitiesEVPVAndIncomingServ
3.12 | BIM, Clash Detection and Interface Resolution Report | Defines model responsibilities and records coordination outcomes where BIM is used. | Meridian | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0008_BIMClashDetectionAndInterfac
3.13 | Detailed Specifications, Finishes and Room Data Schedules | Defines the coordinated quality, performance and room requirements. | Client | 3.20 Detailed Specs, Product & Sales | SPC | PROJ-DDR-SPC-0002_DetailedSpecificationsFinish
3.14 | Final Employer's Requirements | States Client's final contractual scope, performance and information requirements. | Client | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0001_FinalEmployerSRequirements
3.18 | Final Design Responsibility and CDP Matrix | Allocates all contractor, consultant and specialist design obligations. | Meridian | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0002_FinalDesignResponsibilityAnd
3.19 | Design Freeze, Change Control and Coordination Readiness Report | Records the frozen baseline and authority to proceed to technical design. | Meridian / Client | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0003_DesignFreezeChangeControlAnd
4.01 | Final Contract Contractor's Proposals | Provides the final controlled Contractor-side contract design and scope response. | Meridian | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0004_FinalContractContractorSProp
4.02 | Final ER/CP Compliance, Departure and Clarification Schedule | Maintains the executed contractual reconciliation between ERs and CPs. | Meridian | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0005_FinalERCPComplianceDeparture
4.04 | IFC Architectural Technical Design Package | Provides coordinated architectural information suitable for construction. | Meridian / appointed architectural designer | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0001_IFCArchitecturalTechnicalDes
4.05 | IFC Structural, Civil, Drainage and Levels Package | Provides coordinated engineering information suitable for construction. | Relevant engineers | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0002_IFCStructuralCivilDrainageAn
4.06 | IFC MEP and Heating, Cooling, Ventilation Technical Package | Provides coordinated building-services design suitable for installation. | MEP / specialist designers | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0003_IFCMEPAndHeatingCoolingVenti
4.07 | Detailed Fire, Compartmentation and Fire-Stopping Package | Converts the fire strategy into coordinated construction information. | Relevant designers | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0004_DetailedFireCompartmentation
4.08 | Envelope, Roof, Balcony, Window and External Door Technical Package | Coordinates the complete weather, thermal and external-envelope design. | Relevant designers / CDP specialists | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0005_EnvelopeRoofBalconyWindowAnd
4.09 | Apartment, Kitchen, Bathroom, Door and Finishes Technical Package | Coordinates the residential product and internal finishes for procurement and construction. | Meridian / relevant designers | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0006_ApartmentKitchenBathroomDoor
4.10 | Utilities, EV, PV, Water and Sprinkler Technical Package | Coordinates final infrastructure and connection design. | Client / Meridian | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0007_UtilitiesEVPVWaterAndSprinkl
4.11 | Building Regulations, Transitional Evidence and Detailed Compliance Matrix | Maintains the formal regulatory basis and designer evidence. | Client / design team | 3.30 Building Control & Compliance | BCC | PROJ-DDR-BCC-0002_BuildingRegulationsTransitio
4.12 | SOCOTEC Submission, Comments, Approval and Inspection Tracker | Controls all Building Control submissions, comments, inspections and completion actions. | Client / Meridian | 3.30 Building Control & Compliance | BCC | PROJ-DDR-BCC-0003_SOCOTECSubmissionCommentsApp
4.13 | Work Package Schedule, Procurement Schedule and Work Package Documents | Controls the package list, procurement dates and the actual technical/commercial work packages. | Meridian | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0001_WorkPackageScheduleProcureme
4.14 | Specialist and Contractor Design Portion Submissions | Integrates specialist design into the permanent works. | Meridian / CDP specialists | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0002_SpecialistAndContractorDesig
4.15 | Technical Submittal, Material Approval, Sample and Benchmark Register | Controls products and quality standards before order or installation. | Meridian | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0003_TechnicalSubmittalMaterialAp
4.16 | Builders' Work, Openings, Penetrations, Clash and Interface Register | Coordinates physical interfaces before structure and partitions are released. | Meridian | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0004_BuildersWorkOpeningsPenetrat
4.17 | Planning Condition Discharge, Amendment and Compliance Register | Controls remaining conditions and any departure from the approved planning design. | Client | 3.70 Planning Discharge, Risk & Change | PRC | PROJ-DDR-PRC-0001_PlanningConditionDischargeAm
4.18 | Design Risk, Temporary/Permanent Works Interface and Residual Risk Register | Controls design-stage construction and maintenance risks. | CDM Principal Designer / Meridian | 3.70 Planning Discharge, Risk & Change | PRC | PROJ-DDR-PRC-0002_DesignRiskTemporaryPermanent
4.19 | RFI, Technical Query, Design Change and Decision Registers | Controls design queries and all change from the frozen baseline. | Meridian | 3.70 Planning Discharge, Risk & Change | PRC | PROJ-DDR-PRC-0003_RFITechnicalQueryDesignChang
4.20 | Testing, Commissioning, As-Built, O&M and Handover Information Strategy | Defines completion evidence before procurement and installation. | Meridian | 3.80 Commissioning & Readiness | CMR | PROJ-DDR-CMR-0001_TestingCommissioningAsBuiltO
4.21 | Technical Design Readiness Report | Records whether each package is ready for procurement and construction. | Meridian | 3.80 Commissioning & Readiness | CMR | PROJ-DDR-CMR-0002_TechnicalDesignReadinessRepo

## Design Folder Structure
Design Delivery — Folder Structure (Proposed)
L1 = procurement stage; L2 = deliverable grouping. Aligned to the 3-stage spine for simplicity. Confirm before adopting.
L1 Code | Level 1 Folder (Stage) | L2 Code | Level 2 Folder | TYPE | Lead Owner | Items
1.0 | Stage 1 - Bid & Tender
|  | 1.10 | Development & Investment Basis | DEV | Client | 8
|  | 1.20 | Project Brief & Scope | BRF | Client | 4
|  | 1.30 | Surveys, Planning & Statutory Baseline | PSB | Client | 7
|  | 1.40 | Utilities & Sustainability Brief | UTB | Client | 1
|  | 1.50 | Concept Design & Performance | CPT | Client | 11
|  | 1.60 | Tender Scope & Contractor's Proposals | TEN | Meridian | 3
2.0 | Stage 2 - Contract Award
|  | 2.10 | Pre-Con Execution & Governance | PEG | Client initially | 3
|  | 2.20 | Design Programme & Procurement | DPP | Meridian | 3
3.0 | Stage 3 - Pre-Construction
|  | 3.10 | Coordinated Design Packages | CRD | Meridian | 8
|  | 3.20 | Detailed Specs, Product & Sales | SPC | Client | 2
|  | 3.30 | Building Control & Compliance | BCC | Client | 3
|  | 3.40 | Final Contract Documents | FCD | Meridian | 5
|  | 3.50 | IFC Technical Packages | IFC | Meridian | 7
|  | 3.60 | Procurement & Specialist Design | PSD | Meridian | 4
|  | 3.70 | Planning Discharge, Risk & Change | PRC | Client | 3
|  | 3.80 | Commissioning & Readiness | CMR | Meridian | 2

## Master Register
PROJ Canalside Regency — Pre-Construction Delivery Master Register
Ref | Stage | Pre-Construction Document / Deliverable | Purpose / Assurance Provided | Include in Pack? | Status | Priority | Owner / Lead Party | Contributors | Audience | Due Date | Current Version | Storage Link / File Ref | Source / Basis | Notes / Action | Level 1 Folder | Level 2 Folder | TYPE | Proposed File Name
0.01 | Stage 1 - Bid & Tender | Development Business Case and Development Appraisal | Confirms the commercial case, development value and delivery assumptions. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0001_DevelopmentBusinessCaseAndDe
0.02 | Stage 1 - Bid & Tender | Client Strategic Brief | Defines Client's required project outcomes and success criteria. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0002_ClientStrategicBrief
0.03 | Stage 1 - Bid & Tender | Site Acquisition and Due Diligence Summary | Consolidates material site, title and development constraints. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0003_SiteAcquisitionAndDueDiligen
0.04 | Stage 1 - Bid & Tender | Feasibility and Development Options Appraisal | Records the options considered and why the approved development solution was selected. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0004_FeasibilityAndDevelopmentOpt
0.05 | Stage 1 - Bid & Tender | Planning and Development Capacity Appraisal | Records the planning policy and capacity basis preceding the approved permission. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0005_PlanningAndDevelopmentCapaci
0.06 | Stage 1 - Bid & Tender | Initial Development Programme | Sets the overall development, approvals, procurement and construction milestones. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0007_InitialDevelopmentProgramme
0.07 | Stage 1 - Bid & Tender | Development Risk, Abnormals and Procurement Strategy | Combines the principal development risks with the intended procurement and contract route. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.10 Development & Investment Basis | DEV | PROJ-DDR-DEV-0008_DevelopmentRiskAbnormalsAndP
1.01 | Stage 1 - Bid & Tender | Developed Project Brief | Translates Client's objectives into coordinated, measurable project requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0001_DevelopedProjectBrief
1.02 | Stage 1 - Bid & Tender | Development Specification and Quality Brief | Defines the intended development-wide quality and performance standard. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0002_DevelopmentSpecificationAndQ
1.03 | Stage 1 - Bid & Tender | Accommodation, Apartment Type and Area Schedule | Controls the approved unit mix and project area data. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0003_AccommodationApartmentTypeAn
1.09 | Stage 1 - Bid & Tender | Survey Requirements and Existing Information Register | Records required surveys and the status/reliability of existing information. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0001_SurveyRequirementsAndExistin
1.10 | Stage 1 - Bid & Tender | Planning and Statutory Approval Information Register | Creates the controlled index of the approved planning and statutory information. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0002_PlanningAndStatutoryApproval
1.11 | Stage 1 - Bid & Tender | Building Control Route and Transitional Regulations Record | Records why the project proceeds under the confirmed previous/transitional regulations route. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0003_BuildingControlRouteAndTrans
1.12 | Stage 1 - Bid & Tender | Utilities, Sustainability, Energy and EPC Brief | Defines utility capacity, infrastructure and performance requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.40 Utilities & Sustainability Brief | UTB | PROJ-DDR-UTB-0001_UtilitiesSustainabilityEnerg
1.13 | Stage 1 - Bid & Tender | Pre-Construction Information and CDM Design Risk Register | Provides existing safety information and records significant design risks. | TBC | Not Started |  | Client / CDM Principal Designer |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0004_PreConstructionInformationAn
1.14 | Stage 1 - Bid & Tender | Outline Employer's Requirements | Establishes the structure and content of Client's contractual requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.20 Project Brief & Scope | BRF | PROJ-DDR-BRF-0004_OutlineEmployerSRequirements
2.02 | Stage 1 - Bid & Tender | Planning Application and Supporting Documents Register | Indexes the historic application that achieved planning permission. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0005_PlanningApplicationAndSuppor
2.05 | Stage 1 - Bid & Tender | MEP Concept and Heating, Cooling and Ventilation Options Appraisal | Defines the building-services strategy and records the system-selection decision. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0004_MEPConceptAndHeatingCoolingA
3.01 | Stage 1 - Bid & Tender | Planning Decision Notice and Approved Drawing/Document Register | Establishes the definitive planning-approved baseline. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0006_PlanningDecisionNoticeAndApp
3.02 | Stage 1 - Bid & Tender | Planning Conditions, Section 106 and CIL Tracker | Controls every planning condition and obligation by trigger date. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.30 Surveys, Planning & Statutory Baseline | PSB | PROJ-DDR-PSB-0007_PlanningConditionsSection106
1.04 | Stage 2 - Contract Award | Project Execution Plan, Organisation and Appointment Schedule | Defines project governance, reporting, appointments and decision routes. | TBC | Not Started |  | Client initially / Meridian post-appointment |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 2 - Contract Award | 2.10 Pre-Con Execution & Governance | PEG | PROJ-DDR-PEG-0001_ProjectExecutionPlanOrganisa
1.05 | Stage 2 - Contract Award | Design Responsibility Matrix and RACI | Allocates design, coordination, review and acceptance responsibility. | TBC | Not Started |  | Client initially / Meridian post-appointment |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 2 - Contract Award | 2.10 Pre-Con Execution & Governance | PEG | PROJ-DDR-PEG-0002_DesignResponsibilityMatrixAn
1.06 | Stage 2 - Contract Award | Work Breakdown Structure and Scope Breakdown | Structures the project by system, trade, package and deliverable. | TBC | Not Started |  | Client initially / Meridian post-appointment |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 2 - Contract Award | 2.10 Pre-Con Execution & Governance | PEG | PROJ-DDR-PEG-0003_WorkBreakdownStructureAndSco
1.07 | Stage 2 - Contract Award | Design Programme and Information Release Schedule | Baselines design deliverables and approval periods against project need-by dates. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 2 - Contract Award | 2.20 Design Programme & Procurement | DPP | PROJ-DDR-DPP-0001_DesignProgrammeAndInformatio
1.08 | Stage 2 - Contract Award | Design Procurement and Long-Lead Schedule | Links appointments and procurement to required design outputs. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 2 - Contract Award | 2.20 Design Programme & Procurement | DPP | PROJ-DDR-DPP-0002_DesignProcurementAndLongLead
2.01 | Stage 2 - Contract Award | Concept Design Report and Concept Drawing Set | Records the coordinated concept response to the Project Brief. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0001_ConceptDesignReportAndConcep
2.03 | Stage 2 - Contract Award | Updated Accommodation and Development Area Schedule | Confirms the concept-stage unit and area data. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0002_UpdatedAccommodationAndDevel
2.04 | Stage 2 - Contract Award | Structural, Civil and Drainage Concept Strategy | Defines the structural form, foundations, drainage and civil engineering basis. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0003_StructuralCivilAndDrainageCo
2.06 | Stage 2 - Contract Award | Outline Fire and Life-Safety Strategy | Defines the concept fire-safety basis for the non-HRB residential building. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0005_OutlineFireAndLifeSafetyStra
2.07 | Stage 2 - Contract Award | Energy, SAP, EPC, Overheating and Acoustic Performance Strategy | Combines key performance studies that influence the fabric and MEP design. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0006_EnergySAPEPCOverheatingAndAc
2.08 | Stage 2 - Contract Award | Access, External Works, Landscape, Parking, Refuse and Security Strategy | Coordinates the main site and inclusive-access requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0007_AccessExternalWorksLandscape
2.09 | Stage 2 - Contract Award | Utilities, EV Charging, Solar PV and Incoming Services Strategy | Defines capacities, connection routes and energy-infrastructure requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0008_UtilitiesEVChargingSolarPVAn
2.10 | Stage 2 - Contract Award | Outline Specification and Updated Development Specification | Defines the concept performance and quality requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0009_OutlineSpecificationAndUpdat
2.11 | Stage 2 - Contract Award | Concept Cost, Value Engineering and Funding Technical Pack | Tests the concept against cost and funding requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0010_ConceptCostValueEngineeringA
2.12 | Stage 2 - Contract Award | Design Strategy Compliance, Risk and Readiness Report | Records whether the concept is sufficiently complete to proceed. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.50 Concept Design & Performance | CPT | PROJ-DDR-CPT-0011_DesignStrategyComplianceRisk
3.15 | Stage 2 - Contract Award | Statement of Works, Schedule of Works and Tender Scope Documents | Defines the works and tender information at project/package level. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.60 Tender Scope & Contractor's Proposals | TEN | PROJ-DDR-TEN-0001_StatementOfWorksScheduleOfWo
3.16 | Stage 2 - Contract Award | Tender Contractor's Proposals | Sets out Meridian's tender response to the Employer's Requirements. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.60 Tender Scope & Contractor's Proposals | TEN | PROJ-DDR-TEN-0002_TenderContractorSProposals
3.17 | Stage 2 - Contract Award | ER/CP Compliance, Qualification and Departure Schedule | Reconciles the Contractor's Proposals against every relevant ER requirement. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 1 - Bid & Tender | 1.60 Tender Scope & Contractor's Proposals | TEN | PROJ-DDR-TEN-0003_ERCPComplianceQualificationA
4.03 | Stage 2 - Contract Award | Master Design Delivery and Technical Submission Schedule | Controls all Technical Design design, review and approval dates. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 2 - Contract Award | 2.20 Design Programme & Procurement | DPP | PROJ-DDR-DPP-0003_MasterDesignDeliveryAndTechn
3.03 | Stage 3 - Pre-Construction | Spatial Coordination Report | Records the coordinated design status and unresolved interfaces. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0001_SpatialCoordinationReport
3.04 | Stage 3 - Pre-Construction | Coordinated Architectural Design Package | Provides the controlled spatial and planning-compliant architectural design. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0002_CoordinatedArchitecturalDesi
3.05 | Stage 3 - Pre-Construction | Coordinated Structural, Civil, Drainage and Levels Package | Coordinates primary engineering, drainage and external levels. | TBC | Not Started |  | Relevant engineers |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0003_CoordinatedStructuralCivilDr
3.06 | Stage 3 - Pre-Construction | Coordinated MEP and Final Heating/Ventilation Strategy | Coordinates services in space and freezes the principal systems. | TBC | Not Started |  | MEP Designer |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0004_CoordinatedMEPAndFinalHeatin
3.07 | Stage 3 - Pre-Construction | Developed Fire, Compartmentation and Building Regulations Compliance Package | Coordinates the fire and Building Regulations design basis. | TBC | Not Started |  | Relevant designers |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0005_DevelopedFireCompartmentatio
3.08 | Stage 3 - Pre-Construction | SOCOTEC Submission, Comments and Actions Register | Controls Building Control information and responses. | TBC | Not Started |  | Client / Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.30 Building Control & Compliance | BCC | PROJ-DDR-BCC-0001_SOCOTECSubmissionCommentsAnd
3.09 | Stage 3 - Pre-Construction | Apartment Type, Area, Sales and Purchaser Information Pack | Maintains one controlled residential product and sales basis. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.20 Detailed Specs, Product & Sales | SPC | PROJ-DDR-SPC-0001_ApartmentTypeAreaSalesAndPur
3.10 | Stage 3 - Pre-Construction | External Works, Landscape, Parking, Refuse and Access Package | Coordinates the approved site design and interfaces. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0006_ExternalWorksLandscapeParkin
3.11 | Stage 3 - Pre-Construction | Utilities, EV, PV and Incoming Services Coordination Pack | Coordinates connection requirements with the building and site design. | TBC | Not Started |  | Client / Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0007_UtilitiesEVPVAndIncomingServ
3.12 | Stage 3 - Pre-Construction | BIM, Clash Detection and Interface Resolution Report | Defines model responsibilities and records coordination outcomes where BIM is used. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.10 Coordinated Design Packages | CRD | PROJ-DDR-CRD-0008_BIMClashDetectionAndInterfac
3.13 | Stage 3 - Pre-Construction | Detailed Specifications, Finishes and Room Data Schedules | Defines the coordinated quality, performance and room requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.20 Detailed Specs, Product & Sales | SPC | PROJ-DDR-SPC-0002_DetailedSpecificationsFinish
3.14 | Stage 3 - Pre-Construction | Final Employer's Requirements | States Client's final contractual scope, performance and information requirements. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0001_FinalEmployerSRequirements
3.18 | Stage 3 - Pre-Construction | Final Design Responsibility and CDP Matrix | Allocates all contractor, consultant and specialist design obligations. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0002_FinalDesignResponsibilityAnd
3.19 | Stage 3 - Pre-Construction | Design Freeze, Change Control and Coordination Readiness Report | Records the frozen baseline and authority to proceed to technical design. | TBC | Not Started |  | Meridian / Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0003_DesignFreezeChangeControlAnd
4.01 | Stage 3 - Pre-Construction | Final Contract Contractor's Proposals | Provides the final controlled Contractor-side contract design and scope response. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0004_FinalContractContractorSProp
4.02 | Stage 3 - Pre-Construction | Final ER/CP Compliance, Departure and Clarification Schedule | Maintains the executed contractual reconciliation between ERs and CPs. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.40 Final Contract Documents | FCD | PROJ-DDR-FCD-0005_FinalERCPComplianceDeparture
4.04 | Stage 3 - Pre-Construction | IFC Architectural Technical Design Package | Provides coordinated architectural information suitable for construction. | TBC | Not Started |  | Meridian / appointed architectural designer |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0001_IFCArchitecturalTechnicalDes
4.05 | Stage 3 - Pre-Construction | IFC Structural, Civil, Drainage and Levels Package | Provides coordinated engineering information suitable for construction. | TBC | Not Started |  | Relevant engineers |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0002_IFCStructuralCivilDrainageAn
4.06 | Stage 3 - Pre-Construction | IFC MEP and Heating, Cooling, Ventilation Technical Package | Provides coordinated building-services design suitable for installation. | TBC | Not Started |  | MEP / specialist designers |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0003_IFCMEPAndHeatingCoolingVenti
4.07 | Stage 3 - Pre-Construction | Detailed Fire, Compartmentation and Fire-Stopping Package | Converts the fire strategy into coordinated construction information. | TBC | Not Started |  | Relevant designers |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0004_DetailedFireCompartmentation
4.08 | Stage 3 - Pre-Construction | Envelope, Roof, Balcony, Window and External Door Technical Package | Coordinates the complete weather, thermal and external-envelope design. | TBC | Not Started |  | Relevant designers / CDP specialists |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0005_EnvelopeRoofBalconyWindowAnd
4.09 | Stage 3 - Pre-Construction | Apartment, Kitchen, Bathroom, Door and Finishes Technical Package | Coordinates the residential product and internal finishes for procurement and construction. | TBC | Not Started |  | Meridian / relevant designers |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0006_ApartmentKitchenBathroomDoor
4.10 | Stage 3 - Pre-Construction | Utilities, EV, PV, Water and Sprinkler Technical Package | Coordinates final infrastructure and connection design. | TBC | Not Started |  | Client / Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.50 IFC Technical Packages | IFC | PROJ-DDR-IFC-0007_UtilitiesEVPVWaterAndSprinkl
4.11 | Stage 3 - Pre-Construction | Building Regulations, Transitional Evidence and Detailed Compliance Matrix | Maintains the formal regulatory basis and designer evidence. | TBC | Not Started |  | Client / design team |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.30 Building Control & Compliance | BCC | PROJ-DDR-BCC-0002_BuildingRegulationsTransitio
4.12 | Stage 3 - Pre-Construction | SOCOTEC Submission, Comments, Approval and Inspection Tracker | Controls all Building Control submissions, comments, inspections and completion actions. | TBC | Not Started |  | Client / Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.30 Building Control & Compliance | BCC | PROJ-DDR-BCC-0003_SOCOTECSubmissionCommentsApp
4.13 | Stage 3 - Pre-Construction | Work Package Schedule, Procurement Schedule and Work Package Documents | Controls the package list, procurement dates and the actual technical/commercial work packages. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0001_WorkPackageScheduleProcureme
4.14 | Stage 3 - Pre-Construction | Specialist and Contractor Design Portion Submissions | Integrates specialist design into the permanent works. | TBC | Not Started |  | Meridian / CDP specialists |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0002_SpecialistAndContractorDesig
4.15 | Stage 3 - Pre-Construction | Technical Submittal, Material Approval, Sample and Benchmark Register | Controls products and quality standards before order or installation. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0003_TechnicalSubmittalMaterialAp
4.16 | Stage 3 - Pre-Construction | Builders' Work, Openings, Penetrations, Clash and Interface Register | Coordinates physical interfaces before structure and partitions are released. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.60 Procurement & Specialist Design | PSD | PROJ-DDR-PSD-0004_BuildersWorkOpeningsPenetrat
4.17 | Stage 3 - Pre-Construction | Planning Condition Discharge, Amendment and Compliance Register | Controls remaining conditions and any departure from the approved planning design. | TBC | Not Started |  | Client |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.70 Planning Discharge, Risk & Change | PRC | PROJ-DDR-PRC-0001_PlanningConditionDischargeAm
4.18 | Stage 3 - Pre-Construction | Design Risk, Temporary/Permanent Works Interface and Residual Risk Register | Controls design-stage construction and maintenance risks. | TBC | Not Started |  | CDM Principal Designer / Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.70 Planning Discharge, Risk & Change | PRC | PROJ-DDR-PRC-0002_DesignRiskTemporaryPermanent
4.19 | Stage 3 - Pre-Construction | RFI, Technical Query, Design Change and Decision Registers | Controls design queries and all change from the frozen baseline. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.70 Planning Discharge, Risk & Change | PRC | PROJ-DDR-PRC-0003_RFITechnicalQueryDesignChang
4.20 | Stage 3 - Pre-Construction | Testing, Commissioning, As-Built, O&M and Handover Information Strategy | Defines completion evidence before procurement and installation. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.80 Commissioning & Readiness | CMR | PROJ-DDR-CMR-0001_TestingCommissioningAsBuiltO
4.21 | Stage 3 - Pre-Construction | Technical Design Readiness Report | Records whether each package is ready for procurement and construction. | TBC | Not Started |  | Meridian |  |  |  | Rev P01 |  | Design Delivery Register Rev P01 |  | Stage 3 - Pre-Construction | 3.80 Commissioning & Readiness | CMR | PROJ-DDR-CMR-0002_TechnicalDesignReadinessRepo

## Folder Coverage
Folder Coverage — items per stage
L1 Code | Level 1 Folder (Stage) | Items
1.0 | Stage 1 - Bid & Tender | 20
2.0 | Stage 2 - Contract Award | 19
3.0 | Stage 3 - Pre-Construction | 34
| TOTAL | 73

## Dashboard
PROJ Pre-Construction Delivery — Dashboard
Live counts off the Master Register. Set Include / Status / Priority / Due Date there and these update.
Control | Count | Progress | Result
Total deliverables | 73 | Applicability reviewed | 0%
Included - Yes | 0 | Completed | 0
Excluded - No | 0 | In progress | 0
Still TBC | 73 | Not started | 73
Critical priority | 0 | Overdue open | 0
Deliverables by owner / lead party |  |  |  | Deliverables by stage
Owner / Lead Party | Documents |  |  | Stage | Documents
CDM Principal Designer / Meridian | 1 |  |  | Stage 1 - Bid & Tender | 20
Client | 35 |  |  | Stage 2 - Contract Award | 19
Client / CDM Principal Designer | 1 |  |  | Stage 3 - Pre-Construction | 34
Client / Meridian | 4 |  |  | TOTAL | 73
Client / design team | 1
Client initially / Meridian post-appointment | 3
MEP / specialist designers | 1
MEP Designer | 1
Meridian | 17
Meridian / CDP specialists | 1
Meridian / Client | 1
Meridian / appointed architectural designer | 1
Meridian / relevant designers | 1
Relevant designers | 2
Relevant designers / CDP specialists | 1
Relevant engineers | 2

## Guidance & Lookups
How to Use This Register
Field | Required use | Do not do | Owner / Lead Party Lookup | Values
Stage | Set by procurement gate: 1 Bid & Tender / 2 Contract Award / 3 Pre-Construction. | Do not leave a deliverable unstaged — every item must sit in one gate. | CDM Principal Designer / Meridian | Yes
Include in Pack? | Set Yes / No / TBC once applicability is confirmed. | Do not leave items at TBC once scope is fixed. | Client | No
Status | Not Started / In Progress / Complete against actual issue status. | Do not mark Complete before formal issue/acceptance. | Client / CDM Principal Designer | TBC
Priority | Critical / High / Medium by delivery risk. Left blank deliberately — source register carried no priority. | Do not invent criticality; base it on programme need-by dates. | Client / Meridian | Not Started
Owner / Lead Party | Verbatim from source. Note Stage 1 mixes Meridian submissions and client tender info. | Do not silently re-assign a Client/designer deliverable to Meridian. | Client / design team | In Progress
Due Date | Link to the design programme / information release need-by date. | Do not use arbitrary dates disconnected from programme. | Client initially / Meridian post-appointment | Complete
TYPE / File Name | Proposed PROJ-DDR-[TYPE]-[####]. Confirm before adopting. | Do not overwrite the design Ref (0.01-4.21). | MEP / specialist designers | Critical
|  |  | MEP Designer | High
|  |  | Meridian | Medium
Meridian / CDP specialists
Meridian / Client
Meridian / appointed architectural designer
Meridian / relevant designers
Relevant designers
Relevant designers / CDP specialists
Relevant engineers