## Pre-Construction Register
P5RS — CANALSIDE REGENCY APARTMENTS ¦ PRE-CONSTRUCTION DOCUMENT DELIVERY REGISTER
Ref | Pre-Construction Document / Deliverable | Purpose / Assurance Provided | Owner / Lead Party
A. Development Strategy and Investment Basis
0.01 | Development Business Case and Development Appraisal | Confirms the commercial case, development value and delivery assumptions. | CSRA
0.02 | Client Strategic Brief | Defines CSRA's required project outcomes and success criteria. | CSRA
0.03 | Site Acquisition and Due Diligence Summary | Consolidates material site, title and development constraints. | CSRA
0.04 | Feasibility and Development Options Appraisal | Records the options considered and why the approved development solution was selected. | CSRA
0.05 | Planning and Development Capacity Appraisal | Records the planning policy and capacity basis preceding the approved permission. | CSRA
0.06 | Initial Cost Plan and Funding Assumptions | Establishes the budget envelope and major cost allowances. | CSRA
0.07 | Initial Development Programme | Sets the overall development, approvals, procurement and construction milestones. | CSRA
0.08 | Development Risk, Abnormals and Procurement Strategy | Combines the principal development risks with the intended procurement and contract route. | CSRA
B. Project Brief, Scope and Delivery Planning
1.01 | Developed Project Brief | Translates CSRA's objectives into coordinated, measurable project requirements. | CSRA
1.02 | Development Specification and Quality Brief | Defines the intended development-wide quality and performance standard. | CSRA
1.03 | Accommodation, Apartment Type and Area Schedule | Controls the approved unit mix and project area data. | CSRA
1.04 | Project Execution Plan, Organisation and Appointment Schedule | Defines project governance, reporting, appointments and decision routes. | CSRA initially / Meridian post-appointment
1.05 | Design Responsibility Matrix and RACI | Allocates design, coordination, review and acceptance responsibility. | CSRA initially / Meridian post-appointment
1.06 | Work Breakdown Structure and Scope Breakdown | Structures the project by system, trade, package and deliverable. | CSRA initially / Meridian post-appointment
1.07 | Design Programme and Information Release Schedule | Baselines design deliverables and approval periods against project need-by dates. | Meridian
1.08 | Design Procurement and Long-Lead Schedule | Links appointments and procurement to required design outputs. | Meridian
1.09 | Survey Requirements and Existing Information Register | Records required surveys and the status/reliability of existing information. | CSRA
1.10 | Planning and Statutory Approval Information Register | Creates the controlled index of the approved planning and statutory information. | CSRA
1.11 | Building Control Route and Transitional Regulations Record | Records why the project proceeds under the confirmed previous/transitional regulations route. | CSRA
1.12 | Utilities, Sustainability, Energy and EPC Brief | Defines utility capacity, infrastructure and performance requirements. | CSRA
1.13 | Pre-Construction Information and CDM Design Risk Register | Provides existing safety information and records significant design risks. | CSRA / CDM Principal Designer
1.14 | Outline Employer's Requirements | Establishes the structure and content of CSRA's contractual requirements. | CSRA
C. Design Strategy and Performance Definition
2.01 | Concept Design Report and Concept Drawing Set | Records the coordinated concept response to the Project Brief. | CSRA
2.02 | Planning Application and Supporting Documents Register | Indexes the historic application that achieved planning permission. | CSRA
2.03 | Updated Accommodation and Development Area Schedule | Confirms the concept-stage unit and area data. | CSRA
2.04 | Structural, Civil and Drainage Concept Strategy | Defines the structural form, foundations, drainage and civil engineering basis. | CSRA
2.05 | MEP Concept and Heating, Cooling and Ventilation Options Appraisal | Defines the building-services strategy and records the system-selection decision. | CSRA
2.06 | Outline Fire and Life-Safety Strategy | Defines the concept fire-safety basis for the non-HRB residential building. | CSRA
2.07 | Energy, SAP, EPC, Overheating and Acoustic Performance Strategy | Combines key performance studies that influence the fabric and MEP design. | CSRA
2.08 | Access, External Works, Landscape, Parking, Refuse and Security Strategy | Coordinates the main site and inclusive-access requirements. | CSRA
2.09 | Utilities, EV Charging, Solar PV and Incoming Services Strategy | Defines capacities, connection routes and energy-infrastructure requirements. | CSRA
2.10 | Outline Specification and Updated Development Specification | Defines the concept performance and quality requirements. | CSRA
2.11 | Concept Cost, Value Engineering and Funding Technical Pack | Tests the concept against cost and funding requirements. | CSRA
2.12 | Design Strategy Compliance, Risk and Readiness Report | Records whether the concept is sufficiently complete to proceed. | CSRA
D. Coordinated Design and Contract Definition
3.01 | Planning Decision Notice and Approved Drawing/Document Register | Establishes the definitive planning-approved baseline. | CSRA
3.02 | Planning Conditions, Section 106 and CIL Tracker | Controls every planning condition and obligation by trigger date. | CSRA
3.03 | Spatial Coordination Report | Records the coordinated design status and unresolved interfaces. | Meridian
3.04 | Coordinated Architectural Design Package | Provides the controlled spatial and planning-compliant architectural design. | Meridian
3.05 | Coordinated Structural, Civil, Drainage and Levels Package | Coordinates primary engineering, drainage and external levels. | Relevant engineers
3.06 | Coordinated MEP and Final Heating/Ventilation Strategy | Coordinates services in space and freezes the principal systems. | MEP Designer
3.07 | Developed Fire, Compartmentation and Building Regulations Compliance Package | Coordinates the fire and Building Regulations design basis. | Relevant designers
3.08 | SOCOTEC Submission, Comments and Actions Register | Controls Building Control information and responses. | CSRA / Meridian
3.09 | Apartment Type, Area, Sales and Purchaser Information Pack | Maintains one controlled residential product and sales basis. | CSRA
3.10 | External Works, Landscape, Parking, Refuse and Access Package | Coordinates the approved site design and interfaces. | CSRA
3.11 | Utilities, EV, PV and Incoming Services Coordination Pack | Coordinates connection requirements with the building and site design. | CSRA / Meridian
3.12 | BIM, Clash Detection and Interface Resolution Report | Defines model responsibilities and records coordination outcomes where BIM is used. | Meridian
3.13 | Detailed Specifications, Finishes and Room Data Schedules | Defines the coordinated quality, performance and room requirements. | CSRA
3.14 | Final Employer's Requirements | States CSRA's final contractual scope, performance and information requirements. | CSRA
3.15 | Statement of Works, Schedule of Works and Tender Scope Documents | Defines the works and tender information at project/package level. | CSRA
3.16 | Tender Contractor's Proposals | Sets out Meridian's tender response to the Employer's Requirements. | Meridian
3.17 | ER/CP Compliance, Qualification and Departure Schedule | Reconciles the Contractor's Proposals against every relevant ER requirement. | Meridian
3.18 | Final Design Responsibility and CDP Matrix | Allocates all contractor, consultant and specialist design obligations. | Meridian
3.19 | Design Freeze, Change Control and Coordination Readiness Report | Records the frozen baseline and authority to proceed to technical design. | Meridian / CSRA
E. Technical, Procurement and Construction Readiness
4.01 | Final Contract Contractor's Proposals | Provides the final controlled Contractor-side contract design and scope response. | Meridian
4.02 | Final ER/CP Compliance, Departure and Clarification Schedule | Maintains the executed contractual reconciliation between ERs and CPs. | Meridian
4.03 | Master Design Delivery and Technical Submission Schedule | Controls all Technical Design design, review and approval dates. | Meridian
4.04 | IFC Architectural Technical Design Package | Provides coordinated architectural information suitable for construction. | Meridian / appointed architectural designer
4.05 | IFC Structural, Civil, Drainage and Levels Package | Provides coordinated engineering information suitable for construction. | Relevant engineers
4.06 | IFC MEP and Heating, Cooling, Ventilation Technical Package | Provides coordinated building-services design suitable for installation. | MEP / specialist designers
4.07 | Detailed Fire, Compartmentation and Fire-Stopping Package | Converts the fire strategy into coordinated construction information. | Relevant designers
4.08 | Envelope, Roof, Balcony, Window and External Door Technical Package | Coordinates the complete weather, thermal and external-envelope design. | Relevant designers / CDP specialists
4.09 | Apartment, Kitchen, Bathroom, Door and Finishes Technical Package | Coordinates the residential product and internal finishes for procurement and construction. | Meridian / relevant designers
4.10 | Utilities, EV, PV, Water and Sprinkler Technical Package | Coordinates final infrastructure and connection design. | CSRA / Meridian
4.11 | Building Regulations, Transitional Evidence and Detailed Compliance Matrix | Maintains the formal regulatory basis and designer evidence. | CSRA / design team
4.12 | SOCOTEC Submission, Comments, Approval and Inspection Tracker | Controls all Building Control submissions, comments, inspections and completion actions. | CSRA / Meridian
4.13 | Work Package Schedule, Procurement Schedule and Work Package Documents | Controls the package list, procurement dates and the actual technical/commercial work packages. | Meridian
4.14 | Specialist and Contractor Design Portion Submissions | Integrates specialist design into the permanent works. | Meridian / CDP specialists
4.15 | Technical Submittal, Material Approval, Sample and Benchmark Register | Controls products and quality standards before order or installation. | Meridian
4.16 | Builders' Work, Openings, Penetrations, Clash and Interface Register | Coordinates physical interfaces before structure and partitions are released. | Meridian
4.17 | Planning Condition Discharge, Amendment and Compliance Register | Controls remaining conditions and any departure from the approved planning design. | CSRA
4.18 | Design Risk, Temporary/Permanent Works Interface and Residual Risk Register | Controls design-stage construction and maintenance risks. | CDM Principal Designer / Meridian
4.19 | RFI, Technical Query, Design Change and Decision Registers | Controls design queries and all change from the frozen baseline. | Meridian
4.20 | Testing, Commissioning, As-Built, O&M and Handover Information Strategy | Defines completion evidence before procurement and installation. | Meridian
4.21 | Technical Design Readiness Report | Records whether each package is ready for procurement and construction. | Meridian