## Risk Register
Project:
Address:
Document: Commercial Risk Register
Document ref:
Last Updated:
Register Start Date:
Version / Ref:
Prepared By (Commercial Manager):
Reviewed By (PM / Director):
Approved By:
Commercial-Focused Risk Register
RISK IDENTIFICATION | [6 empty] | RISK DESCRIPTION & CONTRACT POSITION |  |  |  | FINANCIAL & PROGRAMME EXPOSURE |  |  |  |  | TIMING & TRIGGERS |  |  |  |  | MITIGATION & CONTROL |  |  | RESIDUAL RISK POSITION |  |  |  | STATUS & REPORTING
Risk ID | Risk Title | Category (Cost / Programme / Design / H&S / Legal / Other) | Risk Type (Threat / Opportunity) | Phase (Pre-Construction / Construction / PC / Defects) | Package Ref / Area (e.g. G01, M01) | Source / Origin (Design / Site Condition / Client / Contract / Supply Chain) | Detailed Description (Cause & Effect) | Contractual Position | Clause Reference | Compensation Event | Financial Provision | Potential Recovery Route (EOT / Loss & Expense / Insurance / Back-to-Back) | Linked CVR / Cost Code Ref | Linked Contingency Item Ref | Funding Assumption (Budget / Contingency / Client / Insurance / Claim) | Risk Trigger/Ciritical decision date | Pre-Mitigation Likelihood (1–5) | Pre-Mitigation Impact – Cost (£) | Pre-Mitigation Impact – Time (Days) | Pre-Mitigation Rating (H/M/L) | Mitigation Actions / Strategy | Action Owner | Target Date | Residual Likelihood (1–5) | Residual Impact – Cost (£) | Residual Impact – Time (Days) | Residual Rating (H/M/L) | Current Status (Open / Monitoring / Closed) | Notes / Comments
R-001 | Ground Conditions – Piling Depth | Cost / Programme | Threat | Pre-Construction / Early Works | G01 – Groundworks & Substructure | Site Condition / Surveys | Borehole data limited; actual ground conditions may require deeper piles, increasing cost and time for foundations. |  |  |  |  | Potential recovery via risk allowance agreement and value engineering elsewhere. | CVR-G01-01 | CONT-001 | Contingency |  | 3 | 150000 | 21 | H | Allow provisional sum and contingency; obtain additional ground investigation; early engagement with piling contractor. | Commercial Manager / Engineer |  | 2 | 50000 | 7 | M | Monitoring | Review once final piling design received.
R-002 | MEP Market Pricing Volatility | Cost | Threat | Pre-Construction | M01 – MEP | Supply Chain / Market | MEP subcontract prices may come in higher than budget due to inflation and supply chain constraints. |  |  |  |  | Potential partial recovery via client VE approval or scope adjustments. | CVR-M01-01 |  | Budget / Contingency |  | 4 | 200000 | 0 | H | Early market testing; negotiate with framework partners; consider specification alternatives and VE options. | Commercial Manager |  | 3 | 80000 | 0 | M | Open | Align with VE register and procurement strategy.

## List
Contractual Position | Financial Provision
Client Risk | Included in Tender
Contractor Risk | Contingency Held
Shared Risk | Excluded
Undefined | Transfer to Subcontractor